Creating Low Cost

A Tactical Plan

In

Powering the New American Hospital

Part of the Best Practice Series

In

Developed for the Gold Standard Management Institute, this work is made available pro bono to the leaders of America’s healthcare organizations. All forms, titles, designs, and written operating instructions are exclusively the intellectual property and registered copyright of GSM Institute, Management House, and Beta Group, Ltd.  No use of these materials is allowed beyond the Terms

of Use agreement.  Any infringement or commercial use will make us extremely cranky and irritated.

TABLE OF CONTENTS

Initiatives   	Page

MAC Administration Instructions	 5

Executive Introduction 	 7

Module Leader & Initiative Teamleader Instructions 	 9

Initiative Team Instructions 	 13

LC.1	Preparation For Session IV and Changes Addressed At

The Uncommon Leader Session	14

LC.1.2	Change Elements Introduced By MHI At TUL

Session	15

LC.1.3	Process Incoming Manager Suggestions From TUL

Session	16

LC.1.4	“What I Want To See In A Proposal” By The CEO	17

LC.1.5	Develop Low Cost Tactical Plan	19

LC.1.6	Conduct People Climate Audit In Preparation For CI 	22

LC.1.7	Staff Swapping	24

LC.2	Low Cost Initiatives For People Productivity	26

LC.2.1	Develop People Productivity	27

LC.2.2	Add Tools As Primary Strategy To Make People Time	29

LC.2.3	Review Of Decision Times	30

LC.2.4	Power Up Down Times	32

LC.2.5	Develop Lite Duty Return-To-Work Program	33

LC.2.6	Out-Source Sideline Operations	34

LC.2.7	Education/Conference Audit	35

LC.2.8	Evaluate Information Services	36

LC.2.9	Review On-The-Job Training Processes	37

LC.2.10	Review Reasons For Associate Overtime	38

LC.2.11	Evaluate Patient Preparation Protocols	39

LC.2.12	Standardize Common Patient Care Administrative

Processes	40

LC.2.13	Standardize Common Administrative Clerical Processes	41

LC.3	Low Cost Initiatives For Financial Processes	43

LC.3.1	Install New Policy: All Service Contracts Require

A Full Rebidding Process	44

LC.3.2	Manage Private Pay Customers	45

LC.3.3	Maximize Cash Flow 	46

LC.3.4	Evaluate Accounts Payable Schedule	48

LC.3.5	Maximize Speed Of Service To Billing Cycle	49

LC.3.6	Eliminate Lost Charges	50

LC.3.7	Review The Timing Of Budget Reports	52

LC.3.8	Evaluate Furniture/Equipment Storage	53

LC.3.9	Evaluation Of Paid Medical Directors	54

LC.3.10	Review The Cost Management Of Marketing Needs	55

LC.3.11	Review Organizational Marketing Costs	56

LC.3.12	Review Budget Variance Reporting Practices—

Standardize	57

LC.3.13	Evaluate The Policy/Practices Of Providing Associates

With Lab Coats, Kleenex, Coffee & Other Creature

Comforts	58

LC.3.14	Review Precertification Process To Capture Revenues	59

LC.3.15	Review Medical Documentation For Reimbursement	60

LC.4	Low cost Initiatives For Operating Processes	61

LC.4.1	Identify Service Lines	62

LC.4.2	Redesign Executive Structure To Reflect Horizontally

Flexible Organization	65

LC.4.3	Standardize Supplies; Reduce Number Of Suppliers	67

LC.4.4	Redesign Organization Structure To Streamline

Communications	68

LC.4.5	Eliminate No/Low Value-Added Services	70

LC.4.6	Paper Systems Condensing	71

LC.4.7	Revisit Pay Evaluation Practices	73

LC.4.8	Locate and Reduce Areas Of Waste—Cost Containment

Audit	74

LC.4.9 	Natural Resources Management Audit	75

LC.4.10	Patient Transportation Analysis	76

LC.4.11	Review Toxic Waste Management Process/Costs	78

LC.4.12	Review and Revise Catering Requests And Guidelines	79

LC.4.13	Review Purchasing Process	80

LC.4.14	Review The Life Span And Repair Tendencies Of

Durable Medical Equipment	82

LC.4.15	Conduct Cost Analysis Of Internal Staff vs Purchased

Services For All External Services Used.	83

LC.4.16	Consider Substituting Reusable Materials For

Disposable Materials	84

LC.4.17	Review The Policy/Practice On Free Meals In The

Cafeteria	85

LC.4.18	Review The Procedures & Protocols For Recycling

Expensive Materials and Supplies	86

LC.4.19	Evaluate Hospital Mailings And Costs	87

LC.4.20	Manage The Costs of Printing/Duplication	88

LC.4.21	Personal Use of Facility Services	89

LC.4.22	Develop A Process For Handling A Large Number

Of Referrals At One Time To Avoid Customer Delay

And Frustration	90

LC.5	Low Cost Initiatives For Managing Innovation	91

LC.5.1	Manage Innovation	92

LC.5.2	Resourcing & Rewarding Innovation	93

LC.5.3	Measure & Set Goals For Innovation	94

LC.5.4	Install The Idea Engine	96

LC.5.5	Develop Reward & Recognition For Low Cost

Improvement	97

LC.5.6	Standardize Common Patient Care Administrative

Processes	98

LC.6	Begin Physician Focus On Low Cost Initiatives	99

LC.6.1	Physician Utilization Of Care Maps/Clinical Protocols	100

LC.6.2	Evaluate The Use Of Economic Credentialing For

Physicians	101

LC.6.3	Review Services Provided To Physicians &

Cost/Benefit Analysis Of The Services	102

LC.6.4	Evaluate The Contents Of The New Hire/Associate

Physical Exam For Appropriateness &

Cost Effectiveness	103

LC.6.5	Evaluate The Possibilities Of Standing Physician

Orders For High Need, High Patient Load/Traffic Areas	104

MAC ADMINISTRATION INSTRUCTIONS

NOTE TO MAC & MODULE LEADER:  These instructions are provided for your use, and should not be included in the packets duplicated and distributed to participants in the Low Cost Initiative Teams.

The Low Cost Strategy contains a number of Initiatives, each to be headed by an Initiative Teamleader.  Coordination of the actions and results of the Initiative Teams comprise the overall Low Cost Strategy.  Administration of the Strategy is as follows:

1.	The Module Leader is chosen by the MAC, in conjunction with the CEO.  The Module Leader is responsible for the completion of Low Cost Strategy Guide  as well as the Low Cost Tactical Plan.

2.	The Module Leader, in conjunction with the MAC, selects the Initiative Teamleaders.  Initiative Teamleaders chair their respective Initiative Teams.

3.	Initiative Teams work through their assigned projects, often in conjunction with other Initiative Teams.  Initiative Teamleaders (being the Chairs of these groups) meet to develop a prioritized list of tasks.  Prescribed time lines are to be met.  In the event that you cannot do all of the Tasks in the prescribed timeframes, this coordinated effort to prioritize becomes most important.  This is most crucial in the Low Cost Strategy  because these actions drive the balance of the NAH effort.

4.	The Low Cost Strategy  Module Leader is to create an organized work chart for the implementation and integration of all Tasks in this Guide.  The Chair is to include the following data for each Task.

•	Responsible party for each Task.  (This is usually

the Initiative Task Leader and the DIG Chair.)

•	Date the Task is to begin.

•	Date the work is to be completed.

•	Expected results including return on investment figures (ROI).

•	Actual results achieved, including return on investment figures.

In any case, where there is no ROI recognized, or the ROI is less than $5,000 or 10% of the current cost of the process, whichever is greater, the MAC is to revisit the work that was done and push for a more complete approach and more creative thinking.  The opportunities for low cost achievements are usually significantly greater than these guidelines, and thus should be achievable.  The challenge will be to break through the old thinking and identify new ways of doing old work.

A standard return on investment (ROI) formula should have been developed prior to the start of TUL and used by all Task/DIG Initiatives to determine the value of their work.  The ROI formula must be simple in its format.  The goal is not exact accounting, but rather the best estimate, on a most conservative basis, of the value of the changes.  When there is question as to which number or figure to use in the calculation of the ROI, it is recommended that the rule of thumb be to take the smaller or more conservative figure to calculate ROI.

5.	A copy of the Executive Introduction to the Low Cost Strategy  is to be distributed to the CEO.

EXECUTIVE INTRODUCTION

The Low Cost Strategy is an organized approach to reducing administrative and operational costs in your organization.  Completion of the Initiatives within the strategy and additional suggested improvements significantly contribute to making your organization the provider of choice.

This Strategy is comprised of a coordination group and six major Initiatives, some of which include multiple Tasks.  The objective is to reduce costs through standardization of practices, analysis of resource utilization, location, management and redesign or reorganization of work in each department and for each service line.  A service line is a grouping of processes and services for a particular type of patient.  For example, typical services lines:

•	Cardiology

•	Oncology

•	Surgical services

•	Women’s services

•	Emergency services, etc.

Current policies, practices, and procedures should be challenged.  It is expected that new ways of doing old things will be recommended, as well as new ways of doing new things.  Your support and approval for pilot programs and policies is imperative to the spirit of an excellent organization.  The degree of success that each organization will have with this module is directly correlated to the degree of new thinking that managers and executives are capable of as well as the degree of follow through that department heads and executives exhibit with each Task.

To make change is difficult under any circumstances.  To motivate change in others is more difficult still.  Follow through by the CEO’s office with corresponding rewards and recognition for work well done, and penalties for non compliance, up to and including dismissal or demotion, are not unreasonable or unexpected.  It is inevitable that some managers, and perhaps even executives, will not do the work, thus dragging down the balance of the organization and fragmenting the achievement of organizational objectives.  Be aware of this possibility and be prepared to deal with it in an effective manner.

There are great opportunities for improvements in every department and operation of the organization.  These Tasks will direct the energies of the people to find troubled areas and correct them.  The CEO and MAC are responsible for follow-up in order to realize massive organizational results.

Who Is Responsible For The Low Cost Strategy?

One Module Leader will be assigned to the Low Cost Strategy.  The Module Leader is responsible for the successful completion of the Low Cost Strategy.  S/he acts as Chairperson to coordinate the Low Cost Strategy Initiative Teams and orchestrates the overall development and implementation of the strategy.  The Module Leader is assisted by Initiative Teamleaders directing specific Tasks in their respective areas.  A dotted-line reporting relationship exists between the MAC and Module Leader with both parties being of equal authority.  The MAC, however, remains responsible for overseeing the completion of all aspects of the organization change effort, and for assisting the Module Leader in removing barriers to achieving this goal.  Both the MAC and Module Leader have a direct reporting relationship to the CEO.  In the event the Module Leader is not achieving the specified necessary results, the MAC is to notify the CEO.

Because prescribed timeframes are crucial to the development and implementation of the Low Cost Strategy, the person assigned as Module Leader must be organized, results-oriented, unbiased toward current practices or policies, a new-thinker, and in total support of the NAH philosophy.

This assignment may or may not be given to the management engineering executive or finance professional.  It should be assigned to the individual with the greatest probability of successfully completing the Tasks.  Considerations in making this assignment should include individual:

•	Skill level

• 	Technical knowledge level

•	Leadership ability

•	Time availability

•	Commitment to new delivery designs

•	Ability to follow/analyze work systems and projects

If someone other than the management engineering executive is selected as the Module Leader, then the management engineering executive should be assigned to the Low Cost Strategy team as an Initiative Teamleader.

The Module Leader position carries with it the functional authority of a Vice President for purposes of implementing the strategy.

Structure Of Low Cost Strategy

The Low Cost Strategy is comprised of a number of people:

•	1 Module Leader/Low Cost Leader.

• 	6 or less Initiative Teamleaders.  More than one Initiative can be assigned to an individual depending on their time and talent.

MODULE LEADER & INITIATIVE TEAMLEADER INSTRUCTIONS

As the Leader and Chairperson, your responsibility is to use the Low Cost Strategy Guide and DIGs developed by Initiative Teams to carry out and embellish a comprehensive Low Cost Tactical Plan, including specific assignments, accountable parties, and due dates for implementation.  The final accountability and responsibility for the strategy design, implementation, and results, lies with the Module Leader.  To organize this work, the Module Leader should follow these steps:

1.	Read this manual thoroughly before taking any action.

2.	With the MAC, select Initiative Teamleaders.  There should be one Initiative Teamleader for each Low Cost Strategy Initiative.  You may assign more than one Initiative to a person depending on the individuals’ time and talent availability.  An Initiative Teamleader can be any responsible supervisory or managerial person.  However, DIGs that are created to carry out an assigned Task should be comprised of at least 50% Associates, with the balance being technical experts in the area of work the DIG is involved with.

Qualities to consider in selecting Initiative Teamleaders:

•	Results-oriented.

•	Open-minded and creative.

•	Ability to simultaneously coordinate interrelated and sometimes very complex DIGs.

•	Willing to work extra hours and expend extra effort.

•	Viewed as politically neutral.

•	Able to devote large amounts of time to this assignment.

•	Thought-leader, open to exploring new delivery systems.

•	Ability to analyze work systems.

3.	Orient Initiative Teamleaders.  Conduct a meeting with all Initiative Teamleaders to review Low Cost Strategy objectives, Tasks, timeframes, etc.  Giving this important group a sense of the Low Cost scope, and an idea of what each Initiative involves will create better understanding and greater cohesiveness among Initiative Teamleaders.  Provide a copy of these directions and the entire Low Cost Strategy to each Initiative Teamleader.

4.	Prioritize all Tasks in the Low Cost Strategy.   All “A” priority tasks must be completed within the prescribed timeframes.  “B” priorities are ideally completed within the prescribed timeframes in order for the most effective change effort to be achieved.  However, if circumstances prohibit this, the timing of “B” tasks can be extended up to 30 days from the prescribed starting time.  A longer delay would be unacceptable as it would jeopardize the momentum of the change effort.  “C” priority tasks are optional, but recommended.

5.	The Tasks described in the Low Cost Strategy are the core elements to be implemented within the prescribed timeframes.  In addition to completing these Tasks, each Initiative Team is asked to identify additional projects (ideas, suggestions, problems) that fall within their area.  These projects are ones that will become the elements of the Low Cost Tactical Plan.  It is the responsibility of the Low Cost Strategy Initiative Teamleader  to develop the Low Cost Tactical Plan.  This plan will include, at a minimum, the Tasks of this Guide as well as numerous additional Tasks that the MAC, Executive Team, Initiative Leaders, and Associates will identify as they work through the Tasks of this Guide.

6.	In conjunction with each Initiative Teamleader, the Module Leader is to help recruit membership for the high priority DIGs.  The Initiative Teamleader is expected to Chair each of the DIGs within their Initiative unless otherwise indicated, and to be responsible for the oversight of each Just Do It (JDI) assignment.  This assures continuity of efforts within the Initiative and the entire Low Cost Strategy.  Tasks are frequently complex and require coaching, leadership, and problem-solving skills which the Initiative Teamleader will have.

7.	Develop and maintain a Gantt Chart for managing this project.

8.	Replace Initiative Teamleaders, or DIG members, who demonstrate a lack of performance.  The performance of each DIG under the Initiative Teamleader is of such importance that poor performance cannot be tolerated.

Role Of Initiative Teamleader

Each Initiative Teamleader serves as chairperson for a series of Tasks with a common theme.  The Initiative is carried out via a number of DIGs or Just Do It (JDI) assignments.  If a DIG is required, the Initiative Teamleader serves as the chairperson, unless otherwise indicated.  It is the Initiative Teamleader’s responsibility to organize and lead all DIGs and JDIs in their area, and to represent, coordinate, and assure proper implementation of DIG recommendations.

Barriers to implementation are to be removed, or worked around, through the leadership of the Initiative Teamleader, with the assistance of the Module Leader and/or the MAC as needed.  Final accountability and responsibility for the success of the Initiative lies with the Initiative Teamleader.

Timeframe For Work

Each Initiative Teamleader is to begin work immediately by:

1.	Scheduling Tasks into the next 12 months based on the required timeframes in the attached Strategy.  A more aggressive time schedule may be adopted, thus moving up the performance of tasks to an earlier time, if desired by the organization.  There are no classroom elements presented in TUL Session IV which would prohibit Initiative Leaders from doing their work on an earlier time schedule.

2.	Identify DIG members or JDI assignees for each Initiative.

3.	Orient DIG members and JDI assignees to the work.  This includes providing each DIG member with a complete copy of the Tasks within their Initiative.  Even though a DIG member may be assigned to work on one particular Task, an understanding of all other work that is being done within the Initiative provides them with a better perspective within which to work.

4.	Break down Task assignments into smaller Tasks assigned to

individuals with specific due dates.

5.	Routinely report the status of the Initiative to the Low Cost Module Leader.  The Council will synchronize the work of all Initiatives in order to avoid conflict and rework.

6.	Begin the work.

Nearly all Tasks can be accomplished within the prescribed timeframes.  Exceptions are noted in the “Timing” element of the Task description.  In no case should a Task require more than 90 days from the prescribed timeframe to complete.  Most will take 30 - 60 days.  Note:  You can accelerate the timing of these Tasks to be as early as is desirable by the organization.

Key To Task Codes

Each Task is coded to prioritize the work.  The following key defines the codes.

A	A “must do.”  It is essential to a successful change effort; to be accomplished within a prescribed timeframe in order to gain maximum impact in the change process.

B	A “must do.”  The start time could be delayed up to 30 days from the prescribed timeframe in order to accommodate other priorities.  In any case, these tasks must be accomplished.

C	Optional but recommended.

Approaches To Work

Task assignments can be undertaken in one of two ways:

1.	Do It Group (DIG).  This is recommended for complex assignments.  It involves multiple people working together to achieve end results.  Some Initiatives contain several ideas, and implementation will require multiple DIGs.

2.	Just Do It (JDI).  This is an assignment completed by one person who “just does it,” whatever “it” is.

Low Cost Strategy Note

This strategy will have a substantial impact on the cost of administration and service delivery, thus profitability of your organization.  This impact varies for each organization depending on the current state of operations and the extent to which Initiatives are implemented.  In no case are Initiatives to be dismissed.  Delays on “B” priorities are acceptable if approved by the Module Leader.  Delays should not exceed 30 days; additional tasks may be added to the list.

Initiative Structure

Each Initiative is organized similarly with the following information provided:

•	Description and objective of Initiative.

•	Explanation of why the assignment is made (this is included in description for some Initiatives.

•	Listing of Tasks to be done.

• 	Title for each Task.

• 	Priority listing.

•	Recommended timing.

•	Initiative Teamleader.

•	Recommended approach.

•	Listing of other assignees to be represented.

•	Listing of work to do.

•	Interactions with other people; a listing of people or projects where coordination, input, or information, would facilitate the process and avoid conflict or problems.

INITIATIVE TEAM INSTRUCTIONS

Each Initiative Team’s assignment is to review their Initiative in detail.  The entire booklet has been distributed to Initiative Teamleaders and is available for their reference if needed.  Read the section describing your Initiative and be prepared to discuss the merits of these ideas with the other members of your Initiative Team.  Your Initiative Team is being asked to implement ideas included in the Initiative, and make additional recommendations and suggestions for ideas related to this Initiative that could be implemented in the next twelve months as part of a comprehensive Low Cost Strategy Tactical Plan.  It is crucial that you read and understand the packet before any meeting, so that you will not be behind the group in terms of understanding the scope and intentions of the module, and so you will be able to make informed decisions and recommendations.  Prereading your Initiative Team’s information packet allows you to identify and obtain any needed information you might find helpful about existing systems and programs in advance of the meeting.

Action steps:

1.	Read your Initiative Team’s packet (your Initiative Team’s portion of the Low Cost Strategy).  Think about the suitability or applicability of each Task of the Strategy for your organization.

2.	Do additional fact-finding as necessary pertaining to your Initiative.

3.	Evaluate and implement each Task included in this packet.

4.	Discuss and generate ideas:  What additional suggestions related to this Initiative might be helpful to your organization on this topic?  Which of these ideas are high, medium, and low priority items?  In what quarter of the coming year should these ideas be pursued by a DIG or a Just-Do-It?

Each Initiative Team is chaired by an Initiative Teamleader who will be working with other Initiative Teamleaders to develop a Low Cost Tactical Plan  based on suggestions generated by all Initiative Teams.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 			ADDRESSED AT THE UNCOMMON LEADER

Description And Objective Of Assignment:  This Initiative is designed to prepare and support the participant group as they work through and adopt new group management practices and organization change elements.  In some cases executive level work is required before presentation of information is presented to the management team at the TUL session.  There are specific assignments made for the CEO to prepare prior to TUL Session IV, and following TUL IV.

Why Is This Assignment Made?  The Initiative Leader for LC.1 is responsible for assuring that all prepatory, supporting, and follow-up materials and information needs for this session are provided.  There are assignments and work that must be done in preparation for TUL Session IV.  They are identified.  You may call Management House if you wish to confirm that you have prepared all the assignments needed in advance of TUL IV.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 			ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.2   CHANGE ELEMENTS INTRODUCED BY MHI AT TUL 			SESSION

Priority: 	A

Timing: 	Session IV

Teamleader: 	 Management House Inc.

Recommended Approach: 	JDI

Other Assignees:	CEO

Interactions With Others: 	CEO and Executive Group

Work To Do:  Management House will present the materials for TUL Session IV including the introduction for the CEO’s presentation of “What I Want To See In A Proposal”, and the CEO’s presentation of the organization’s strategic plan to the group.  The CEO will make the actual presentation to the class.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 			ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.3		PROCESS INCOMING MANAGER 								SUGGESTIONS FROM TUL SESSION

Priority: 	A

Timing: 	Session IV

Teamleader: 	 MAC Chair

Recommended Approach: 	JDI

Other Assignees:	None

Interactions With Others: 	The MAC

Work To Do:  Capture all of the problems identified, and suggestions for improvement which are made at TUL Session IV.  Most of these ideas and suggestions will be shared during the feedback session of the breakout sessions which will occur in the afternoon of each TUL presentation date.  The MAC is to take notes during the feedback sessions and collect the acetate sheets following the conclusion of the TUL session in order to capture the problems and/or suggestions generated.  The content of the acetate sheets represents many ideas and problems yet to be addressed.  Translate the suggestions and problems into DIGs and JDIs to be addressed by the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 			ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.4		WHAT I WANT TO SEE IN A PROPOSAL, BY 						THE CEO

Priority: 	A

Timing: 	Session IV

Teamleader: 	 CEO

Recommended Approach: 	JDI

Other Assignees:	None

Interactions With Others: 	Support staff as needed.

Work To Do:  Managers often feel “at sea” in terms of knowing how to communicate with executives.  As a result they are often too wordy, don’t know what topic categories should be discussed, whether the executive wants a lot of data, and the like.

The President or chief sponsoring executive should present a short outline of “What I Like to See in a Proposal” to the management team.  The purpose is to instruct managers directly on what it takes to sell top management on their ideas.  Our experience is that this information and format is much appreciated by the management team, and makes proposal reviews more efficient and effective for the executive.

It is suggested that the President read the MANSYS chapters on Proposal Selling and Change Managing.  Appropriate sections of the Change Management Action Plan have been requested by some Presidents to be part of their managers’ proposals.  Please endorse any of the MANSYS guidelines that you particularly agree with.

The presenter should think through what values might accrue if s/he got everybody in the organization on a similar wave length as to proposal presentation—would that favor the selling of good ideas?

Also, talk to managers about some of the political realities, such as timing, what a turn down means, and the like.  Some managers take a “no” as a personal failure rather than seeing it in its’ proper light.  What is the context within which proposals can have life and impact?

Keep your presentation to 10 or 15 minutes.  A sample handout of a good proposal or a suggested outline will be helpful to managers.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 			ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.5	DEVELOP LOW COST TACTICAL PLAN

Priority: 	A

Timing: 	Session IV

Teamleader: 	Los Cost  Module Leader with assistance, if needed.

Recommended Approach: 	JDI

Other Assignees:	None

Interactions With Others: 	Assistance from the RAC and TAC as needed.

Work To Do:  Review all Tasks in the Low Cost Strategy Guide.  Become familiar with Tasks that have already been done in cost management in the past.  Learn about the processes used and the results achieved in the previous efforts.  We do not want to redo work that has previously been done.  Yet, we are not entirely confident that the maximum results have been achieved on past initiatives.  Thus, where past initiatives are related to new low cost Tasks, assess how long of a time period has elapsed since the previous Initiative was undertaken, how significant the previous results were, and if there is further potential for improvement.  Initiatives that were undertaken more than 18 months ago are fair game for a revisit at this time.  It is likely that there are once again opportunities for improvement in these areas of operations.

Following the format of a typical MBO tool or detailed Tactical Plan, outline each objective or goal to be accomplished, the departments to be affected, tools to be used, timeframes (use quarterly basis) in which results are to be achieved, accountable parties, and the measurable outcomes expected.  Tasks of the Low Cost Strategy Guide are a basis for the Tactical plan.  However, many additional Tasks, specific to your organizational needs must be added.  There are hundreds of cost management and resource utilization areas that are yet to be identified.  Using the power of focus groups comprised of Associates, patients, physicians and vendors to assist in identifying the list of cost management objectives.

Use the following questions to prompt discussions among focus groups of Associates and Customers.

•	Looking at your specific job, where is there unnecessary waste of time?  Unnecessary waste of resources?

•	What resources can be recycled or have their utilization extended?

•	What clinical procedures are we doing more frequently than we  need to?  i.e. are there work redos that should not be occuring?  Can we “stretch” the timing or frequency with which certain protocols are carried out without adversely impacting the quality of the service?

•	Where is there “waiting” time in any work related process?  How can that “wait time” be made more productive?

•	Where is there ”wait” time in the Customers’ experience?  How can that wait time be made more productive in order to complete the clinical protocol more quickly and thus be able to discharge the Customer/Patient earlier?

•	What barriers stand in the way of earlier patient discharge?

•	What generic substitutes can be used in place of high-priced brand name items?

•	Where can the consolidation of equipment/supplies occur in terms of the number and type used as well as the inventory location of splintered small quantities stored here and there?

•	How can we achieve better pricing on the products/supplies we must purchase?  (Don’t give in to the supplier’s defense of “you are already getting the best discount we can offer.)

At any time during the discussion, ask people to expound on a particular new comment or thought and explain it further.  Tangential comments and ideas often lead into otherwise unexplored areas.

The key to creating a successful Low Cost Tactical Plan is to listen effectively to everything that is said in the focus groups and departmental meetings as well as “off the cuff” comments made by Associates in their daily work routines.  Explore how each idea can be implemented in some fashion or form and include each idea in the Low Cost Tactical Plan.

Your Low Cost Tactical Plan should include a minimum of 150 to 200 specific Tasks.  More Tasks represent more improvements to be made.  If you have less than 150 Tasks in your Tactical plan, start over because you have missed something in the instructions or execution of this Task.

Publish the Low Cost Tactical Plan to all managers.  Establish recognition, reward and reinforcement items for various levels of achievement of these goals.  Consider multiple levels of rewards:  individual, department, team, and organization.  Be sure to communicate with energy and enthusiasm when achievements are made.  Communication and celebration create energy for further achievements.  It becomes self-perpetuating.

This is one of the most crucial Tasks in this Module.  The success of the module depends largely on the ability to create and fulfill a comprehensive Low Cost Tactical Plan.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR SESSION IV & CHANGES 				ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.6	CONDUCT PEOPLE CLIMATE AUDIT IN 				PREPARATION FOR CI PROCESSES

Priority: 	A

Timing: 	Following Session III.

Teamleader: 	MAC

Recommended Approach: 	DIG/JDI

Other Assignees: 	To be determined

Interactions With Others: 	None

Work To Be Done: 	An audit of the organization climate is needed at this point.  Consider the following items.  If you answer unfavorably to one or more of the questions, there is work to be done before proceeding with the Low Cost Strategy Guide portion of the TUL program.

Audit Questions:

•	What problems exist that make it hard to get Associates involved with Low Cost Initiatives or DIGs?  These barriers need to be broken down before proceeding with low cost projects.

•	Have DIG and Values training sessions been conducted as a precursor to Low Cost work?  If not, what is the problem, or where are the problem areas?

•	Do work standards or quotas exist that need to be eliminated?  If so, take them up as discussion/decision topics at the next Executive Team meeting.

•	Are there substantial HR problems that still need to be removed?  What can be done to expedite this?

•	Do any problem supervisors or intimidators stand in the way?

When/ how will they be removed?  Is executive assistance needed?

•	Is there any reason why Associates should not be allowed to redesign work systems?

•	Is the organization willing to regroup Tasks, change job content, cross train as appropriate?

•	Are there barriers that rob people’s pride in their work?  Why can’t the barriers be removed?  (It was part of an earlier Grow The Best People Strategy Task)

Upon completion of the audit questions, make the necessary corrections to operations in order to answer each audit question in the affirmative.  The objective is to expand the flexibility and responsiveness of the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.1:	PREPARATION FOR TUL & CHANGES 				ADDRESSED AT THE UNCOMMON LEADER

TASK LC.1.7	STAFF SWAPPING

Priority: 	A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG/JDI

Other Assignees: 	To be determined

Interactions With Others: 	Executive Group

Work To Be Done:  The benefits of staff swapping fall into two primary areas in terms of this assignment.  First, staff swapping results in a better understanding of how another department operates, and thus how your job interacts with other jobs and the results thereof.  Secondly, staff swapping results in improved relationships between and among people and departments.

There are two tiers of decision-making to this assignment.  First, executives are to identify departments who have routine conflicts with one or more departments.  Departments in a less than cooperative state with other departments are primary candidates for job swapping.  Conflict is often overcome when a greater understanding of the other’s situation occurs, and this is often the result of job swapping.  Executives are to pair up departments with any degree of conflict between or among them and arrange for job swapping situations to occur.  (The conflict need not be major in order to qualify for job swapping.)

Once departments are paired up for swapping, the question is,”which jobs should be swapped?”  In order to get the greatest impact for your effort, answer the following questions in order to determine which types of jobs should be swapped.

1.	What aspect of the other department seems to be irritating

to your department?  This is a clue as to the type of job that should be swapped.  The job positions that are becoming irritated should be swapped with those that appear to be causing the irritation in order to gain a better understanding of one another’s situation when it gets to the problem-solving stage.

2.	Is it a person, policy, procedure, or situation that contributes to

the irritation?

The job swap does not have to be a swap of jobs that are on an equal pay basis, or on an equal professional basis.  Because the job swap is for a relatively short period of time, and because there are no powers of decision-making that transfer with the job swap, there is no danger of wrong decision-making.  Therefore, any level of employment can be swapped with any other level of employment in an effort to gain a better, more in depth perspective of what others experience in their job.  This is the preface for substantial problem-solving among and between departments, and for the beginning of smoother, more team-like performances.

Once job swapping has occurred between and among departments with relationship development needs, then job swapping should begin to occur between and among all departments who interact with one another in terms of patient care.

Job swapping should occur for a period of two - five days depending on the need for a better understanding between the departments.  One job swapping event should be planned for each department for each month of the year.  This is an assignment that is on-going until all members of a department have had an opportunity to experience at least one job swap.

Job swapping adds understanding and smoothness to the integration of departments working together and problem-solving together.  It further adds to the personal and professional development and understanding of staff members in both departments.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

Description And Objective Of Assignment:  The objective of this Initiative

is to review and revise policies and practices that inhibit people productivity, and to support new thinking in terms of new ways of using people and tools to improve people productivity.

Why Is This Assignment Made?  This Initiative was created in order to identify and acquire tools that are needed to improve people productivity;  remove old work methods that inhibit productivity; revise policies that delay people performance in order to improve the overall productivity of all people in the organization, and thus the overall productivity of the organization as a whole.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.1	DEVELOP PEOPLE PRODUCTIVITY

Priority: 	A

Timing: 	Following Session VI

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	To be determined

Interactions With Others: 	Coordinate with the Director of Training and TAC as needed.  You may want to include universal Associate work assignments in the productivity educational packet/video.

Work To Do:	The purpose of productivity training is to educate and apply the new knowledge of productivity techniques to your work environment in order to make changes and improvements.

Put the productivity power of Associates into action.  Establish standards and assignments to be given to each Associate attending the Productivity Training session(s).  For example, Associates may be required to return to their work site after the productivity training and make at least one improvement in the way they do their work.  Each improvement is to be reported to the department manager, who in turn, reports the financial significance of the improvement to the MAC, or designee, for inclusion in the ROI calculation.  (Note:  Not all improvements in work will have an easily identifiable financial impact.)

Begin by orchestrating intradepartmental Associate work groups in order to think of new ways to improve team productivity.  Group Associates with related work together.  Give them the assignment of finding at least one way to improve their overall productivity.  Let them rearrange their work as needed to increase productivity.  The groups will report their productivity improvement ideas to their Department Head, who assigns or approves the estimated financial impact of the improvement, and forwards the ROI information to the MAC for ROI record keeping.  When this stage of productivity improvement is complete, move to interdepartmental groups.  Departments that routinely work together, or that impact upon one another, should be grouped together.  Because of the large matrix of combinations that interdepartmental groups could create, allow each department manager to choose one other department manager to begin working with.  This will control the number of requests that any department head will receive.  After a specified period of time, start a second round of interdepartmental groups.  Keep the effort continuing.

Consider incorporating productivity standards into Associate and managerial performance evaluation forms, and tie compensation to it.  Work with the current educational tracking system to assure that Associates are trained in productivity concepts and tools.  Departments lagging in training in this area are to be reported to the MAC who will take the necessary steps to assure that training is provided to all Associates.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.2	ADD TOOLS AS PRIMARY STRATEGY TO 			MAKE PEOPLE PRODUCTIVE

Priority: 	A

Timing: 	To be conducted following Session V

Teamleader:	Module Leader

Recommended Approach: 	DIG

Other Assignees: 	Representative from Finance/Budgeting Department

Interactions With Others:	Finance Department

Work To Do:  Investment in tools is an aggressive strategy that pays off 90% of the time.  Your Task is to lead an aggressive campaign to gain executive approval for increased funds for purchasing needed tools.

Start with the Vision Council.  Get their input and philosophy on what the current budget calls for and if/how it can be enlarged or shifted to include the required amount of funds for the desired amount of tools.  What justifications will they need?

Work with the Department Heads to develop a list of tools needed to improve productivity in each department.  Include the estimated cost for each tool, and the estimated increase in productivity.  (This would be the cost of tools vs. the cost of time without the tool).

A set of instructions and standards should be developed for managers to refer to when developing their “wish” list.  This will maintain a sense of consistency in responses.

Develop a process for prioritizing requests for tools.  Undoubtably, the financial requirements for providing all tools on the “wish” list will be greater than any organization could reasonably afford in the short term.  A process for prioritizing purchases organizes the funding process, and provides standards of operation that are clearly understood by managers, thus avoiding unjust critics.  Generally, low cost items that impact many people are best bets.  Buy the best tools available.  Quality over cost is a better tactic.  Look for tools that reduce the amount of human time needed.  Consider more exotic, costly tools on a trial basis.  Invest in transport robotics and new biotechnology.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 			PRODUCTIVITY

TASK LC.2.3	REVIEW OF DECISION TIMES

Priority: 	A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	None

Interactions With Others: 	None

Work To Do:  Identify where there are unacceptable delays in decision-making and approvals both within each manager’s individual departmental operations, and within chains of authority, communication, approval processes, and within councils and committee structures.  There are no “sacred cows” in this Task.  Look at committees and task forces, board meetings, normal line approvals for all functions including financial, clerical, and general operational and administrative functions.

Chart out the time frames for approvals of all decision-making types within each department, from department to department, and from department to executives, and from executives to administration.  The goal is to reduce decision-making times by 50% at a minimum.  Analyze why decision making takes so much time, and create ways to bust time barriers.  Common reasons for lengthy decision-making include:

•	The decision-maker is not available for some period of time

and thus cannot address the question/decision.

•	The decision requires the input of many people and it takes a goodly length of time before all parties have a common time available to address the question.

The speed with which decisions are processed directly affects the speed with which the organization can operate.  Cut out “waiting times,” reduce the number of people that must be involved in the decision-making.  Utilize a more rapid communication process, i.e. e-mail, v-mail, etc. and establish standard operating timeframes for decision-making.  The goal should be to address any and all decisions within three to five business days with the majority of decisions being handled within a standard of 36 hours.  The collective time involved within a slow decision-making process does not insure a better decision, it only assures a slower organizational performance.

Revamp each system and/or process where time delays are occurring, aim for a minimum 50% reduction in time or more.  Think in creative New American Hospital terms.  When experiencing barriers to change and improvement, take the issue to the operating Vice President for resolution and support.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.4	POWER-UP DOWN TIMES

Priority: 	 A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	None

Interactions With Others: 	None

Work To Do:	Identify “down times” or periods of time when low productivity levels are consistently found within the department.  These are opportunities for improved productivity and efficiency.  To better utilize these light productivity times, consolidate the work that occurs in light productivity periods into a condensed time period of higher productivity, thus creating a segment of high productivity and a vacant segment of low or no productivity into which other work can be channeled or FTEs can be redistributed.

If consolidation of light productivity and time cannot be accomplished, then additional work is to be assigned to the light productivity time periods in order to make them more productive periods of time.  For example, the night shift is often a time when work loads fluctuate dramatically, yet staff coverage must exist.  Therefore, numerous positions on the night shift avail you of work capacity to be filled.

The goal is 100% work productivity at objective levels for all positions at all times.  Sometimes the type of tasks used to balance out the workload for a position is of the clerical or less skilled basis that can easily start and stop with numerous disruptions, and yet not impact on the quality of the results.  Weekend shifts also offer potential to carry greater productivity work levels.  Telephone operators working night and evening shifts, are typical positions where on-the-job “knitting” occurs and greater productivity could be reaped.

Survey work productivity levels to identify “weak” productivity times and positions and then reconfigure the work processes.  Aim for at least 2.5 FTE to be freed up in the organization by shifting work to down time locations and situations.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.5	DEVELOP LITE DUTY RETURN-TO-WORK 				PROGRAM

Priority: 	 A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Employee Health Nurse

Interactions With Others: 	Include representatives from Nutrition Services,

Housekeeping, Nursing and Human Resources

Work To Do:	Employees with on-the-job injuries often cannot immediately return to their full, normal, job functions.  However, they are capable of doing some levels of work, either as a part of their regular job or some other job in the organization.  Yet without a Light Duty Return To Work Program, the organization pays out workers compensation dollars and receives no productivity results in return.

The objective of this Task is to develop a Light Duty Return To Work Program to maximize productivity per payroll dollar.  To develop this program, identify the job tasks that may qualify for Light Duty assignment for nearly any type of injury.  There should be numerous jobs of various skill levels that qualify for the Light Duty program.  The return to work assignment for each individual will be specific to the type of injury, personal limitations of the individual, and the needs of the organization.

Additionally, policy statements as to the requirements for participation in the Light Duty Program, explanation of the role of the Employee Health Nurse and medical review process in this new program, and determination of the compensation level and accounting details needed to coordinate payment from this program with workers compensation payments and other insurance programs, are also to be designed for your organization.

The end result should be an earlier employment of people with on-the-job lost time injuries, even if the early assignments of work are not necessarily as skillful as those they held before their injury.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.6	OUT-SOURCE SIDELINE OPERATIONS

Priority: 	 A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	None

Interactions With Others: 	COO, Director of Finance, specific Directors

of Operations

Work To Do:	This is a Task that will come under heavy scrutiny as implementation of the objectives is likely to mean a loss of present jobs in many cases.  Thus, enter this Task with a fresh, unbiased thinking and evaluate the possibility of out-sourcing tasks and functions that are not directly a part of your mission and primary service.  Out-sourcing has been proven to be economically effective while at the same time boosting the quality of function performed, and allowing the organization to focus on developing and delivering its primary mission–healthcare.

Areas for immediate out-sourcing consideration include:

•	Housekeeping

•	Food Services

•	Natural Resources

•	Utility Management

•	Human Resource Management, or portions thereof.  i.e. benefit mgt.

references, employee health, training

•	Accounts Receivable Management

•	Medical Records Transcription

•	Special lab services

•	Special rehab services

•	Other services where high quality and time lines of service can be provided at lesser cost by out-sourcing to an organization that focuses on performing these functions as their core business.

•	Business office functions, or portions thereof.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.7	EDUCATION/CONFERENCE AUDIT

Priority: 	 A

Timing: 	Session I

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Education

Interactions With Others: 	None

Work To Do:	Evaluate planned expenses for outside education and conferences for the next 12 months.  Put the brakes on any management development expenses outside the TUL program for this time period.  Toughly evaluate the need to attend conferences, seminars, and outside training.  Refocus education, skill-building, and training to internal programs sponsored by the organization.  The cost per participant is far better.  Further, conduct a Training Needs Assessment for this 12 month period.  Expand internal training from the narrowly focused clinical services to a broader scope of clinical services, supervisory skills training, managerial skills building (following TUL), etc.

Advance your thinking.  Envision a revenue producing education and training department advanced enough to sponsor specialty training, for a fee, to other regional healthcare institutions, as well as community education conferences.  Affiliate with a local university to obtain college credit where possible for the supervisory or management development sessions that you will be providing.  Affiliate with vocational training schools to better manage the quality and quantity of hard-to-fill vocations/technical positions.

Work with Human Resources, career planning, and staff planning to identify cross training needs and specific identification of positions within your organization where job obsolesce is likely to occur.  Work to move these people into other skilled areas where you will have a greater demand by providing appropriate training in advance.

Not only does this Task create a revenue center from a support center, but it contributes to the economics of the organization by assisting in the avoidance of downsizing, and the costs and morale problems associated with it.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.8	EVALUATE INFORMATION SERVICES

Priority: 	 A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Information technology staff as assigned.

Interactions With Others: 	Physicians. nurse managers, other department leaders as needed.

Work To Do:  Review the current state of information affairs.  Is appropriate real time patient information available to physicians, nurse managers, discharge planners, medical records and billing offices?  Real time patient information allows physicians to quickly and easily monitor patient progress and clinical path progression, thus assuring a high quality of patient care and more expedient discharge.

Audit each patient service delivery area and primary physicians to determine what is currently available and how to augment the amount of relevant information and the timeliness of such information.  Then, prioritize the information needs in line with strategic objectives and take action for improvements.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.9	REVIEW ON-THE-JOB TRAINING PROCESSES

Priority: 	 A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Department Managers

Interactions With Others:

Work To Do:  Each department already has on-the-job training in place for the majority of the positions.  The question is:  Is the on-the-job training process complete and adequate, or is it inadequate?  Are elements of training “not to do’s” that may seem obvious to a trained or experienced person, included in the on-the-job training?

Many accidents, complications, errors and problems within the organization are created accidentally by well-meaning, unthinking, or untrained Associates.  Have you thought of everything to be included in your on-the-job training?  Are you using a buddy system for new Associates?  Are you buddying up new Associates with your best Associates, or just any Associate?  Check the completeness of the on-the-job training for each job by testing it out on a new Associate.  Write down the questions that they ask and include answers to their questions as a part of your usual on-the-job training.  Look for the obvious defensive information pieces that people should know about as well as the obvious how-to’s of the job.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 			PRODUCTIVITY

TASK LC.2.10	REVIEW REASONS FOR ASSOCIATE OVERTIME

Priority: 	 A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Department Managers

Interactions With Others: 	Payroll Department

Work To Do:  Payroll overtime is an unnecessary expense that is typically driven by other events such as physician tardiness to a case thus requiring staff to wait for the physician, or late orders for service that must be done that same day, or poor productivity planning on the part of the department supervisor or manager.  Look at the departments who have experienced payroll overtime in the past six months.  Investigate why the overtime is occurring and make the necessary adjustments to assure that overtime no longer occurs at is at least substantially reduced.  Within each reason for overtime there is a problem to be solved and a cost to be cut.

When the reasons for overtime have been identified and the changes in behaviors corrected, report the previous overtime expenses on an annualized basis to the MAC as a cost savings to be logged on their ROI records.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.11	EVALUATE PATIENT PREPARATION PROTOCOLS

Priority: 	 A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 None

Interactions With Others: 	Department Managers as needed.

Work To Do:  Patients should arrive for admissions, testing, procedures, etc. fully prepared with completed information forms, physical tests in order, completed charts, etc. in order to avoid further delays in backtracking and duplicated efforts.  All departments are to review their protocols for preparing patients with all Associates.  Do not assume that any Associate is fully knowledgeable about all protocols.  Constant education is needed.  Reevaluate when, where, and how patient preparation should take place.  Meet with the Associates of the department(s) that service the patient just before you receive them in your department (looking upstream in the patient care process).

Then, meet with the department(s) that receive the patient immediately following your services (looking down stream in the patient care process) to see what additional patient preparation needs they may have fro you in order to keep the patient service flow going smoothly upon the patient’s arrival in their department.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.12	STANDARDIZE COMMON PATIENT CARE 			ADMINISTRATIVE PROCESSES

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 None

Interactions With Others: 	Include unit clerks/assistants, nurses and nurse

management representatives on the DIG

Interactions With Others: 	None

Work To Do:	The objective is to create a common, unified arrangement for unit supplies, support equipment, administrative forms, worker communication, etc. that is a mirror image on each nursing unit.  The end result will be a “cookie cutter” approach to the detailed layout of each patient/nursing unit in order that staff can quickly and easily locate commonly used forms, supplies, equipment, etc. reducing wasted time and worker frustration.  The reduction of wasted time and worker frustration translates into more productivity for the organization; an economic benefit.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.2:	LOW COST INITIATIVE FOR PEOPLE 				PRODUCTIVITY

TASK LC.2.13	STANDARDIZE COMMON ADMINISTRATIVE 			CLERICAL PROCESSES

Priority:  B

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 None

Interactions With Others: 	 Administrative Assistants, Executive Assistants, 							Departmental Secretaries

Work To Do:	In general, administrative assistants, executive assistants, and often departmental secretaries use many of the same tools, and have many of the same job Tasks.  Flexibility among these positions within the organization is important to creating a more efficient and effective operation.

Convene a DIG of Administrative Assistants, Executive Assistants, and Department Secretaries to do this work.  The objective is to standardize the work systems and tools that they use.  All work systems and tools are fair game.  Look to standardize word processing equipment, software, filing systems, calendaring of standard meetings, and the calendaring process, forms, etc.  The objective is to make movement from one administrative position to another (either on a temporary, emergency, or regular basis), fluid as we seek to employ the most effective and efficient processes to accomplish administrative tasks and enlarge and enrich the Administrative Assistant job function.

It is expected that a number of forms will be either consolidated into one new form that all Administrative, Executive and Departmental Secretaries will use, or that, by consensus, one form per function will surface as best for all to use and the others will be discarded.

Work toward an information system that will help manage the calendaring process;  one that will show the calendars of all those who commonly meet.  The objective is to reduce the time/effort needed to schedule a meeting.  By typing in each attendees name, the system will identify time periods when all participants have a common opening.  By using common computer software, Administrative Assistants and other can move from desk to desk easily, filling in for one another etc. and providing a seamless continuum of service.  This is just one idea of many where this staff of high level administrative support people can simply consolidate and standardize the way in which they perform their work.  Of course, there will always be a few idiosyncrasies required by the personalities of particular bosses, but the larger objective is standardization and flow between staff.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

Description And Objective Of Assignment:  The objective of this initiative

is to review and revise policies and practices that result in a less than optimal financial performance for the organization in order to boost financial performance for the same level of business performance.

Why Is This Assignment Made?  This initiative was created in order to identify and modify financially oriented policies and practices in order to improve financial performance based on the same level of business activity.  Aggressive financial policies and practices can represent a significant boost to cash flow for an organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.1	INSTALL NEW POLICY:  ALL SERVICE 				CONTRACTS REQUIRE A FULL REBIDDING 			PROCESS UPON RENEWAL

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 Director of Finance, Director of Purchasing

Interactions With Others: 	 Department heads as needed.

Work To Do:  All healthcare organizations are involved in a number of maintenance/service contracts of one nature or another.  For example, temporary help contracts, facility management contracts, large equipment maintenance contracts, purchasing contracts, etc.  These supportive service-like contracts often roll over naturally term after term, and the relationships between vendor and the hospital grow tighter and less questionable over time.

We must take a new approach to vendor and service management contracts.  Look at the relationship through literally new eyes.  Set the service and/or maintenance contract out for rebidding to other suppliers with each term of renewal.  Competition is rigorous and it is likely that you can acquire like or better service for a like or better pricing with a rebidding process.  Even if you are using the premier provider for a certain type of service, there are always new comers to the field who should be given some consideration.  You can also use the facts learned by investigating competitive providers of service as a negotiating tool when renegotiating your service/maintenance agreement.  Go for improved services, quality, quantity and reduced prices.  Your relationship with the vendor should be continuously changing and evolving around the idea of improved services and costs for your organization.

Those vendors who do not participate in an evolving and improving relationship with you are most likely losing their competitive advantage in the market regardless of their current size or position.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.2	MANAGE PRIVATE PAY CUSTOMERS

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 Director of Finance.

Interactions With Others: 	Director of Admissions, as needed.

Work To Do:  Private pay customers represent a much smaller proportion of the total customer base, and therefore often receive less than adequate attention when it comes to the management and collection of their accounts.  Some hospitals that I have visited have out of touch policies such as not accepting cash payments from self paying customers!  Others have nearly ignored the self pay or private pay customer base in terms of account collections.

Review and revise the current policies surrounding private pay customers.  Look to install practices that make it easy for private pay customers to pay their bills on the same aggressive schedule as would be expected from insured customers.  Research the protocols for effective collection of past due accounts and put them into place.  Self pay patients should be treated as insured patients would.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.3	MAXIMIZE CASH FLOW

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance

Interactions With Others: 	Director of Finance

Work To Do:  For purposes of this assignment, cash flow management refers to the time period beginning when the customer pays the bill via writing the check, to the time the payment received is optimally invested.

Flowchart, using cycle time analysis, the steps, and waiting times from the moment the customer or payer drops payment in the US Mail or electronic mail to when the organization has optimally invested the funds.  For example, given an insurance payer, (and this process must be done for each major insurer or payer), outline each step and each point of time passing, including how much time passes with each step, and between each step, until the money is optimally invested in your accounts.  Squeeze time out of each step, and from between steps, by improving or redesigning the aspects of the process you can control.  Then, meet with each insurer or payer and work with them to redesign and improve their portion of the process.  To start looking for improvements follow these steps:

•	Track the time period from the point of time of patient discharge to the point in time in which an invoice is created for the patient.  The goal is to get all patient charges into the system and processed the day of discharge.  No late or lost charges, and no delay in invoice processing.

•	Track the period of time it takes from the point of invoice creation to the point of patient and payer receipt of invoice.  The number of days that it takes to transport the invoice from the hospital to the payer(s) can be reduced by investment in electronic systems whereby charges can be electronically transferred to the insurance payer daily as the invoice is created.  By managing this piece of time in the cash flow system, the overall Accounts Receivable days can be reduced without changing any other aspect of the process.

A system of this nature allows insurers and other payers to direct deposit, via daily electronic deposits/transfers, the moneys due and payable to you each day.  This will eliminate the time period in which the check is traveling through the US Postal System, thus reducing your Accounts Receivable by days.  This is a relatively common practice and should not be difficult to establish if you don’t already have it in place.

•	Track the time lapse between when the customer writes the payment check and when it is received at your organization.  The U.S. Post Office may be costing you undue delays in accounts receivable days.  To remedy this, track the time period for receipts of payment through the postal system.  You may wish to establish an accounts receivable postage box specifically for payment receipts.  This allows you to collect monetary payments without waiting to process the incoming mail through the hospital mail system.  Collect the money payments and directly deposit each payment as the first step of your money management process.  Then match payments to the customer and to the invoice.  Get the cash in the bank early.

•	Negotiate a high paying money market rate with your bank for the account in which the majority of the cash flow of the organization will be passing through.  Do not accept the usual Jumbo CD rate.  They can and will do better for you considering the millions of dollars of cash that will flow through their organization.  Push for more than your banking representative tells you is possible.

•	Establish an automatic money sweeping process for your money market account at the bank.  The objective is to move the money that clears the system daily into a higher yielding investment vehicle the day that it is available.  This requires daily monitoring.  However, banking institutions can arrange to “sweep” your account daily for you and deposit the funds into a prearranged higher yielding investment vehicle.

•	Set a goal of at least 25% improvement (meaning a reduction) in time from point of customer/insurer payment to optimal investment of the funds.  Use cycle time analysis to determine the length of time from cash receipt to optimal investment.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.4	EVALUATE ACCOUNTS PAYABLE SCHEDULE

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance

Interactions With Others: 	Director of Finance

Work To Do:  Review your current Accounts Payable process.  Are discounts being taken?  Are payments processed on time?  To the extent that you are an honorable community service organization, the reputation of the organization is somewhat affected by numerous factors.  One small influencing factor is the timeliness by which your organization pays it bills.  Some payments must be made on time and not one day late.  For example, mortgage payments, investment banking schedules, etc. have no tolerance for delinquent payments.  Yet other payables do possess some tolerance for a “slower” payment—unspoken terms.  Review your financial/investment house responsibilities and assure continued timely payment.  Separate out other suppliers and vendors and work the cash flow timing element.  Schedule accounts payable payment at a 45 - 60 day schedule following the due date.  Take discounted terms even if it is after the fact, and eliminate any delinquent charges that are assessed.  This timing schedule is generally acceptable and will not raise concerns outside of investment banking relationships, although payment schedules beyond the 90 - 120 day delinquent cycle will be likely to draw criticism.

The increase in cash flow for the extended period of time results in an increase in investment income for this same period of extended time.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.5	MAXIMIZE SPEED OF SERVICE TO BILLING 			CYCLE

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance, Service Line Managers, as needed

Interactions With Others: 	Director of Finance, Service Line Managers, as needed

Work To Do:  Identify the main/primary service lines that provide the majority of cash flow to the organization.  These are usually high volume/high cost services.  A service line is a grouping of departments or processes commonly involved in the delivery of services to a particular type of patient.  Examples of commonly noted service lines include:

•	Emergency Services

•	Cardiac Services

•	Women’s Services

•	Oncology Services

•	Surgical Services, etc.

Separate each of the service lines.  Using cycle time analysis, chart the steps and timeframes from point of service delivery to prepared bill/invoice for each service line.  Reduce/eliminate all waiting times between when a service is delivered and when charges are processed to the customer’s account..  Move toward “consumption billing” or daily billing.  Time is money, and therefore for each day cash flow is maximized, income is also maximized.

There are typically great time delays found between when a service is delivered and when it is charged to the Customer’s accounts AND there is typically a great time delay between when the medical info/services charges are turned in and the time when the invoice is delivered to the Customer.  Find ways to speed the time from service delivery to invoice receipt.  The minimum goal is to reduce service to billing time by 33%.  Seek to move toward instantaneous billing.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.6	ELIMINATE LOST CHARGES

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	 Director of Finance, Service Line Managers, as needed.

Interactions With Others:

Work To Do:  Identify major service lines in the organization.  A service line is defined as a grouping of departments, services, or processes commonly involved in the delivery of services to a particular type of patient.  Examples of commonly noted service lines include:

•	Emergency Services

•	Cardiac Services

•	Women’s Services

•	Oncology Services

•	Surgical Services, etc.

Within each service line, flowchart and analyze the process of delivery of services through to the point of billing.  Look for areas where charges get lost, missed, miscoded.  Fix the system.  Make it “idiot-proof”.  No offense is intended by this label.  The intent is to make the system safe against losing charges.  Consider lump-sum, or “package pricing” for small services or products that are routinely forgotten, lost, or never captured.  This approach, or something similar, will

•	Reduce the`amount of time needed to process charges, thus leaving more time for other work.

•	Capture what might otherwise be lost charges/revenues.

•	Reduce unnecessarily lengthy Customer invoices that show “itemized aspirin.”

•	Camouflage the difficult-to-explain costs like a $2.00 charge for an aspirin or a $5/day charge for television.  This too will improve patient satisfaction as points of agitation are removed.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.7	REVIEW THE TIMING OF BUDGET REPORTS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance

Interactions With Others: 	Director of Finance

Work To Do:   Budget reports that reflect the current financial status of each department’s operations need to be available to department mangers immediately following the close of business for that month in order to make necessary and timely adjustments in departmental performances.  Reports that are available 3 + weeks following the close of business are of little or no use in correcting problems as they occur.  Managers need up to the minute, current information in order to make the necessary adjustments.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.8	EVALUATE FURNITURE/EQUIPMENT IN

Priority:  B

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Materials Management or party responsible for storage

of equipment/supplies

Interactions With Others: 	Materials Management or party responsible for storage

of equipment/supplies

Work To Do:  Often the furniture and equipment from past managers, projects, etc. are stored in a warehouse facility and not used.  Inventory the items in storage and redeploy those that can be used within the organization.  Sell off the balance that cannot be redeployed, and move them out of the organization.  Free up the space and redeploy the financial resources.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.9	EVALUATION OF PAID MEDICAL DIRECTORS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	CEO, Chief of Medical Staff

Interactions With Others: 	CEO, Chief of Medical Staff

Work To Do:  Some organizations have a number of paid medical directors on their payroll.  Generally speaking, paid medical directors are likely to be an unnecessary expense as there are a great many qualified physicians who are wiling to serve in the role of medical director for their speciality without compensation, or with a significantly reduced compensatory rate in exchange for the visibility and business benefits that come with such a position.  Think about this possibility.  If you cannot move dramatically toward this position in one swoop, then move toward it in a series of aggressive moves.  The organization’s position with respect to paid medical directors should evolve as the relationship between hospital and medical staff evolve.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.10	REVIEW THE COST MANAGEMENT OF 			MARKETING NEEDS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Marketing

Interactions With Others: 	Department managers, as needed.

Work To Do:  Typically there is a “dumping” of marketing costs onto the Marketing Department through which marketing tools and products such as brochures, signes, etc., are usually centralized.

Consider moving to a marketing line item for each department, and charging back the cost of marketing services to the department requesting them.  Publish a cost sheet of the charges associated in the most typical types of marketing requests, i.e. brochures, posters, etc.  A charge back process for marketing materials will dramatically help manage the marketing costs of the organization.  Create a list of questions for department managers to use to help assess if their request for marketing material is truly required, or just desired.  If the cost/benefit analysis of the request makes good business sense; if the investment in marketing materials is a priority, and fits within the BHAGs for the organization, then it should receive appropriate attention, and funding.  If not, then discard it.  Such a list will help managers sort out the realities of what otherwise might seem to be a general request.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.11	REVIEW ORGANIZATIONAL MARKETING 			COSTS

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Marketing

Interactions With Others: 	Executives, as needed.

Work To Do:  Marketing costs in healthcare organizations are a significant line item in the overall operating budget of the organization.  Yet, many organizations expend outrageous amounts of marketing dollars based on some philosophy that does not translate to new patients, or better business performance levels.  I often drive past billboards in the greater Chicago area, only to see advertisements for a healthcare system name.  The billboard does not tell me or any other passer by anything more than a name that is unrelated to anything else.  I often hear public notices on the radio sponsored by some healthcare group or another which does not translate into a greater number of patients for the organization.

A more business like, cost/benefit analysis needs to be performed on the advertising and marketing plans for each organization.  The basic business question of “will these advertising and marketing dollars spent translate into greater revenues and profits, or not?” needs to be asked.  And, “how directly are these expenses tied to the acquisition of better business performance?”

It is time that healthcare executives started to view their marketing and advertising campaigns as expenses in the way that the great consumer marketing giants of American business, such as Procter & Gamble, view their marketing decisions.  What will the pay off be?  How quickly will the pay off occur?  How direct is the pay off? etc., and let go of the non explicitly, ill-directed efforts that seem to override the majority of today’s healthcare organization’s marketing budgets.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.12	STANDARDIZE BUDGET VARIANCE 				REPORTING PRACTICES—STANDARDIZE

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance/budgets

Interactions With Others: 	Director of Finance/budgets

Work To Do:  Budget variance reporting practices are as different under each executive’s authority as the personality’s of each executive are.  Some are very tight and controlling.  Others, very loose and uninvolved.

Budget variance reporting needs to be standardized for all managers in the organization to comply with.  The time line for reporting should be tight—within five business days from the receipt of the budget report.  The variance reporting needs to include a statement as whether or not the variance will be corrected in the coming time periods, and how quickly.  And if it will not be corrected, then adjustments to the budget need to be requested to truly reflect the activity in the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.13	EVALUATE THE POLICY/PRACTICES OF 			PROVIDING ASSOCIATES WITH LAB COATS/ 			KLEENEX, COFFEE AND OTHER CREATURE 			COMFORTS

Priority:  B

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Select department managers where appropriate

Interactions With Others: 	Select department managers where appropriate

Work To Do:  Improving the organizational climate does not mean providing endless creature comforts to Associates.  There is a line between what is appropriate to provide in a friendly work environment, and going beyond business protocols to a level which later can turn a bit sour.  Determine what basic guidelines and creature comforts, if any, will be universally applied to all Associates in all departments.  Universal applications of creature comforts will break down barriers between various professions and departments.

P.S.  Creature comforts that are made available for patients or waiting visitors need not be extended to the work force.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.14	REVIEW PRECERTIFICATION PROCESS TO 			CAPTUR REVENUES

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:  Manager of Precertification and Director of Finance

Interactions With Others: 	Manager of Precertification and Director of Finance

Work To Do:  Provider contracts of all nature contain some degree of precertification which must be done appropriately and timely in order to assure that the organization will receive the maximum reimbursement due it.  However, the precertification process is often sloppily managed (not to say that is the definite case at your organization at this point in time), and great sums of reimbursement dollars are lost annually due to lack of precision and timing in the precertification process.

This Task is concerned with reviewing the precertification process and identifying the amount of money that is lost to the organization over the past 15 months due to missed details on the precertification process.  This number will be amazingly high.

Your responsibility is to review, revamp and readminister the precertification process in a manner that assures all precertification work is done completely and timely on all patients in order to assure that every dollar of reimbursement due the organization can be legitimately collected.  This will mean work process changes at a minimum; it will mean additional training of staff in these jobs; and it will require new standards of performance for all staff in these jobs.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.3:	LOW COST INITIATIVES FOR FINANCIAL 			PROCESSES

TASK LC.3.15	REVIEW MEDICAL DOCUMENT FOR 				REIMBURSEMENT

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:  Director of Medical Affairs

Interactions With Others: 	Director of Medical Affairs

Work To Do: Lack of medical documentation, or documentation provided in a timely manner is key to lost reimbursement revenues.  Appropriate medical documentation provided in a timely manner is essential to the collection of full reimbursement.

The objective of this Task is to quantify in general terms the amount of revenue lost for the past 15 months due to missing, late, incomplete medical documentation.

The next step in the Task is to review the work system for collection of medical documentation and identify where improvements need to be made in order to assure timely, correct and complete medical documentation for purposes of reimbursement, and to make changes in the system as needed to assure that such documentation is provided to the appropriate people, in the required format and in the required timeframe.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING 			PROCESSES

Description And Objective Of Assignment:  The objective of this initiative

is to review and revise policies and practices that result in less than optimal operations within the organization.  Improved operations lead to more satisfied customers, less frustrated Associates and physicians, better use of resources, and a higher quality of service and outcomes.

Why Is This Assignment Made?  Often organizations become so engulfed in their daily activities that they do not take the time to stand back and look at the bigger picture of activity within the organization.  The following low cost initiatives reflect specific tasks for the organization to undertake at the pace which is most comfortable for the organization.  Obviously, the faster and more complete  each task is undertaken, the more significant the impact will be on the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.1	IDENTIFY SERVICE LINES

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Chief Operating Office and Director of Planning

Interactions With Others: 	Coordinate with the Task addressing “Redesigning 						Executive Structure To Reflect Horizontally Flexible 						Organization.”

Work To Do:	Consider moving to a Service Line Management approach or a horizontally managed organization.  Envision one person managing all aspects of Patient Service from admission to discharge, including profit and loss, for each major service line.  This would be the desired end result.  Your Task is to identify and simplify various service lines currently within your organization.  A service line is defined as a grouping of products, services, or processes, commonly delivered to a particular type of patient.  For example, commonly found service lines include:

•	Cardiology

•	Oncology

•	Surgical services

•	Women’s services

•	Emergency services

•	Pediatric

The objective of service line management is to provide a seamless continuum of care for each patient, in the most efficient and effective manner.  This includes resource utilization management as well as clinical and administrative management.

When service lines are identified, the next step is to identify a service line project manager for each respective service line, or combination of service lines.  Service line managers are like CEO’s of their service or product line.  They have final accountability for all aspects of the entire service line delivery, from the moment the patient is admitted or referred to the collection of bills.  This is not a new or additional layer of management.  The service line manager is often the expansion of the job description of the top department leader within an identified service line.  This is a change in the organizational structure. Rather than a structure that has a Department Leader for every department and each department leader reports to a Vice President, the new service line organization creates one Service Line Leader for each service line.  Previous department leaders are renamed as supervisors and now report to the Service Line Leader/Manager who has full responsibility for the operations, profit and loss, etc. of the service line operation.  They are in essence a CEO of a service line.

The impact on the organization of a service line model will be seen in the centralization of problem-solving at the Service Line Leader level, thus identifying one central point where physicians, patients, Customers of any nature, and Associates can direct problems for resolution.  It is also a highly empowered position which allows the Service Line Leader to make the necessary decisions to manage the Service Line operation, make necessary corrections in procedures, policies, etc., without having to go through heavy bureaucratic approval processes.  In summary, this is a significant position and should be treated as such.

Service line management is a radically different approach to management–one that makes great sense, but has not been experienced by many of your managers.  As CEO/COO consider thinking and acting in service line terms.  Evaluate the positive-negative results of service line management.  Each project manager for a service line can conduct the research for you.  It may make sense to initially organize a number of the larger service lines.  i.e. Emergency Services, Surgical Services, etc., which are already, to some degree, operating under a service line management concept.  Expand the concept further within these arenas.  Keep in mind the need to consider the working relationships, scope of responsibility, and accountability that current department managers have.  A move toward a service line management structure and operations will impact many of their jobs.  Adequate training and information on their revised job responsibilities and relationships will need to occur in order to avoid unnecessary confusion.  Also, a reorientation to thinking in terms of product line management will be needed by all those affected by the change.

Expected results:  A correctly implemented product line management strategy should yield the following results:

•	Close management of each product line from start to finish.  Thus patients should have a more seamless, integrated, and efficient experience under this approach.

•	More rapid and effective responses to problem situations that arise in any portion of the product line operation as there is one centralized accountable party empowered, trained, and tooled to make decisions.  This person is motivated and directed by their personal responsibility to manage the entire product line.

•	Efficiencies in work systems and therefore reduced costs to operate the same system.

• 	Improved quality of services conducted.

•	Improved physician and patient satisfaction.

•	Improved Associate opinions of their work place and quality of care provided.

The problem with the traditional structure of departmentalized operations is that the central and accountable party for most problemed situations is not any one individual.  Rather, various department managers own bits and pieces of the problem because of the high degree of inter-relatedness between departments.  Thus, it is significantly more difficult to completely solve a problem, to completely correct a system operation, and to assure that the corrections are maintained in place.  The length of time it takes to convene multiple parties to meet, work through decisions, etc. is significantly longer than when one central and accountable party, the service line manager, is directing operations.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.2	REDESIGN EXECUTIVE STRUCTURE TO 				REFLECT HORIZONTALLY FLEXIBLE 				ORGANIZATION

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	JDI

Other Assignees:	CEO and COO

Interactions With Others: 	None

Work To Do:	Evaluate the current executive structure.  The optimal number of executive positions is the minimal number.  Old American Hospitals are typically executive top heavy which is a revenue buster and a time delayer.  Fewer positions, staffed with appropriately effective leaders, result in a more flexible and rapidly responding organization.  Broaden responsibility areas, by combining numerous jobs, and enrich and grow managerial functions by redeploying work assignment to managers.  The following responsibility areas are suggested as the maximum number of top executive positions.  Some New American Hospitals operate effectively with fewer positions.  We recommend:

1.	Vice President, Patient Care

2.	Vice President, Ancillary and Support Services

3.	Vice President, Finance

4.	Vice President, Managed Care and Physician Relations

The prescribed organizational structure may seem lean to most readers of this Guide.  However, with appropriate training and development as provided in the TUL program, many of the daily follow-up and monitoring functions that are presently done by vice presidents can be delegated to managers.  This will free up executives to build the business while daily operations are managed by managers.

Retaining a heavy executive level in the organization is leadership procrastination.  If not by choice, then by dictate, the numbers of executive positions will be reduced at the time of acquisition/affiliation or simply by market demand in terms of eliminating unnecessary costs.  A majority of “system” healthcare care facilities are operating with a shared CEO over numerous hospitals and related healthcare facilities, a COO, and a VP Finance position.  That’s all.  The balance of traditional vice president positions for such functions as patient care, human resources and operations, are being absorbed by the director level, and in many cases combined into even fewer positions, i.e. marketing, public relations and human resources are lumped together in one director position.

Organizations with eight or more executive positions are strong candidates for restructuring.  Use the talents of managers to perform the “task-type” functions and select “relationship-type” functions.  Build on their skills, hold them accountable for aspects of the service line operations and success, and reward them accordingly.  If further assistance with executive assessment or career development is needed contact Stephanie at Management House, Inc.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.3	STANDARDIZE SUPPLIES:  REDUCE NUMBER OF 	SUPPLIERS

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Purchasing

Interactions With Others: 	None

Work To Do:	Collect data identifying commonly purchased items of various types from various suppliers used within numerous departments.  For example, has your organization standardized the type and brand of latex gloves used, surgical supplies used, nursing unit supplies used, office/administrative supplies used?  There is no need to order and inventory five kinds of nursing supplies.  Standardize on a type of common supply used by numerous departments.  This Task will likely require input from all department managers and physicians affected.  Consensus may be an impossible goal, thus set your vision on the goal of satisfying as many people as possible, but realize that you will not be able to satisfy everyone.  Changes of this nature require cooperation from all parties in the organization.  Move the decision-making along as quickly as possible.  Avoid getting bogged down in endless discussions about why a particular additional product design element is needed in order to satisfy one or two people.  Remember, the goal is to simplify the number of products inventoried.  i.e. one type, model, and supplier of vinyl gloves for the entire organization; one supplier of hygienic goods, etc.

Break managers into groups with common supply needs and work with each group independently to achieve consolidation of supply types and vendors.  Break physicians into groups with common supply needs and work with them to reach common supply needs where possible.

If the number of items ordered is reduced via standardization, the amount of money required to inventory items will be significantly reduced, and the power of negotiation for larger quantities will benefit the organization with reduced costs per item.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.4	REDESIGN ORGANIZATION STRUCTURE TO 			STREAMLINE COMMUNICATIONS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	CEO

Interactions With Others:

Work To Do:  Redesign the organization structure to represent the horizontal functions and flow which your Customer experiences.  The number of bureaucratic levels should be minimized, and accountability and leadership assigned on a service line basis.  Service line or product line management was introduced in an earlier Task.  A service or product line is a combination of products, process and services usually conducted on patients with a common diagnostic qualities.  For example, commonly found service lines include:

•	Emergency Services

•	Women’s Services

•	Oncology Services

•	Cardiology Services

•	Orthopedic Services

•	Children’s Services

Now that a service line organization is in place, the roles of many executives must change.  They are no longer needed to monitor and manage the service line operation.  If the executive’s job can be refocused to build new —nonexisting business, then do so.  Otherwise, this executive position may no longer be needed.

Under the new service/product line organization structure, new channels and means of communication need to be identified and communicated.  Because the service line manager has full responsibility for the entire operation of the service line, including profit and loss responsibility, it is imperative that a smooth and rapid communication system be in place from all supporting aspects of the service line to the service line manager.  For example the flow of paperwork and verbal communication will need to be faster.

It is recommended that the entire communication process from Associates through coordinators and managers to the service line manager be critically evaluated.  Look to replace traditional paper forms and requests for information with electronic communication.  Reduce the number of people that must be involved in any decision to one or two at a maximum.  Consider a common communication board to communicate basic information to all involved in the service line operation.  Establish a standard turnaround time for decisions and communications.

The new seamless and rapidly flowing service line process requires a seamless and rapidly flowing communication system.  Involve your information systems people where needed.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.5	ELIMINATE NO/LOW VALUE-ADDED SERVICES

Priority: 	A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	None

Interactions With Others: 	None

Work To Do:	Looking at each segment of the organizations’ operations, including clinical support, administrative, etc., and call the question of what services or functions are we performing that do not add true value to the customer?  By this we mean what frills have been added to our services that are “nice to have”, but are not truly valued by the Customer?  Eliminate these functions or pieces and redeploy the human and financial resources to higher priority services as voiced by Customers.

Set a goal of at least three to five no/low appreciated value-added items per department that can be deleted.  Estimate the value of the time and/or resource savings with each Task deletion, and report this to the MAC for ROI tracking.  Talk with your Customers to determine more highly appreciated ways in which value can be added to your services.  Redeploy the savings from deleted tasks, or a portion of the savings, into new, customer-appreciated, value-added services.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.6	CONDENSING PAPER SYSTEMS

Priority: 	 A

Timing: 	Session V

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	None

Interactions With Others: 	None

Work To Do:	The cost of collection of duplicate information on different forms is more costly than it initially appears.  Costs include the cost of time to collect the information, the cost of frustration in providing duplicate information, the cost of printing duplicate forms, the cost of filing duplicative forms, the cost of space for duplicate forms—get the picture?

The objective of this task is to zap, delete, or get rid of at least 30% of the forms currently in place in the organization.  The reduction in the number of forms can take place via a combination of various forms, deletion of out-dated forms, redesign of forms for multiple uses within a service line, etc.

Look for major pockets of applications for forms to consolidate or delete.  For example, Human Resources is a department that uses many forms that can often, when challenged, be deleted or combined, or automated.  Other departments that utilize forms and are candidates for simplification include each of the major service lines in the organization.  Start with the first step upon entering the hospital, the admissions process, and follow the patient through the entire service line experience, including all of the possible ancillary services that may be called upon to assist with the patient care, and then look at all of the various forms presently required.  Work to consolidate and combine all of these forms to assure a more complete and expeditious processing of information.

Another way to go about this Task is in the following two phase process.

Phase I.	Identify unnecessary forms and delete them.  Some organizations actually have a “Forms Committee” to review and approve the design and use of forms in the organization.  If this is your situation, the objective of this “Forms Committee” is to delete unnecessary forms; those which are in print or in use but are “silly” in nature.  For example, any form that solicits the comment, “why do we have a form for this?” would qualify as a silly purposed form.  Or, “there’s a form for that . . .!?” would also identify a form that probably doesn’t make much sense.

In addition, your Task is to:

•	Simplify any form that is in existence, and reduce the overall number of people who must use it.

•	Simplify or reduce the number of signatures required on any one form.

•	Delete the form entirely and save the time to use it and the cost to print it.

Set a goal of at least 25 forms to zap or improve, resulting in time and cost savings.

Phase II.	Seek out unnecessary reports and delete them.  Conduct an audit of computer generated reports.  Include:

•	The title of the report

•	How frequently it is generated

•	To whom it is distributed

Ask each person on the distribution list if the report is still needed; if the frequency of the report is still appropriate or if a less frequent schedule would work.  It is possible to provide a centralized location where infrequent users could access reports if they needed and thus eliminate the need to distribute and process the infrequently used, but frequently generated reports.  The result is a savings in time to generate the report, distribute the report, and file or process the report.

We want to discontinue distribution and multiple storage of reports that are not used, or are not needed as frequently as they are presently being distributed.  Rethink the need for this information.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.7	REVISIT PAY EVALUATION PRACTICES

Priority:  B

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Human Resources

Interactions With Others: 	None

Work To Do:	Inconsistencies in performance evaluation processing can lead to legal liabilities as well as creating chaos within the organization.  There are cost savings to be had, and legal liabilities to be reduced, if consistency in pay practices is assured, and if proper performance evaluations are conducted.

This Task calls for an audit of actual pay practices across all jobs and departments in the organization.  Audit for consistency in overtime pay practices.  i.e. who gets overtime, how overtime is calculated, and based on what set of circumstances is overtime compensation paid.  Also audit for consistency in on-call time compensation practices, and holiday and vacation pay.  We generally find inconsistencies have evolved over time and should be corrected.  These inconsistencies in compensation practice application can be the basis for legal dispute, expense, and potential back pay orders.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.8	LOCATE & REDUCE AREAS OF WASTE—

CONDUCT COST CONTAINMENT AUDIT

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	A management engineer, if one is on staff.

Interactions With Others: 	Department managers.

Work To Do: The Cost Containment Audit is provided by Management House and should be distributed to each manager and supervisor to be completed and summarized for the MAC.  (The Audit is available from the DIG Coordinator at your organization.)  Each manager and supervisor is to answer each question on the Cost Containment audit.  There is no such thing as “N/A”.  Interpret each question in the most generous form or application.  If the question is not directly applicable to your department, it is likely that it is applicable, to some degree, to your operation in a tangential way.  Be sure to involve all of your Associates in the evaluation of the questions found in the Cost Containment Audit.  Associates provide a wealth of information and new ideas.

The results of the Cost Containment Audit can be summarized in the following bullets:

•  At least 12 -15 actionable items are to be identified and acted

upon in each work area under each supervisor who has received a 		Cost Containment Audit.

•  A tangible return on investment needs to be calculated for each

actionable item resulting from the Cost Containment Audit and 			forwarded to the MAC Chair within 30 days of the assignment.

Managers who fall short of these minimal performance requirements are to be visited by their executive, and the assignment is to be reissued to them.  Again, these are very minimal standards of performance.  It is likely that a moderate effort with all Associates in a normal department will result in 50 + responses to the Cost Containment questions.  Don’t settle for sub par performances.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.9	NATURAL RESOURCES MANAGEMENT AUDIT

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Facilities Management

Interactions With Others: 	Director of Facilities Management

Work To Do:  Natural Resource consumption and management is a highly specialized field of expertise.  Considering the hundreds of thousands of dollars spent annually for heat, electric, water, etc. a professional audit of the management of such functions is called for.

Speciality firms such as Johnson Controls will conduct such audits on a no fee basis as an opening opportunity to talk with you regarding their products and services.  Other energy management consultants will charge a percentage of the savings.  Either approach is acceptable.

The goal is to minimize cost outlay by employing smarter systems and processes of utilization and management of these resources.  For example, the means by which your organization procures electricity, natural gas, and water resources is quite negotiable.  Also, the scheduling of certain facility management functions will impact the cost of each process.  Just as telephone companies charge different rates for usage of the same telephone lines during different times of the day, or days of the week, the cost of electricity varies in the same manner.

The number of suppliers of natural gas are numerous, and thus the cost to purchase this commodity varies significantly from vendor to vendor.

It pays to employ an energy/natural resources specialist to conduct a facility-wide audit and outline your options for improvements.  Extraordinary cost savings in terms of thousands of dollars or more are expected from the results of this Task.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.10	PATIENT TRANSPORTATION ANALYSIS

Priority:  A

Timing: 	Session V

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Patient Transportation

Interactions With Others: 	Director of Patient Transportation

Work To Do:  Taking each of the service lines independently, chart the type and amount of patient transportation currently used in the service line.  i.e.  wheel chairs, walking to and from various departments for services, rolling beds to and from departments, etc.

Sum up the amount of time a typical patient in your service line spends transporting themselves or being transported by an employee, to and from various departments for service.  Brainstorm on how the transportation time can be reduced by at least 50%.  Think in terms of satellite units of service, pods of service, etc. which will reduce patient transport and speed delivery of service.  Use the following questions to generate creative thinking:

•	What services can be performed while the patient is in their own bed?

•	What services/equipment can be made mobile and brought to the patient rather than bringing the patient to the equipment?

•	How can departments with frequent patient interactions be relocated to a mutually convenient location in order to minimize the distance traveled by both patients and staff?

•	How can clinical testing be coordinated and sequenced so as to minimize the number of times the patient must change locations or travel through the organization?

The goal is to minimize the amount and distance traveled by both staff and patients, and to maximize the seamless flow of services to the patient in the most efficient, effective and fluid fashion.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.11	REVIEW TOXIC WASTE MANAGEMENT 				PROCESS/COSTS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Facilities Management

Interactions With Others: 	Director of Facilities Management

Work to Do:  Toxic waste management is often an unnecessarily costly and/or overly costly process.  There are methods for optimal management of toxic waste.  Your assignment is to benchmark top performing organizations in toxic waste management for information and ideas on how to better manage the cost of toxic waste from your organization.  Use the additive process theory, explained in Session V and found in the Session V workbook, to design an even better process for your organization to use in it’s management of toxic waste.  Your goal is to reduce the cost of toxic waste management by a minimum of 20%.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.12	REVIEW AND REVISE CATERING REQUESTS 			AND GUIDELINES

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Nutrition Services

Interactions With Others: 	Director of Nutrition Services

Work to Do:  Catering requests are a source of unruly, and often unexpected expenses for healthcare organizations.  In the many healthcare organizations that I have worked in, there is one thing that is constant—the frequency of food and drink that are made available to executives, managers and Associates on a routine, or nearly daily basis.  One can literally reduce their personal food budget by 30% if they were to attend the majority of “eating” events at the hospital!  One Associate of a New American Hospital said she had never “seen so much meetin’ and eatin’” as she did at that hospital!

The point here is simple and direct:  establish catering guidelines for all department managers, including the type of foods that are available for selection for specific types of events, the advanced time needed to place the catering order, etc., and managing the use of food for purposes other than patient care needs.  Consider charging departments directly for the use of food.  Nutrition Services people need to learn to say “no” to requests outside of the guidelines without being penalized/criticized for it.  Department managers need to be responsible for the costs of the food they order.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.13	REVIEW PURCHASING PROCESS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Purchasing

Interactions With Others: 	Director of Purchasing

Work to Do:  This Task will make traditional materials management people nervous.  They are likely to present some opposition to many of the concepts and directions of this Task.  It is important to get them to think in new and creative ways.  Stalinist traditional materials management staff will make it impossible to make progress in this area.

Assemble a group of coordinators and/or managers that frequently place purchase orders of supplies and equipment.  List the “customer” irritations with the current purchasing system and correct them.  Conduct a cycle time analysis of the purchasing process.  Where do time delays occur?  Make changes to eliminate time delays.

Identify three to five of the highest dollar volume vendors.  Following internal corrections in the processes of the Purchasing Department, involve each of the three to five major vendors in a further system enhancement effort.  Ask their advice on:

•	How to minimize average inventoried quantities carried, thus maximizing cost utilization.  Even though you may feel that you have squeezed every cost savings dollar out of the organization, working with vendors under your new and improved system will help you to identify otherwise unseen opportunities.

•	How to speed delivery of ordered articles to the organization and internal location where they are used.  Satellite inventories may be created or the delivery of materials may be made directly to the department initiating the request without passing through the receiving department first.

Many departments will not be able to fully or even partially implement a satellite inventory system.  Regardless of the situation for those items not inventoried in the department, the speed of delivery of requested items to the department must be improved by at least 50% with the goal being delivery upon demand or within the hour of request.

•	What additional services or processes can vendors provide which will make purchasing from them preferred over purchasing from other vendors?  i.e. the vendor delivers the product to each unit where it is to be inventoried, rather than to a centralized materials management department, thus eliminating the time delay of receiving goods in purchasing and then processing onto each respective unit.  Don’t give up quantity discounts or dollar volume discounts.  Convert vendor thinking from individual department orders to organization-wide orders when negotiating pricing.  Price negotiation should remain within the Purchasing Department.  Only individual ordering, inventorying and delivery would now possibly go directly to the departments.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.14	REVIEW THE LIFE SPAN AND REPAIR 				TENDENCIES OF DURABLE MEDICAL 				EQUIPMENT ON HAND IN THE ORGANIZATION

Priority:  B

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Purchasing

Interactions With Others: 	Director of Purchasing

Work to Do:  One of the frequent frustrations of patient care givers at all levels in all organizations is the undependable nature of the DME equipment needed to serve the patient; namely not enough equipment available, or the equipment that is available is not in good working order resulting in staff frustration, lost productivity, unsatisfied patients, etc.

The objective of this assignment is to take an inventory of the DME equipment needed routinely within each department and compare that need with the actual equipment that is available and assigned to the department.  Budget for the additional DME needed.

A second part of this assignment is for the Director of Purchasing to compare the life span of the current DME to the expected life span for that equipment.  In any case where the expected life span of the DME is less than the best/longest, new vendors need to be sought out.  In cases where the DME life span is disappointing, the Director of Purchasing should take up this issue with the vendor.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.15	CONDUCT COST ANALYSIS OF INTERNAL 			STAFF VS PURCHASED SERVICES FOR ALL 			EXTERNAL SERVICES USED.

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Finance

Interactions With Others: 	Department Managers

Work to Do:   Frequently, the cost of doing facility-based work with temporary or regular staff is significantly less costly than using an outside vendor.  This is the case generally with such projects as landscaping, facility repairs, clerical support, and many other services that the organization routinely contracts for with outside agencies.

This assignment is concerned with taking a more aggressive, self-managing approach to internalize the work projects through regular staff or temporarily employed staff, and redeploying the savings to other revenue generating projects rather than revenue consuming projects.

To begin this Task, audit the number of types of outside services that the organization uses.  Review this list asking the question, “do we have, or could we acquire, the competency to manage this work internally?”  If the answer is “yes”, then the next step should be taken.

The second step is to conduct a cost/benefit analysis and a comparison of the cost of the project if it is managed internally vs the cost of the project if it is managed by an outside organization.  If there is more than a 15% difference in cost, or more than $5,000 difference in cost, it is definitely worth bringing the project in-house to manage.

In many cases we have become dependent upon outside vendors to handle much of this work.  It becomes a relationship of convenience that must be broken in order to get the optimal use of our financial resources deployed.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.16	CONSIDER SUBSTITUTING REUSABLE 				MATERIALS FOR DISPOSABLE MATERIALS

Priority:  B

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Purchasing

Interactions With Others: 	Department Managers

Work to Do:  The majority of the supplies that we use in patient care management are disposable in nature.  The disposable nature is easier to use due to the need for sterilization, rapid deployment, etc.  However, there are numerous situations where disposable supplies could be substituted with reusable type supplies.  For example, velcro strips could be substituted for tape in the use of splints on patients.  The velcro strips are more cost effective and more comfortable for the patient— a double win.

Each department manager is to work with their staff and/or a focus group of patients to identify at least three, or more, disposable supplies or equipment that can be substituted with reusable supplies or equipment, and which would also prove to be a positive move from the patient’s perspective.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.17	REVIEW THE POLICY/PRACTICE ON FREE 			MEALS IN THE CAFETERIA

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Nutritional Services

Interactions With Others: 	Director of Nutritional Services

Work to Do:  Free food in the hospital is an on-going cost that needs to be better controlled.  Another task is dealing with the cost and frequency of catered food in the organization.  This task will address the number, frequency, and purpose of providing free meals to people other than patients, in the organization.  Common recipients of the free meals include physicians, visiting vendors, executives, and others.

Begin this Task by researching the number of free meals distributed in your organization.  Maybe your organization is an exception, and this is not a costly behavior for you.  However, if you are in the majority, you will find that the number of free meals distributed is substantial.

In that case, look at the types of people or situations wherein the free meals are being distributed.  If free meals are a perk provided to physicians, then think again.  What benefit does this provide to your organization, or is this something that has always been done at your organization—a carry over of days gone by that actually bring you no specific business benefit?

Consider rewriting your policy on free meals within the organization.  If all of this feels strange to you, as if you feel that you are “taking food out of someone’s mouth”, think again.  You can redeploy the costs of the free food you are giving away into a reward and recognition program for ideas and installation of ideas on how to improve the organization.  Remember, in the New American Hospital, everything is earned, and any good work that is done should be recognized and rewarded.  So, free meals do not fit into that philosophy unless is it a free meal as a reward for other work or ideas contributing to the overall performance of the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.18	REVIEW THE PROCEDURES & PROTOCOLS 			FOR RECYCLING EXPENSIVE MATERIALS 			AND SUPPLIES

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Department managers

Interactions With Others: 	Department managers

Work to Do:  Within many areas of operations in the patient care arena there are opportunities to recycle expensive components of the materials or supplies used in the service.  For example, the radiology film used in the Radiology Department can often be recycled through a specific radiological film recycling organization.  The resulting effect is a reduction in the cost of the film used for Radiology services.

The objective of this task is to get department managers thinking about the various ways in which they can become active in recycling portions of the more expensive equipment and materials/supplies used in their operations.  Radiology is one example.  A second example would be the refilling of the toner cartridge from the copying machine rather than ordering new toner cartridges.  This also reduces or eliminates the need and cost for disposing of the empty cartridge.  There are numerous opportunities of this nature throughout the organization.  Each department should be expected to identify at least one supply or equipment that can be recycled at a reduced cost to the organization.  Many departments will find more than one opportunity for recycling.  This task is both economically important as well as environmentally responsible.  Patient care areas, nutritional services, radiology and pharmacy are key target areas for significant change under this assignment simply due to the nature of the work that they do.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.19	EVALUATE HOSPITAL MAILINGS AND 				COSTS

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:

Interactions With Others: 	Mail department

Work to Do:  As an executive within an organization, a member of a residential community, and as a consultant to many healthcare organizations, I have seen and have received numerous mailings that went directly into the waste can.  By the same token, I have also seen and received a number of very effective mailings.  This Task is concerned with the large number of ineffective mailings that organizations routinely send out.

Begin by conducting an audit of the many types of printed communications that are mailed out from your organization each year.  Include the number of pieces represented by each mailing, the targeted audience for each mailing, the size of each mailing, and the frequency of each mailing.  Then, work to find ways to reduce the number of mailings that go out by combining publications, eliminating publications, redefining the frequency of publications, and better targeting the recipients of the publications.  Your goal is to reduce overall mailing costs by at least 30%.

For additional savings on mailing costs, question the means by which the communication can take place.  Is a written format always required, or can the written format be substituted, at least periodically, with film, posters or some other type of communication?  Also, look to your local bulk mailing specialist at the US Postal Services for other facts on how to reduce the costs of bulk mailings.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.20	MANAGE THE COSTS OF PRINTING AND 			DUPLICATION

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Purchasing or Material Management

Interactions With Others: 	Director of Purchasing or Material Management

Work to Do:  The costs of printing and duplication continue to spiral upward.  Many organizations have learned to manage these costs quite well.  Others have not yet paid attention to this cost.

The objective of this Task is to review the printing patterns, quantities and equipment currently in place in the organization.  Are the pieces of equipment sufficient to do the type of work and quantity of work your organization demands of it, or are you spending endless hours of unproductive time standing in front of the duplicating machine making the packets that you need?  In your assessment, consider the following costs of maintenance, supplies, paper and time to duplicate.  What types of printing jobs are more cost effective to have done outside the organization with a commissioned printer in his down time? Consider duplicating on two sides of the paper.  Look at the amount of manual time currently involved in copying and translate this to a payroll expense.  Can a volunteer be used for large duplicating jobs?  Can desk top publishing be used to offset graphic expenses that can be easily managed on a personal computer?  Look at all the options and compare them to your current operation.  How is it that your current operation can benefit from your ideas and changes?

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.21	PERSONAL USE OF FACILITY SERVICES

Priority:  A

Timing: 	Session II

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Director of Telecommunications, select managers

Interactions With Others: 	Director of Telecommunications, select managers

Work to Do:  Some people do not distinguish the use of facility assets for business from facility assets for personal use.  They kind of look at the facility as an extension of their personal life.  They rationalize their behaviors for using the long distance telephone lines for personal use, for taking office supplies home as school supplies for the kids, for using the mail room service and express mail for personal use, borrow facility equipment for personal use, etc.  The majority of people do act appropriately, however there are more than a few who fall into the inappropriate ranks.  Your Task is to create a greater awareness of the appropriate/inappropriate use of facility assets for personal use—in a respectful and forthright manner.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.4:	LOW COST INITIATIVES FOR OPERATING  			PROCESSES

TASK LC.4.22	DEVELOP A PROCESS FOR HANDLING A 			LARGE NUMBER OF REFERRALS AT ONE TIME 		TO AVOID CUSTOMER DELAY AND 				FRUSTRATION

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Chief Nursing Officer and Chief Operating Officer

Interactions With Others:

Work to Do:  Think ahead!  How will your system handle it when a large number of referrals are sent to your facility?  What will the contingency plan be for processing admissions, serving patient needs, etc.?  What will the maximum waiting time be?  Where will the additional resources come from?  What is the maximum capacity before you reach system overload?  Think through staffing needs, physical needs, physician needs, etc.  At what point in your business performance levels will you have to reach before you make changes to adapt to a heavier load?

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

Description And Objective Of Assignment: The objective of this assignment is keep the pace of innovation quick and steady within the organization.  The new culture of the New American Hospital is beginning to take hold in your organization, but there remains a great deal of work to be done.

Why Is This Assignment Made?  Many of the problemed areas in the organization, as well as many of the solutions to the problems, are brought up in the TUL training sessions.  These rays of enlightenment need to be captured and fully processed within the organization.  The following tasks will help you to capture these ideas.

In addition, your organization is now approaching the conclusion of the formal TUL classroom sessions whereby Management House has served as an extension of your organization development staff.  In the months following the conclusion of the formal TUL sessions, it is imperative to the continued success of the organization that you consistently look for ways to improve Customer Satisfaction, High Quality, Low Cost, and Best People.  The following Tasks will help to assure that constant innovation does occur within your organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.1	MANAGE INNOVATION

Priority:  A

Timing: 	Session VI

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC

Interactions With Others: 	None

Work to Do:  Use data from DIG records to analyze where operations are improving substantially.  Look for areas where DIG activity is strong and frequent.  These may be the areas that are significantly embracing the NAH philosophy and doing the necessary work to change their part of the organization.  Sort by KRA and other descriptors to retrieve the data and analyze the trends.  Look for departments with frequent and high numbers of DIGs, managers and/or Associates who have participated on a large number of DIGs or have created a large number of DIGs, or Associates who are responsible for innovation that have had a significant singular impact on the organization, i.e. high tangible ROI, relief from frequent Customer irritation, etc.

In those KRAs where there are fewer DIG ideas being generated, seek to set higher goals of achievement; establish a new or refreshed recognition, reward and reinforcement program for innovation and installation in that KRA, and attempt to focus the new KRA work to benefit one or more the BHAGs for this period of time.  If additional strength in leadership of this KRA is needed, identify a champion of the KRA.  The champion should be an informal, but strong and influential leader (Associate) within the Associate ranks.  Find some reason or reward for this person to take on the challenges of leading or assisting in the leadership of that KRA.  Others will follow.

In an additional sequence to this task, identify the departments, managers and Associates who will be responsible for your future KRA achievements and leadership.  These will be people who will possibly rotate onto one of the key strategy groups, and who will take either direct or indirect leadership roles in one or more of the KRAs or BHAG areas.  Begin by involving these people to a lesser degree now.  Familiarize them with your thinking and approaches.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.2	RESOURCE AND REWARD INNOVATION

Priority:  A

Timing: 	Session VI

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC

Interactions With Others: 	None

Work to Do:   At this point the DIG and JDI process is relatively mature in your organization.  It is likely that the process has undergone some degree of modification from it’s original introduction; it now works better for your organization; it has been customized to your needs.  It is now becoming a part of the culture.  The original reward, recognition, and reinforcement programs were designed to create and reinforce great numbers of ideas and DIG work.  At this point, it is time to start thinking in terms of newer, broader, bigger, rewards for achievement of the BHAGs in year two of TUL.

In year two, the NAH culture should be taking strong hold.  The concept of BHAGs should be common knowledge, and you have had some experience in the first year with setting BHAGs.  For the BHAG concept to be successful, it must be reinforced with substantial rewards for achievement of the goals, and consistent communication as to the status of achievement of the BHAG goals by department, and for the organization as a whole.

Do not let innovation slow for want of resourcing.  Consider profit sharing of new revenue or expenses saved to fund innovations.  Design a reward structure for hard and soft ROI projects.  Include substantial rewards for all Associates whose departments meet their BHAG goals.  Achievement of BHAG goals will unite the strong in your organization, and highlight the weak.  They will build a net among team players, and isolate non team players.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.3	MEASURE AND SET GOALS FOR INNOVATION

Priority:  A

Timing: 	Session VI

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC and CEO

Interactions With Others: 	MAC and CEO

Work to Do:  The implementation rate for DIG ideas in year two needs to be boosted to 90% + implementation of all ideas submitted, or portions of all ideas submitted.  By this point in time, DIG and DIG Chair training should have occurred for nearly all Associates, thus the quality of the DIG process should have evolved to something considerably greater than it was in year one.  In addition, the organizational culture at this point should be much more open and receptive to piloting and/or accepting new ideas.

By this point in time it is important that the work of innovation and DIG idea creation become a part of every Associates’ job and work responsibility.  In an earlier Task we asked that the job description for all Associates be revised to include the creation of a specific number of DIGs each year.  At this point, it is time to assure that DIG ideas and implementation requirements become a greater part of each Associate’s job description.  Raise the bar of expectations to at least two ideas created and implemented each year for each Associate.  The key to this Task is the implementation of the ideas.  It is no longer good enough to just generate an idea.  Each Associate must be active in implementing at least two new ideas each year.  Assure that new minimal standards of performance are added to the Associate and managerial performance evaluation format.  By the way, the number of ideas generated and implemented should be greater for managers than for Associates.  We recommend a minimum of five new ideas and installations for each manager and a minimum of two new ideas and installations for each Associate.

You can take this idea even further and target the type of ideas to be generated either by BHAG category or KRA, as needed by the organization.  A new and more significant reward concept involves competition for promotions.  You can take this concept in one of two directions.  One, establish a significant number of DIGs to be created and implemented as a part of the qualification process for internal promotions.  This assures that those who move into supervisory, management, or executive positions are fully involved in the innovation process within the organization.

A second approach, which is also a “power” type reward, is to allocate temporary powers (for a given period of time) to those who are selected based on their recent past performance in terms of innovation.  This “power” type reward can be designed to have “power” over a given amount of innovation dollars for a specific KRA for a specific period of time, or it can be designed to be a position in charge of a specific major innovative project that may or may not be a part of the Associate’s usual work responsibilities.  If it is not a part of the Associate’s routine responsibilities, then the reward may seem to be of even greater value.  See the trend?  A new type of reward and recognition process that is added on to the already existing 3R process.  Get creative.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.4	INSTALL THE IDEA ENGINE

Priority:  A

Timing: 	Session VI

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC

Interactions With Others: 	MAC

Work to Do:  New DIG and operational ideas will drop off significantly at the conclusion of the formal TUL classroom session.  The Idea Engine is designed to open up more and more channels of communication and innovation in the organization in order to keep innovation alive.  Up to this point we have been focusing primarily on ideas generated by Associates, and managers.  Although this group remains the primary source of continuing ideas for continuous improvement within the organization, we will now actively go to physicians, vendors, patients, and the community for additional innovative ideas for improvement.

This Task is centered around the challenge of opening up new channels of communication and innovation within and around the organization.  The key to success will be the promotion of the channels of communication as well as involvement of the idea initiator in the installation of the idea.  Involvement solidifies the experience and tends to create additional buzz within the community and circles of communication surrounding the idea initiator.  This type of communication is news worthy and will have a positive impact on the future relationships of these special populations of people and the healthcare organization.  These are relationships that can become everlasting; valuable assets to the organization that can be drawn upon at later dates for future problem-solving help or innovative ideas.

Make the Idea Engine easy to access and utilize by those outside of the organization.  Think in terms of telephone access, or computer access via the WEB, or any other medium that is easy to transfer an idea quickly and easily into the organization.  Time has always been a valued asset, but in today’s fast paced living environment, it is truer than ever and ideas are lost simply because of the inability to easily deliver them to someone who can do something with them.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.5	DEVELOP REWARD AND RECOGNITION FOR 			LOW COST IMPROVEMENTS

Priority:  A

Timing: 	Session V

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC

Interactions With Others:

Work to Do:  The work of this TUL Session is more difficult and sophisticated than other pieces of work in TUL.  The reason is because it involves the revamping of major processes. systems, and service lines within the organization.  This work crosses many lines of authority and work design, and requires open thinking and a non territorial approach to work redesign.  Special reward and recognition programs are needed to motivate and reward those who do the tough work of process and system analysis and change.

Your Task is to create 3R (reward, recognition and reinforcement) programs that are specific to low cost and high quality improvements to work processes, systems, and service lines in order to drive the motivation and work.

Think in terms of a major reward or recognition for those who overhaul significant processes, systems, or service lines.  It is known that there are significant opportunities for improvement in all of these ideas, but it requires the open thinking of the managers in charge of these operations in order to make the changes.  Too many organizations procrastinate on processes and system work, or are blind to the needs for improvement until it is too late.  When it becomes too late, the fate of the process and department move out of the control of the manager and into the hands of a dramatic cut and slash approach that is damaging to the organization.  As Jack Welch states in the title of his book, “Control your Destiny or Someone Else Will”  Now is the time to take control of your destiny by controlling and improving the work processes you are involved in and responsible for.  This Task is responsible for developing unique reward and recognition programs for those who do this work.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.5:	LOW COST INITIATIVES FOR MANAGING 			INNOVATION

TASK LC.5.6	STANDARDIZE COMMON PATIENT CARE 			ADMINISTRATIVE PROCESSES

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC

Interactions With Others: 	Representatives from nursing care staff

Work to Do:  This Task is concerned with standardizing the common administrative processes used on all patient care units in order to make it easier and faster for administrative, support, and clerical staff to rotate from unit to unit, and easily find the materials needed to do their job.  There are specific common elements on every unit that can be standardized among the units.  For example, where forms are kept, where records are kept, how records are kept, where communication information for the unit is posted, where recent and critical information is kept on the unit, how to handle basic protocols with patients, physicians, and management for each unit etc.  The objective is to make transferability from unit to unit easy, efficient and effective for staff.

Begin by convening a focus group comprised of representatives from the various job titles that work on the unit in a clerical, administrative, or support capacity, and listing:

•	The various duties that they do

•	The frustrations that they experience

•	Their ideas on what could be standardized on each unit.

Then go to work to make it happen with their help.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

Description And Objective Of Assignment: The objective of this assignment is focus the energy and attention of physicians on low cost, high

quality initiatives.

Why Is This Assignment Made?  Until this point in time, physicians have been involved in the NAH effort in a secondary way, as needed in particular situations, as called for.  There have been few initiatives that directly effect all physicians.  The following initiatives are largely applicable to some degree to all physicians in some positive manner, and will have a significant impact on the quality of services provided by physicians to your organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

TASK LC.6.1	PHYSICIAN UTILIZATION OF CARE MAPS;

CLINICAL PATHWAYS AND PROTOCOLS

Priority:  A

Timing: 	Session V

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	MAC, Medical Staff Leadership

Interactions With Others: 	MAC, Medical Staff Leadership

Work to Do:  Most organizations still have a number of physicians on staff who are operating outside of the approved clinical pathways, protocols, care maps, or any other designated patient care protocol.  They are still ordering unnecessary items, procedures, tests, etc. and using organization resources in a less than optimal manner.  The reasons for these behaviors is not always known.  What is important is that we change these behaviors that are outside of the acceptable protocols and replace them with behaviors that still meet the physician’s needs and are also within the clinical pathways, or accepted protocols.  Time is running out, and your patience with rebel-like physician behavior, or physician resistance to change must become more action-oriented.

Your Task is to identify the physicians operating outside the approved clinical pathways, review their resource utilization and record of disciplinary discussions, and develop an action plan to correct the inappropriate behaviors now.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

TASK LC.6.2	EVALUATE THE USE OF ECONOMIC 				CREDENTIALING FOR PHYSICIANS

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	CEO and medical staff leadership

Interactions With Others: 	CEO and medical staff leadership

Work to Do:  The concept of economic credentialing, which is sometimes known by other names, is the evaluation of past physician performances with regard to resource utilization for particular types of diagnoses and cases.  To the extent that we credential physicians to use hospital facilities based on their training and medical background, so should we credential them to use hospital facilities or not based on their resource utilization and quality outcome backgrounds.

If you are not already involved in economic credentialing, then it is time to investigate it’s applications and results, and begin installation of economic credentialing.  If you plan to install such a protocol on a gradual basis, then begin with the diagnosis and physicians who are most dramatically outside of the normal resource utilization patterns.  Cut your losses in this arena first and set an example for others who might naturally choose to change their behaviors before they become future examples and/or issues.  The best situation is when the facts speak for themselves and physicians can see how far outside the protocols their specific behaviors are.  The second best situation is when physician peer groups can be influential enough to change physician behaviors.  The least preferable situation is when an ultimatum must be issued.

In any case, economic credentialing will force the issue.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

TASK LC.6.3	REVIEW SERVICES PROVIDED TO PHYSICIANS 		AND THE COST/BENEFIT ANALYSIS OF THE 			SERVICES

Priority:  A

Timing: 	Session III

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	CEO and medical staff leadership

Interactions With Others: 	Department managers as needed

Work to Do:  Take an inventory of the perks, benefits, and free-bees provided to physicians in order to attract them to practice at your facility.  Translate the perks into tangible dollars.  Consider the benefits you are supposedly deriving from the investment in these perks.  Is the organization realizing the benefits they thought they would from these endeavors, or possibly not?  For example, many organizations offer physician financial incentives such as advancements on the cost of Yellow Page advertising, billing services, etc. for which reimbursement is agreed to and expected, but for which the amount of follow-up required to get the reimbursement is excessive.  If you find that the financial incentives are indeed valuable, then look to restructure the situation to assure a timely and uninterrupted payback.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

TASK LC.6.4	EVALUATE THE CONTENTS OF THE NEW 			HIRE/ASSOCIATE PHYSICAL EXAM FOR 			APPROPRIATENESS AND COST 					EFFECTIVENESS

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Physical exam physician

Interactions With Others: 	Department managers, as needed.

Work to Do:   The new Associate hire physical evaluation/exam process is in need of review.  The cost of conducting a new Associate physical exam ranges from nearly nothing to several hundred dollars in tests and physician fees for exams that are not necessary for the employment situation.  What aspects of the current new hire physical exam process are truly necessary, and which can be deleted as they have no direct impact on the person’s ability to do the job, or as a liability (worker’s compensation) to the organization?

Many organizations conduct a full physical exam including pap exam, EKGs etc. on all new Associates and on other Associates for their annual physical exam.  Some of this is over-kill and not needed.  At the same time, we need to assess what additional testing should we be doing during the physical exam to assure that the person is physically capable, without threat of damage to themselves or others, to do the job?  Review and revise the new Associate physical exam content to design an exam that better assesses the potential liabilities that a new Associate may bring to the organization.

NEW AMERICAN HOSPITAL ASSIGNMENT

INITIATIVE LC.6:	BEGIN PHYSICIAN FOCUS ON LOW COST 			INITIATIVES

TASK LC.6.5	EVALUATE THE POSSIBILITIES OF STANDING

PHYSICIAN ORDERS FOR HIGH NEED PATIETN 		LOAD/TRAFFIC AREAS

Priority:  A

Timing: 	Session IV

Teamleader: 	Module Leader

Recommended Approach: 	DIG

Other Assignees:	Medical staff representation as needed

Interactions With Others: 	Medical staff representation as needed

Work to Do:  Some areas of high traffic patient care operations represent consistent requests for routine physician orders, yet physicians are not always readily available to the patient care staff.  The result is that nurses, patients and others wait for the physician to present him/herself before the order can be written.  This “waiting” represents unproductive, down time for the patient and staff, and contributes to a longer length of stay as well as frustrations for staff and patients.

Identify areas where there are consistent requests for the same types of tests, prescriptions, services, etc. that, by law or licensing require a physician to order, but in reality, the nurses alert the physician as to the need, and they (nurses) typically administer the treatment.  Can you establish a standing physician order, with specific qualifying conditions surrounding it, that nurses can turn to in order to keep the process flowing rather than stopping it to wait for the physician?  Areas to consider are those in the ER, outpatient surgery, etc.

To begin, convene a focus group of nurses on each unit and ask them what physician orders would be helpful to have on a standing basis for them to use in order to keep the flow of patient service going in the absence of a doctor?  With the help of the quality and risk management staff, determine which of the ideas presented by each focus group can safely be turned into a standing physician order to be accessed by the nursing staff in specific, outlined, patient situations.  Calculate the amount of time saved that is represented by the use of these standing orders.  Translate the saved time on an annualized basis into length of stay and assign a value to the length of stay that is saved with the use of the standing physician order.