## NAH √list 91 (7-04)
CREATING THE NEW AMERICAN HOSPITAL
ORGANIZATION RENEWAL ACTION PLAN (Version 92.0: 9/06)
Part of the Gold Standard Management Series
Registered Copyright: Gold Standard Management Institute & Management House, Inc
Visit us at GoldStandardManagement.org or ManagementHouse.com
1. Use following list of organization change items to create action plan. Check what's needed and add other items.
2. What's needed: Sweeping overhaul in corporate culture, radical shift in management philosophy, & a permanent
commitment at all levels of the organization to seek continuous improvements
3. Timing codes are suggested start & completion times based on Management House experience.
BTUL = Before TUL course begins
S1 = Session 1
S2 = Session 2
S3 = Session 3
S4 = Session 4
S5 = Session 5
YR1 = 1 year from program start
Priority codes: A = Must Do; B = Must Do, can go 30 days longer than shown;
C = Optional, but recommended.
Work not done, or not done on time, will retard the speed & quality of organization renewal attained.
4. Assignments. Each Module is assigned to an exec/manager by the CEO & is responsible for overall execution.
Task leaders are chosen by Modular Leader with help from MAC. Assignments shown are suggested only.
Leaders may assign pieces to DIGs or JDIs. Progress on all items is monitored & overseen by MAC
& reported to CEO.
CAC = Communications Action Council
CEO = Chief Executive Officer
DIG = Do It Group. Groups under direction of a chair, department head or MAC.
JDI = Just Do It. Usually these items are assigned to a single in-house subject matter expert or change
agent.
MAC = Management Action Council. Items done by MAC, or which they oversee in DIGs or assignment.
MGRs = All managers/supervisors. This item may require a team recommendation or something all
teams are to do.
MHI = Management House Inc. Consultant. These items usually are consultant assisted.
ML = Module Leader. Responsible for ensuring implementation of all module tasks.
SAC = Socialization Action Council
VP or VPs = Vice President of a function, or VPs as a group.
BTUL = Before TUL course (seminars) begins
WAVE 1—ORGANIZING FOR REVOLUTION
MODULE BTUL: PLAN, SELECT & ORGANIZE
Module Leader:
INITIATIVE BTUL.1: SET UP INITIAL ASSIGNMENTS
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing// | Team | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BTUL.1.1 | ASSEMBLE THE CHANGE TEAM |  |  |  | BTUL/A | CEO | JDI
Set up a dynamite MAC, SAC, CAC, RAC, RAC, PAC. Bright, nervy, mouthy,
energetic people who can lead the change.
Secretary available on at least half time basis to support MAC.
Plan for separate DIG Coordinator position as volume builds rapidly.
Macintosh computer capability will assist interaction with MHI.
BTUL.1.2 | PLAN THE KICK OFF |  |  |  | BTUL/A | MAC | DIG
|  | Identify location & send invites. Prepare speeches. |  |  |  | Chair
Prepare TUL material handouts, assignments, expectations.
BTUL.1.3 | MAC BEGINS WORK PER MAC GUIDE |  |  |  | BTUL/A | MAC | DIG
|  | Set up a "Genesis Room" for all MAC meetings, items, posted plans. |  |  |  | Chair
Review MAC Guide in detail.
Create Gantt Chart of tasks.
Use check off list for Pre-TUL preparation.
BTUL.1.4 | SELECT MODULE LEADERS WITH CEO |  |  | A | BTUL/A | MAC | JDI
|  | Pick well organized drivers to oversee that all module tasks accomplished. |  |  |  | CEO
MAC retains overall coordination responsibility.
Module Leaders report to the MAC for the duration of their project.
BTUL.1.5 | MAC & MODULE LEADERS REVIEW THE NAH ACTION PLAN |  |  |  | BTUL/A | MAC | DIG
|  | First determine that 90%+ of items are acceptable. |  |  |  | Ex. Vision
Discuss doability of the work list in the time constraints suggested.
Agree on approach to task & make assignments.
Notify MHI of any items that will not be implemented, allow MHI to advise.
BTUL.1.6 | COORDINATE NEEDS FOR TUL COURSE |  |  |  | BTUL | MAC | JDI
|  | Review specific needs for speaker, seminar site, seminar support. |  |  |  | Chair
BTUL.1.7 | DESIGN DIG/JDI TRACKING SYSTEM |  |  |  | BTUL/A | MAC | DIG
|  | Review forms and data to be collected. |  |  |  | Chair
Minimum data collected includes; DIG #, Chair name, cost, ROI, completion
date, telephone #, KRA field.
BTUL.1.8 | SAC BEGINS WORK PER SAC GUIDE |  |  |  | BTUL/A | SAC | DIG
|  | Plan one social event after each TUL Session. Plan at least one cheer, |  |  |  | Chair
skit, or song, for the start of Day 2 of each TUL Session. Organize
social events between TUL sessions and spread SAC events throughout
the organization.
BTUL.1.9 | CAC BEGINS WORK PER CAC GUIDE |  |  |  | BTUL/A | CAC | DIG
|  | Plan program orientation for managers. |  |  |  | Chair
Place NAH Scoreboard in cafeteria to record gains.
BTUL.1.10 | EXECUTIVE MEETINGS TO PREPARE FOR CHANGE |  |  |  | BTUL/A | MAC | JDI
|  | Purpose is to orient in-house change Agents via philosophy discussions. |  |  |  | Chair
Vision Council members read "Creating the New American Hospital" ASAP.
Assess history/culture of organization: What Values are in our history?
Don't underestimate need to create new management culture.
Create awareness that quality, not cost, key to success.
Create atmosphere of Excellence as an offense strategy,
not survival of defense.
Open Challenge Climate to foster innovation & bias for action.
BTUL.1.11 | TUL CHEERLEADER RESPONSIBILITIES |  |  |  | BTUL | MAC | JDI
|  | Purpose is to demonstrate executive leadership & socialization skills. |  |  |  | Chair
Act as the TUL hospital advocate.
Keep TUL initiatives/philosophies on the forefront of discussions.
Take up slack when there is extra TUL work to do & no one else is volunteering.
Keep socialization & a sense of humor in the culture.
This is a rotating assignment.
BTUL.1.12 | RAC BEGINS PER RAC GUIDE |  |  |  | BTUL/A | RAC | DIG
|  | Review RAC Guide and objectives. |  |  |  | Chair
Chart all current RAC activities & their effectiveness levels.
Identify where ineffective programs exist & replace them.
Where do new RAC programs need to be placed?
BTUL.1.13 | TAC BEGINS PER TAC GUIDE |  |  |  | BTUL/A | MAC | JDI
|  | Review TAC Guide and objectives. |  |  |  | Chair
|  | Review NAH Action Plan for tasks involving TAC support. |  |  |  | TAC
|  | Chart when training will be needed. Identify audience sizes. |  |  |  | Chair
Organize trainers and schedules to be prepared for TAC training.
BTUL.1.14 | PREPARE DIG TRAINING FOR TUL S 1 ROLL OUT |  |  |  | BTUL/A | MAC | JDI
|  | Develop internal DIG training program for mgrs to experience immediately |  |  |  | Chair
|  | following TUL S1. |  |  |  | TAC
Chair
INITIATIVE BTUL.2: MAKE EARLY KEY PERSONNEL DECISIONS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing// | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BTUL.2.1 | SELECTION OF THE NAH MANAGEMENT TEAM |  |  |  | BTUL/A | CEO | JDI
Remove Obvious "Losers": Uncommitted Executives.
HR executive: Adequate for heavy demands of renewal effort?
Nurse executive: Half the people depend on her/him to lead change.
CFO: An innovative resourcer & business builder or only naysayer?
COO: Will there be program enforcement & dynamic support?
Weak links in the chain? Ask for executive assessment if needed.
Remove Obvious "Losers": uncommitted managers and supervisors.
Allow people to transfer to staff jobs or leave organization.
Decide whether all current managers should attend TUL.
Not inviting certain managers is a powerful change message to others.
Decide whether any non management high potentials should attend TUL.
BTUL.2.2 | BUILD THE EXECUTIVE TEAM |  |  |  | BTUL/A | CEO | JDI
Purpose is to "get tight", speak with "one voice".
Heal executive schisms, get the team together, create top unity.
Keep philosophical differences in closed conversation.
Socialize the executive team.
Sign the commitment to excellence, require the blood oath.
BTUL.2.3 | ASSURING VP PERFORMANCE & "FIRE IN THE BELLY" |  |  |  | BTUL/A | CEO | JDI
CEO counsels with VPs about the importance of their commitment.
VP leadership example a requirement for organization success.
Install Executive Buddy System.
Install MBWA standards for managers.
Begin executive coaching sessions.
BTUL.2.4 | CHANGE EXECUTIVE HIRING PRACTICES |  |  |  | BTUL/A | CEO | JDI
Improve selection processes: Leaders, not managers.
Hire experienced risk takers, don't rely on staid & fearful.
Promote from within to send powerful change message.
INITIATIVE BTUL.3: CREATE A CHANGE STRATEGY & ACTION PLAN
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BTUL.3.1 | ADOPT/ADAPT CHANGE ACTION PLAN FOR ORGANIZATION RENEWAL |  |  |  | BTUL/A | Executives | DIG
Plan on several planning sessions & discussions.
Set up a detailed action plan. Spend a lot of time and thought on it.
Remember that it’s easier to fight a war on paper than on the battlefield.
Review the Organization Renewal Action Plan (this document)
Are all elements acceptable? What needs to be added/changed?
Make assignments, set dates & priorities.
Complete the MHI "Inventory on Change Management" & "Action Plan."
Discuss & plan based on the sections of the "Action Plan."
• Manage the Change Formula
• Assess the environment & change situation
• Deal with resistance
• Action planning & next steps
Read Dr. Sherman's book, "Creating the New American Hospital"
BTUL.3.2 | PROVIDE SUFFICIENT HR SUPPORT FOR CHANGE EFFORT |  |  |  | BTUL/A | VP HR | JDI
|  | Consider having an HR Audit conducted to assess department adequacy. |  |  |  | MHI
HR staffing adequate? One FTE/100-150 employees is standard.
T&D budget adequate? $2200/-IBM, 3.7% budget-Motorola, 5% hours-HP.
Start identification of in-house trainers for:
• Associate orientation to NAH & values statement
• DIG training
• Continuous improvement training
BTUL.3.3 | BUILD PROGRAM SUPPORT AMONG THOUGHT LEADERS |  |  |  | BTUL/A | CEO | JDI
Think through what constituencies need to be communicated with.
Identify thought leaders. What concerns will they have?
Do the political work of persuasion. Deal with board concerns
through communication. When and how will you make them look like heros?
Get thought-leader physicians on board. Organize a communications campaign.
Identify MD problems experienced with hospital. Fix for credibility.
Devise communication/participation approaches to key groups/individuals.
Socialize & network supporters. Act quickly: Produce results to increase
credibility. Find supported critical issue to quiet resistant enclaves.
Publicize our gains, competitors' losses.
How will you stand out above the crowd in TUL?
BTUL.3.4 | CONDUCT EXECUTIVE CHANGE MANAGEMENT READINGS PROGRAM |  |  |  | S0-5/A | CEO | JDI
Use Vision meetings periodically to discuss major change issues.
Purpose: Stand back & assess what's going on in the change process.
Assign Vision member to lead discussion based on suggested readings.
BTUL.3.5 | IDENTIFY EARLY DIG PROBLEMS TO SOLVE |  |  |  | BTUL/A | MAC | JDI
Identify 10- 12 DIG problems to solve prior to TUL S 1.
BTUL3.6 | IDENTIFY CEO RECOGNITION PLAN |  |  |  | BTUL/A | MAC | JDI
|  | Identify managerial and Associate recognition plan that will be given to CEO. |  |  |  | CEO
BTUL.3.7 | ADMINISTER INVENTORY ON CHANGE MANAGEMENT |  |  |  | BTUL/A | Executives | JDI
|  | Focus on the formula for change and particularly the amount of dissatisfaction |  |  |  | MAC
of "Big D" in the organization. How will you generate enough Big D to keep
the momentum for improvement high?
INITIATIVE BTUL.4: FINANCIAL CHANGES TO SUPPORT RENEWAL
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BTUL.4.1 | RETURN ON INVESTMENT CALCULATION |  |  |  | BTUL/A | CFO | DIG
Prepare Return On Investment (ROI) form for DIG/JDIs to use & track their
contributions.
BTUL.4.2 | DEVELOP BUDGET FOR IMPROVEMENTS & DIG IDEA IMPLEMENTATION |  |  |  | BTUL/A | CFO | JDI
Don’t say no because of dollars.
Ask for no & low cost options to lower resource utilization.
Create development accounts to fund innovation.
Pursue operations auditing as a way to dig out waste. Allow for a % of dollars
saved to the unit to fund future changes.
BTUL.4.3 | INSTALL NEW AMERICAN HOSPITAL FINANCIAL MANAGEMENT PRACTICES |  |  |  | S1/A | CFO | JDI
Reduce approvals required, increase spending limits.
Integrate Customer service & Associate programs to budget.
BTUL.4.4 | CREATE PROFIT CENTERS |  |  |  | S3/B | CFO | DIG
Revenue generating departments to receive profit & loss statement.
Move away from expense budget information only to increase accountability.
Make more clear the distinction between profit generating & using units.
BTUL.4.5 | DETERMINE BHAGs MEASURES OF PERFORMANCE |  |  |  | BTUL/A | CEO | DIG
Use 4- part strategy of Hi Satisfaction, Hi Quality, Low Cost, and Best People
around which to establish four primary BHAGs; one in each of the four
categories. Be prepared to share BHAGs with TUL group at Session I.
Then roll out BHAGs to all departments with specific department goals.
BTUL.4.6 | DETERMINE DEPT/INDIVIDUAL BHAGs & MEASURES |  |  |  | BTUL/A | MAC | DIG
Organization BHAGs are to be allocated to departments in a manner that will
allow for achievement of organization goals.
INITIATIVE BTUL.5: ESTABLISH DIG SYSTEM
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BTUL.5.1 |  | Locate Victory Scoreboard on large cafeteria wall or well-traveled hallway. |  |  | BTUL/A | CAC | JDI
Explain to Associates how the Victory Scoreboard works, categories, etc.
BTUL.5.2 | INTRODUCE DIG SYSTEM TO ORGANIZATION |  |  |  | S1/A | TAC Ch. | DIG
Select DIG trainers.
Launch DIG training sessions.
Communicate the program.
Incorporate the collectin of DIG ideas from Associates into every organizational
event.
WAVE 2—THE CHANGE MACHINE
MODULE LD: PROFILES IN EXCELLENCE
KRA Focus: Organization Culture (Build the Management Machine)
Module Leader:
INITIATIVE LD.1: CHANGES ADDRESSED AT UNCOMMON LEADER SESSION
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.1.1 | CONDUCT TUL SESSION: "PROFILES IN EXCELLENCE" |  |  |  | S1/A | MHI | JDI
Day 1: "Creating the New American Hospital"
Day 2: "Uncommon Leadership & Management Effectiveness"
LD.1.2 | CHANGE ELEMENTS INTRODUCED BY PRESENTER AT TUL SESSION |  |  |  | S1/A | MHI | JDI
Create values statement in management development session.
Assign managers to seek benchmark comparison for unit.
Group assigned to suggest changes in executive & management titles.
Capitalize Customer in all publications & correspondence.
Capitalize Associate in all publications & correspondence.
Introduce MANSYS & get early concept adoptions.
Set up KRA hours.
Adopt meeting management guidelines.
Assign quarterly work planning–MS-02.
Educate on Work-Gating Concepts.
LD.1.3 | PROVIDE TUL SESSION SUPPORT |  |  |  | BTUL/A | MAC | DIG
Organize meeting site, TUL supplies, and speaker requirements.
LD.1.4 | PROCESS INCOMING MANAGER SUGGESTIONS FROM TUL SESSION |  |  |  | S1/A | MAC | JDI
Use overhead lists created at session—extend by brainstorming.
Sort rapidly & assign to DIGs, Just Do Its.
Where possible, direct work to JDIs to speed time lines.
Keep balance between Module Action Plan items & manager suggestions.
Must build the management machine, not just react to manager targets.
Get set up with computer to plan, track & retrieve data.
INITIATIVE LD.2: ESTABLISH VALUES CENTERED MANAGING & CLIMATE
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.2.1 | DEVELOP COMMITMENT STATEMENT |  |  | A | S1/A | ML | JDI
All supervisors & managers to sign statement.
All supervisors & managers to display statement in work areas.
Decide whether to open up signing to all Associates.
Publicize Commitment Statement.
Anyone disagreeing to be moved to staff function or out of organization.
LD.2.2 | REVIEW & APPROVAL OF VALUES STATEMENT |  |  |  | S1/A | CEO | JDI
Insert executive demands/standards: What values do they want?
Test: Will "Service, Respect, Excellence" be absolutely required?
Test values statement with reference groups: Any political fallout?
LD.2.3 | CREATE VALUES GUIDE FOR ASSOCIATES |  |  |  | S1/A | MAC | DIG
Can be separate or rolled into Associate handbook.
Don't slow down introduction if Associate handbook redo will take time.
Spell out specific value-centered behaviors.
Use with recruitment efforts.
LD.2.4 | HOUSEWIDE ROLLOUT OF THE VALUES STATEMENT |  |  |  | S2/A | MAC | DIG
Multiple publications highlighting the Values.
Signage "Writ Large," intensive internal values public relations campaign,
"Pump" the Values.
Orient All Associates to the meanings & use of values & NAH concepts.
Include in New Associate Orientation.
LD.2.5 | ADD VALUES & NAH PHILOSOPHY TO NEW ASSOCIATE ORIENTATION |  |  | A | S2/A | ML | JDI
|  | Associates sign commitment & values statement. |  |  |  | HR Dir.
Explain DIGs, JDIs, BHAGs, department BHAGS, and how each Associate
can individually participate.
INITIATIVE LD.3: REDEFINE EXECUTIVE ROLE & JOB
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.3.1 | REDEFINE EXECUTIVE TEAM ROLE IN SERIES OF DISCUSSIONS |  |  |  | S1/A | CEO | JDI
Define what a NAH executive should do.
Openness to criticism, participation, & supportive of change required.
Send drumbeat to managers: a management transformation required.
Redefine executive jobs as Listeners, Servants, Integrators, Visionaries.
Change executive titles, concept introduced in TUL.
Executives are to lead by example, do what the program calls for.
Warn against being aloof from the change effort.
Create constancy of purpose toward improvement of service.
Drive out fear so all may work effectively.
LD.3.2 | ESTABLISH NEW EXECUTIVE ROLE BEHAVIOR REQUIREMENTS |  |  | S-1 | S1/A | CEO | JDI
MBWA required 50% of time.
Executive group to review MBWA procedures, avoid aimless wandering.
Executives to ask for managers rating on their MBWA effectiveness.
VPs visit all departments, all shifts in area of responsibility early & often.
Explain NAH changeover, ask for ideas.
VPs work in their departments minimum of 1 month/year.
VPs cheerlead the change process, celebrate achievements, encourage all.
Download delegation: Push decisions to lowest possible level.
Identify problem categories that can be moved downward.
Identify tasks to discontinue.
Identify areas where manager review will be discontinued.
Goal: free up time for true executive work.
VPs to remove themselves from most operations decisions.
Consider casual business dress for managers to reduce status barriers.
LD.3.3 | VP CONTROL REQUIRED AS PART OF CHANGE PROCESS |  |  |  | S1-5/A | VPs | DIG
|  | Monitor each manager's understanding & development needs. |  |  |  | ML
Coach, counsel, warn managers regarding progress after each session.
Break barriers between departments & require team work.
Review MAC input regarding manager compliance with assignments.
Focus on quarterly work plans, KRA hour, staff development.
Review manager's impact on divisional NAH goals.
Require managers to champion values & change direction.
INITIATIVE LD.4: REDEFINE MANAGER & SUPERVISOR TEAM ROLE & JOB
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.4.1 | REDEFINE MANAGEMENT TEAM ROLE IN SERIES OF DISCUSSIONS |  |  |  | S1-2/A | VPs | JDI
|  | Define what a NAH manager should do: |  |  |  | ML
Creative destroyer, hit man of the useless.
Creator of the new, midwife to the future.
Openness to criticism, participation, & supportive of change required.
Redefine manager jobs: Team adviser, senior Associate, servant, coach.
Change manager titles, concept introduced in TUL.
Send drumbeat to managers: a management transformation required.
Management blood oath: Signature to excellence commitment.
Fire up management attitudes & motivation.
Warn against being aloof from the change effort.
Go to OPEN communications---Everything in the open.
First amendment speech, new channels/subjects allowed.
Control clans & departmental agendas; team build or flatten resistance.
Use team building and socialization, isolate resisters, change group norms.
Remove manager blockages for political credibility, gain allegiance.
Create continuous improvement expectation, accept less than perfection
Drive out fear, identify and remove intimidators and restraint elements.
LD.4.2 | ESTABLISH NEW MANAGER/SUPERVISOR BEHAVIOR REQUIREMENTS |  |  |  | S1-3/A | VPs | JDI
|  | Discussion held by each VP with their managers: |  |  |  | ML
Throw out job descriptions as actual manager behavior guide—use values.
Require managers use effective management practices found in MANSYS.
In time, manager evaluations will be done by peers, Associates, Customers.
Status differentials between managers & Associates will be reduced.
Consider casual business dress for managers.
Force download delegation, systematic reassignment of work downward.
Determine match between work & level.
Decisions at lowest possible level to increase speed, quality.
Require both high structure and high consideration in leadership.
MBWA as required style, teach specifics of how-to-do & set time standard.
Large % work time with Customers/Associates—Listen, believe, do.
LD.4.3 | ESTABLISH NEW LEADERSHIP SELECTION CRITERIA |  |  |  | BTUL/A | CEO | DIG
Improve selection via job posting, group interviews, assessment, training.
Promote from within, no leadership spots to inexperienced.
Select leaders, not managers. Key need is people skill, not technical.
Hire risk takers, entrepreneurs, commandos.
Remove uncommitted and problem managers, reward supporters.
LD.4.4 | REMOVE PROBLEM LEADERS & DEVELOP TEAM COMMITMENT TO NAH |  |  | A | BTUL/A | ML/CEO | JDI
Identify any problem managers—defined here as not willing to commit.
Create action plan within 30 days for rehabilitation or removal.
Coordinate removal with VP HR.
Risk: Left unmanaged, this problem will sandbag organization renewal.
INITIATIVE LD.5: STANDARDIZE MANAGEMENT PRACTICES
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.5.1 | REVIEW ADMINISTRATIVE & DEPARTMENTAL POLICIES |  |  |  | S2/A | ML | DIG
This assignment does not include people policies—a separate task.
Remove/revise any policy that doesn't fit letter or spirit of values.
Remove/revise policies judged as "dumb" by management users.
Shorten/condense policy manual by 50%.
Increase managerial flexibility of application in line with values.
LD.5.2 | IMPLEMENT THE MANAGEMENT SYSTEM (MANSYS) |  |  |  | S2/A | ML | DIG
Gain consensus of MANSYS tools or changes to be made.
Establish time frames for use of management forms; i.e. monthly, quarterly.
Have in-house trainers trained in MANSYS as a resource.
Conduct in house training sessions for all members of supervision.
Monitor compliance of key sections introduced in TUL training sessions.
Planned performance (MBO): Control what gets done. (MS-02 form)
Work gating: Set priorities & kill useless/minimal value work.
Time: Meeting management and KRA hour.
Conflict management system: Control, resolve, eliminate.
LD.5.3 | ADD REVISIONS/NEW ELEMENTS TO EVOLVING MANAGEMENT SYSTEM |  |  |  | S1-5/A | ML | DIG
Add revisions or new elements introduced in course into MANSYS manual.
Values statement created by group.
Group specified leadership behaviors in terms of what's in/out.
President's specification of what he/she wants to see in proposals.
Communicate & train people as needed.
Integrate MANSYS quarterly plans to organization strategic plan.
INITIATIVE LD.6: REVITALIZE MEETINGS MANAGEMENT
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.6.1 | INSTALL MEETING MANAGEMENT PROCEDURES |  |  |  | S2/A | ML | DIG
Enforce proper meeting disciplines as a symbol of organization change.
Build in a sunset provision. All groups must justify existence each year.
Unless getting results, schedule JCAHO required meetings for short time frames.
Evaluate all meetings on 1-10 scale for effectiveness: restructure as needed.
Rehab/remove poor meeting leaders.
Instill the philosophy that we must be ruthless with time.
LD.6.2 | RESTRUCTURE DEPARTMENT HEAD MEETING TO AID THE REVOLUTION |  |  |  | S1/A | CEO/ | JDI
|  | Turn it into a problem-solving arena and debate forum. |  |  |  | ML
Break meeting into small groups where elements can be worked on.
All one way announcements published prior to meeting in SuperMemo.
LD.6.3 | EVALUATE ALL MEETINGS, THEN GET THEM ON PRODUCTIVE TRACK |  |  |  | S2/B | ML | DIG
Do a housewide estimate of meetings frequency, cost, effectiveness.
Target meetings to be discontinued, streamlined, shortened.
Set up procedure so that all meetings are evaluated each time.
Executive review required if meetings pulling less than 8 on 10 scale.
LD.6.4 | IDENTIFY WHAT NEW MEETINGS/COUNCILS ARE NEEDED |  |  |  | S3/B | ML | DIG
Consider a Supervisory Council as a way to power up first line people.
Institute “Whosoever will” attendance as a way to break down barriers.
INITIATIVE LD.7: INCREASE COMMUNICATION DYNAMICS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LD.7.1 | SET UP DEPARTMENTAL COMMUNICATION CENTERS |  |  |  | S1/A | ML | JDI
Understand concept, then contact managers to determine sizes needed.
Order necessary equipment & get installed.
Review suggested content & placement of items in MANSYS Manual.
Begin posting elements called for to help change process.
LD.7.2 | BLUR CHAIN OF COMMAND TO ENCOURAGE BOUNDARY CROSSING |  |  |  | S1/A | ML | JDI
Don't issue updates of organization chart, cease emphasizing it.
Encourage people to begin free form interaction across the organization.
Install the First Amendment. People may talk to others without approval.
State "chain of communication does not follow chain of command".
Look for behaviors that suppress communication or overcontrol.
LD.7.3 | REISSUE PHONE BOOK AS "ORGANIZATION CHART" |  |  |  | S3/A | ML/CAC | JDI
Purpose: Assist direct access to people across organizational lines.
Focus is more on organization of work than organization of people.
Include all Associate names in alpha section.
Include department names & topic index in yellow pages.
Set on computer to allow periodic updates.
LD.7.4 | BOOST PC USAGE |  |  |  | BTUL/A | IS DIR | DIG
Evaluate need for PCs for productivity & communication improvement;
improvement in patient info and physician satisfaction; reduce paper flow.
streamline work processes for speed.
MODULE BP: GROWING THE BEST PEOPLE STRATEGY
KRA Focus: People Growth & ORGANIZATION CLIMATE
Module Leader:
INITIATIVE BP.1: CHANGES ADDRESSED AT UNCOMMON LEADER SESSION
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.1.1 | CHANGES ADDRESSED AT THE UNCOMMON LEADER PROGRAM |  |  |  | S2/A | MHI
Iidentify the assignments and work to be done in the organization as they
become apparent in this TUL Session.
INITIATIVE BP.2: EXECUTIVE RESPONSIBILITIES FOR PEOPLE MANAGEMENT
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.2.1 | REDUCE BARRIERS & STATUS DIFFERENTIALS |  |  | A | S1/A | ML | DIG/JDI
Identify status barriers & differentials.
Managers choose 2 barriers/month for 3 months to bust.
Require report from mgrs. of the barriers they are personally busting each
month.
BP.2.2 | EXECUTIVES AWARD ASSOCIATES FOR LIVING VALUES |  |  | A | S1/A | Vision | DIG
Choose a symbol to be the award.
Publicize the story behind the symbol.
Give the award as frequently as possible.
Make "an event" out of giving the award; publicize it & the recipient.
BP.2.3 | RECONSTITUTE MANAGEMENT COUNCILS TO INCLUDE ASSOCIATES |  |  | A | S3/C | ML | DIG
Challenge the need for each management council's existence.
Include 1+ Associates on each management council.
Associate represents personal opinion, not entire Associate population.
BP.2.4 | HOLD ON ASSOCIATE LAYOFFS: FIND MORE CREATIVE SOLUTIONS |  |  | A | BTUL/A | ML/CEO | JDI/DIG
Stand by people if you want them to stand by you.
Do not destroy the morale of the army that will lead you to glory.
Use HR tactics short of a layoff to reduce head count. Follow the rules:
No layoffs, preserve the human environment.
Get rid of problem people, keep good people.
Enlist Associate cooperation in cost/revenue management.
Handle by attrition, retirement, re-training.
Get creative, find ways to increase revenue & decrease costs.
BP.2.5 | SUPPORT THE HR STRUCTURE & STAFFING LEVELS |  |  | B | S4/B | ML/CEO | DIG
Change program has been underway. Is HR executive a good fit?
Are HR programs comprehensive, up to snuff, effective?
Industry standards for staffing are 1 HR /150 Associates.
BP.2.6 | CREATE A POWERFUL CHANGE UNIT OUT OF EDUCATION |  |  | A | S3/A | CEO | DIG
Devise a strategy that will turn education into powerful change driver.
Goal is empowerment & knowledge at lowest possible levels.
Centralize all training functions & expenditures.
Increase training budget: 1% of operating budget or double current budget.
Set standard of hours of training/Associate: 2 hours/week to start.
Focus training effort on Customer service needs & technical skills.
Upgrade & expand training offerings.
Create a Center For Learning Excellence.
BP.2.7 | EVALUATE MANAGERS |  |  |  | S3/A | CEO | JDI
|  | Evaluate the work, effort, commitment and results of managers in TUL. |  |  |  | VPS
If there are changes to be made, now is the time.
INITIATIVE BP.3: R.E.S.P.E.C.T.
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.3.1 | CHANGE TO ASSOCIATE, PARTNER OR OTHER TITLE OF RESPECT |  |  |  | S1/A | MAC | DIG
Forsake use of "employee", "lower level", "subordinate", "FTE", for hourly staff.
Capitalize Associate in all publications & policy manuals.
Explain why change is made.
BP.3.2 | BOOST ASSOCIATE PRIDE THROUGH APPEARANCE UPGRADING |  |  |  | S3/B | ML | DIG
Upgrade Associate dress code, personal hygiene standards.
Upgrade Associate break areas for cleanliness.
Set new standards for neatness in Associate work areas.
BP.3.3 | CREATE VALUE-CENTERED GUIDE FOR ASSOCIATES |  |  |  | S1/A | CEO | DIG
Associates need to know what behaviors are expected of them.
The Value-centered guide is a clear and handy reference to keep Assoc.
behavior on track.
BP.3.4 | STOP TIME CLOCKS—GO TO TIME CARD TRUST |  |  |  | S2/A | ML | DIG
Use elevation of people as a symbol of change.
Design automated system.
Reduce time to paycheck delivery.
Make an event out of time clock destruction—start a museum?
INITIATIVE BP.4: REVISE PEOPLE POLICIES
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.4.1 | SIMPLIFY PEOPLE POLICIES TO REFLECT VALUES & GET RESULTS |  |  | A | S2/A | ML | DIG
Streamline policies, reduce the number of policies by 25%.
Make "user friendly" & manager supportive.
BP.4.2 | REMOVE NEGATIVE LANGUAGE & TITLES FROM JOB DESCRIPTIONS |  |  |  | S3/A | ML | DIG
Decide whether to combine this task with 2.4.3—remove negatives quickly.
Put all on computer–jobs will stay in flux in NAH.
|  | Change employee titles to increase respect: Eliminate horrible titles ASAP. |  | A
Retool jobs for dignity: end "lower level" subordinate talk.
Stop assumptions about limits on people: knock down job limits.
Eliminate constricting guidelines & artificially limiting job responsibilities.
BP.4.3 | REVISE JOB DESCRIPTIONS TO FREE & FOCUS PEOPLE |  |  | B | S5/B | ML | DIG
Decide whether to combine this task with 2.4.2.
Rewrite job descriptions; simplify–one page long.
Expand job titles and responsibilities; write fewer, broader jobs.
Include value-centered behaviors as requirement for all jobs.
Include KRA focus for all managerial jobs & wherever else possible.
Tie Customer service requests to job & system changes.
Move lists of detailed job tasks & standards of performance to each department.
BP.4.4 | PRESENTATION "UNDERSTANDING DISCIPLINARY PROCEDURES" |  |  |  | S2/A | Dir. HR | JDI
Dir. HR presents current disciplinary policy to group.
Suggestions are made for policy improvement.
INITIATIVE BP.5: ASSOCIATE TRAINING PLAN
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.5.1 | PLAN FOR ASSOCIATE & MANAGEMENT TRAINING PROGRAMS |  |  | A | BTUL/A | Dir. Ed. | JDI
|  | Identify topics, trainers, locations & timeframes. |  |  |  | TAC Ch.
|  | Get support of executives & managers to release Associates for training. |  |  |  | ML
Identify multiple mediums & resources for delivery of training.
Train the trainers to conduct identified modules of instruction.
Set up master calendar & publicize.
BP.5.2 | NEW AMERICAN HOSPITAL TRAINING MODULE |  |  | A | S1/A | Dir. Ed. | JDI
|  | Audience: All Associates. |  |  |  | TAC Ch.
|  | Content: Values orientation & NAH concepts, any rewards for knowledge. |  |  |  | ML
BP.5.3 | DIG & DO-IT TRAINING MODULE |  |  | A | BTUL | Dir. Ed. | JDI
|  | Audience: All Associates. |  |  |  | TAC Ch.
ML
BP.5.4 | DIG CHAIR TRAINING MODULE |  |  | A | S2/A | Dir. Ed. | JDI
|  | Audience: All managers & selected Associates. |  |  |  | TAC Ch.
ML
BP.5.5 | INTERVIEW TRAINING MODULE |  |  | A | S2/B | Dir. Ed. | JDI
|  | Audience: All managers & selected Associates. |  |  |  | TAC Ch.
ML
BP.5.6 | BASIC CONTINUOUS IMPROVEMENT METHODS TRAINING MODULE |  |  | A | S5/A | Dir. Ed. | JDI
|  | Audience: All Associates interested in the topic. |  |  |  | TAC Ch.
ML
BP.5.7 | ADVANCED CONTINUOUS IMPROVEMENT METHODS TRAINING MODE |  |  |  | S5/A | Dir. Ed. | JDI
|  | Audience: Select managers & Associates. |  |  |  | TAC Ch.
ML
INITIATIVE BP.6: REWARD, RECOGNITION & REINFORCEMENT
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.6.1 | DESIGN & DELIVER ASSOCIATE REWARDS FOR KNOWING THE VALUES |  |  | A | S1/A | RAC | DIG
|  | Choose award and methods of stating the values. |  |  |  | Chair
|  |  | Example= Value wagon; coffee wagon with mugs pushed by CEO. |  |  | ML
Involve CEO or VP in awarding.
Concentrate the effort in short time period; 2-3 days.
Build into new Associate orientation.
Increase socialization–make it fun!
BP.6.2 | DESIGN & DELIVER ASSOCIATE REWARDS FOR LIVING THE VALUES |  |  | A | S1/A | RAC | DIG
|  | Create awards for values to create heroes that teach. |  |  |  | Chair
|  | Following organization awards, go to departmental programs. |  |  |  | ML
Include rewards as standard element in all proposals.
Rotate/refresh the reward system quarterly.
Add host of non financial rewards; $ for results only.
BP.6.3 | DESIGN & DELIVER REWARDS FOR DEPT/DIVISION KRA ACHIEVEMENTS |  |  | A | S2/A | RAC | DIG
|  | Create awards for KRA accomplishment. |  |  |  | Chair
|  | Tie rewards to work objectives. |  |  |  | ML
Increase socialization & celebration–make it fun/zany.
BP.6.4 | INTEGRATE 3RS INTO PERFORMANCE EVALUATIONS FOR SUPERVISORS |  |  | A | S2/B | MAC | DIG
|  | Good performance includes actively giving recognition. |  |  |  | RAC Ch.
ML
BP.6.5 | KILL OFF DEAD OR OUTLIVED RECOGNITION PROGRAMS |  |  |  | S2/B | RAC | DIG
|  | Audit participation & impression of current programs. |  |  |  | Chair
|  | Revitalize ones with potential. |  |  |  | ML
Discard inactive ones.
Create new, exciting ones; rotate them.
BP.6.6 | DESIGN & DELIVER REWARDS FOR DIG PARTICIPATION & OUTSTANDING |  |  |  | S1/A | RAC | DIG
|  | DIG PERFORMANCE |  |  |  | Chair
|  | Establish minimum participation level 3-5+ DIGs for special recognition. |  |  |  | ML
Determine who will evaluate outstanding DIG performance.
Set criteria to judge outstanding DIG performance.
Determine pyramiding reward system.
Communicate program to all Associates.
INITIATIVE BP.7: INTEGRATING VALUES, ORGANIZATION & WORK PERFORMANCE
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.7.1 | DESIGN & IMPLEMENT PEER & CUSTOMER EVALUATIONS FOR |  |  | A | S4/B | ML | DIG
ASSOCIATES & DEPARTMENTS
Include self-evaluation.
Ratings feed into department and individual performance evaluations.
Ratings impact compensation.
BP.7.2 | REVISE EXECUTIVE & MANAGERIAL PERFORMANCE EVALUATION FORM |  |  | A | S2/A | ML | DIG
Add values section–appears before job performance factors.
Add section on leadership and championing NAH culture.
Add section on achievement on KRA work objectives.
Add section on manager's use of 3-Rs with staff.
Incorporate peer & Customer evaluations wherever possible.
Self evaluation + supervisory performance evaluation.
BP.7.3 | REVISE PERFORMANCE EVALUATION FORM FOR NON MANAGERIAL JOBS |  |  | A | S4/A | MAC | DIG
|  | Add values section–appears before job performance factors. |  |  |  | DIR. HR
|  | Add section on Associate's use of 3-Rs with staff. |  |  |  | ML
Incorporate peer & Customer evaluations wherever possible.
Self evaluation + supervisory performance evaluation.
BP.7.4 | IMPLEMENT EARLY COMPENSATION PROGRAM CHANGES |  |  |  | S5/A | ML | DIG
Kill off COLAs, step increases, payments for non performance.
Slow down Associate pay evaluation/promotion---stay competitive.
INITIATIVE BP.8: SELECTION, PROMOTION, RETENTION
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.8.1 | BEGIN MULTIPLE INTERVIEW PROCESS FOR APPLICANTS & TRANSFERS |  |  | A | S2/A | ML | DIG
Install a selection system worthy of the name, target responsibilities.
Tighten up on selection: Pick winners, stop hiring warm bodies.
Use managers & Associates to interview.
BP.8.2 | DEVELOP EXTENDED PROBATION PROGRAM |  |  | B | S3/B | ML | DIG
Associate works on unit before final hiring.
Test skill level before committing.
BP.8.3 | POWER UP PROMOTION POLICY FOR INTERNAL CANDIDATES |  |  | A | S3/A | ML | DIG
Write policy requiring promote from within to get at non development.
Promote from within–selection & development impacts.
Use opportunities to develop managers, require more development.
Try people out without making permanent commitment.
BP.8.4 | DEVELOP ASSOCIATE RETENTION PROGRAMS—EXIT INTERVIEW |  |  | B | S3/B | ML | DIG
Reduce turnover as a major goal by fixing organization deficiencies.
Install exit interview program to identify issues.
Assess turnover reasons to increase retention: Stop the outflow.
INITIATIVE BP.9: PEOPLE COMPLAINT RESOLUTION & MANAGEMENT
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
BP.9.1 | CONDUCT ASSOCIATE ATTITUDE RESEARCH & ACT ON FINDINGS |  |  | A | BTUL/A | MAC | DIG
|  | Should outside consultant be used due to in house problems/sensitivities? |  |  |  | Dir. HR
|  | Identify Associate problems & irritations & remove them. |  |  |  | ML
Train supervisors to understand research results.
Train supervisors in how to make changes.
Conduct feedback sessions with Associates.
Make changes in each department.
BP.9.2 | STREAMLINE POLICY FOR PROBLEM EMPLOYEE REMOVAL |  |  | A | S2/A | MAC | DIG
|  | Make policy "user friendly"; send clear message of manager support. |  |  |  | Dir. HR
|  | Publish policy to all Associates so that it is enforceable. |  |  |  | ML
Train management: TUL Session 2 lays out philosophy.
Train management: Provide in-service on discipline procedures.
BP.9.3 | INSTALL "WRITE TO THE TOP" PROGRAM |  |  | B | S3/B | CAC | JDI
|  | Written, confidential communication from Associate to CEO. |  |  |  | ML
Publish in newsletter if Associate gives permission.
BP.9.4 | INSTALL "LUNCH WITH THE BOSS" PROGRAM |  |  |  | S4/C | CAC | JDI
|  | No VPs attending, direct personal communication with CEO. |  |  |  | ML
CEO follows up on problems/issues.
All responses come from CEO, not an assignee.
BP.9.5 | INSTALL ASSOCIATE HOTLINE |  |  |  | S2/A | MAC | DIG
|  | For Associate comments/problems with rapid turnaround time response . |  |  |  | ML
Phone line available 24 hours a day, 7 days a week.
Assign telephone code such as "TEAM".
BP.9.6 | RAPID TURNAROUND TIMES FOR RESOLUTION OF ASSOCIATE PROBLEMS |  |  | A | S2/A | ML | DIG
|  | Publish protocol in HR policy manual & get into Associate awareness. |  |  |  | Dir. HR
|  | Establish rapid turnaround times for conflict management. |  |  |  | ML
Associate inquiries/calls responded to in 1 business day.
Get answer within 3 business days if don't have it & give feedback.
Build an Associate appeal process.
Assess: Is the organization surfacing problems rather than ignoring them?
MODULE CS: TOTAL CUSTOMER SATISFACTION STRATEGY
KRA Focus: Customer Satisfaction & Economics
Module Leader:
INITIATIVE CS.1: CHANGES ADDRESSED AT UNCOMMON LEADER SESSION
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.1.1 | CONDUCT TUL SESSION: "CUSTOMERS: THE REASON FOR BEING" |  |  |  | S3/A | MHI
Day 1: "The Customer is King"
Day 2: "Accountability in Management"
CS.1.2 | CHANGE ELEMENTS INTRODUCED BY PRESENTER AT TUL SESSION |  |  |  | S3/A | MHI
Introduce the Customer Strategy.
Formation of Customer Super DIGs.
Each department to run at least one focus group.
Introduce CEO presentation: "Manager's Guide to Success."
Cost Containment Audit assigned as source of Customer service funds.
CS.1.3 | PROVIDE TUL SESSION SUPPORT |  |  |  | S3/A | MAC | JDI
CS.1.4 | PROCESS INCOMING MANAGER SUGGESTIONS FROM TUL SESSION |  |  |  | S3/A | MAC | JDI
Use overhead lists created at session—extend by brainstorming.
Sort rapidly & assign to DIGs, Just Do Its. Where possible, direct work to JDIs
to speed time lines.
Keep balance between Module Action Plan items & manager suggestions.
Must build the management machine, not just react to manager targets.
Get set up with computer to plan, track & retrieve data.
INITIATIVE CS.2: CUSTOMER COMMUNICATION FOR RESULTS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.2.1 | SOLVE CUSTOMER FACILITY NAVIGATION PROBLEMS |  |  |  | S3/A | ML | DIG/JDI
Focus is to help patient/visitor get around facility on their own.
|  | Add/improve hospital maps, signage to solve the "I'm lost!" problem. |  | A
Train volunteers & staff in how to reference.
Add/improve fire safety & exit instructions.
|  | Add service directory instructions. |  | A
|  | Add telephone quick response instructions. |  | A
Explore providing patient and visitor in-servicing via TV or print.
CS.2.2 | RESOLVE & MANAGE COMPLAINTS |  |  |  | S3/A | ML | DIG
|  | Establish a Customer hot line. |  | A
|  | Use a card system (3C) to gather complaints, compliments, and suggestions. |  | A
CS.2.3 | CUSTOMER-FOR-A-DAY |  |  |  | S3/A | ML | DIG
Assign Associate to experience all facets of being a Customer for an
entire day; Make suggestions or take immediate action on improvements
to Customer Satisfaction.
CS.2.4 | MANAGER'S GUIDE TO SUCCESS |  |  |  | S3/A | CEO | JDI
To be presented at TUL Session III By CEO. It should be a detailed
concise listing of behaviors & expectations of behavior from the CEO to all
supervisors & managers. Deliver to the group using an overhead projector
& handout copies to the audience. Incorporate into future mgr. handbook.
INITIATIVE CS.3: IDENTIFYING & TARGETING CUSTOMERS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.3.1 | IDENTIFY WHO THE CUSTOMER IS |  |  |  | S3/A | ML | DIG/JDI
Identify who the Customer groups/individuals are for each operating area and
post this information on the department communication board.
Discuss with unit Associates how they can best serve the different
constituencies of Customers. Fact find where there are problems in
Customers service, and correct them.
CS.3.2 | MANAGE PHYSICIAN ACCOUNTS |  |  |  | S3/A | ML | DIG
|  | Assign responsibility for each physician to a member of staff. Only one |  | A
person from the entire organization should be assigned to each physician.
Centralize the effort to avoid physician irratation and develop relationships.
CS.3.3 | CONDUCT CONTRACT REVIEWS & POSITIONING |  |  |  | S3/A | ML | DIG
Identify all current customer contracts, i.e. managed care, insurers, employers,
etc. Assign a liaison to each contract to meet with customer & review
service levels, additional needs, required changes, etc. Correct weak
situations now, and add value where indicated by the Customer. Protect
current contracts & build relationships for additional renewals & referrals.
CS.3.4 | TARGET NEW EMPLOYER, COALITION, & MANAGED CARE CUSTOMERS |  |  |  | S3/A | ML | DIG
Identify potential new patient contract sources. Assign liaison to develop
relationships with them. Look for weaknesses in current customer relation-
ships & build your program to defeat competitors weaknesses plus add
more value.
CS.3.5 | BUILD PHYSICIAN CUSTOMER BASE |  |  |  | S2/A | ML | DIG
Identify where future reimbursement & healthcare needs will be. Review
physician customer base in these areas. Target new practices & physicians
to build your business in these mushrooming areas.
INITIATIVE CS.4: MAKING SERVICE WORK—REMOVING IRRITATIONS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.4.1 | REMOVE CUSTOMER IRRITATIONS |  |  |  | S3/A | ML | DIG
|  | Remove complaints from the system, don't just smooth feathers. |  | A
Practice "naive listening" to see the organization anew.
Use "Customer Dimensions of Quality" to target needed service improvements.
|  | Readjust operating standards which are often set too low. |  | A
CS.4.2 | CREATE A HEALING ENVIRONMENT |  |  |  | S3/A | ML | DIG
Identify ways to de-institutionalize the facility & build a warmer, more
comfortable healing environment. Add softness to patient rooms & waiting
areas, add self-managing aspects to patient areas, more relaxing components
& alternatives, i.e. soft nature sounds in audio or form, more patient
education materials on each unit for patients & family to access, etc.
INITIATIVE CS.5: MAKING SERVICE WORK—ADDING VALUE
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.5.1 | ADD VALUE TO EXISTING SERVICES |  |  |  | S3/B | ML | DIG
|  | Use moments of truth concept to improve the system. |  | A
Practice "naive listening" to see the organization anew.
Increase value to Customer. What makes your service or product or
experience better than, or different from others who offer the same product
service, product or experience?
CS.5.2 | ADD NEW VALUE ADDED SERVICES |  |  |  | S3/B | ML | JDI
|  | Each manager is to identify growth segments & opportunities within their |  | A
area of expertise or tangential area of expertise. Target serviceable
Customer segments—forget dead pockets. Monitor "service enhancements,"
"is this working?" Does it make a difference to Customers, or is it just
something that has been added and has no real value to the Customer?
CS.5.3 | TOTAL CUSTOMER SATISFACTION GUARANTEE |  |  |  | S3/A | ML | DIG
Identify 4 -5 areas/services where you can guarantee Customer
Satisfaction or the service is free, or a penalty to paid to the Customer
if the guarantee is not met. Examples of guarantees include:
meals, timeliness of admitting or other service, housekeeping
standards, etc.
INITIATIVE CS.6: MEETING & EXCEEDING CUSTOMER EXPECTATIONS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.6.1 | SET HOUSE-WIDE STANDARDS OF PERFORMANCE—SOPs |  |  |  | S3/A | ML | DIG/JDI
Copy successful Customer service practices in benchmark companies.
|  | Use moments of truth concept to improve the system. Set standards in |  | A
each of the following areas as a start:
|  | Personal appearance , telephone response time, telephone waiting time, |  | A
|  | and telephone manners, Customer waiting times, call light response times, |  | A
|  | problem-solving response time, desired customer satisfaction index, etc. |  | A
Set 95% minimum performance standard for each within each department.
CS.6.2 | GRAPH CUSTOMER SATISFACTION RATINGS |  |  |  | S3/A | ML | JDI
Present at TUL S3: graphed results of customer satisfaction ratings for the
past 12 months. Inpatient vs outpatient, and a combination of both.
Indicate the percentile ranking for your organization as "Excellent," and the
percentile ranking for your organization as "Above Average." List
the six worst rated departments in Customer Service. List all depts. where an
average response to any one question on the Customer satisfaction survey is
"average" or less.
CS.6.3 | PERSONAL COMMUNICATION TRAINING |  |  |  | S3/A | ML | DIG
Prepare & deliver training to all Associates on how to address patients &
one another. Discard negative messaging, gossip, and slang, sloppy
conversation. Replace it with scripted ways to address patients & one
another; a positive, grammatically correct address, and set standards of
performance to address a friendly, positively oriented environment.
INITIATIVE CS.7: LINKING HUMAN PERFORMANCE TO CUSTOMER NEED
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.7.1 | REWARD PERFORMERS: AGGRESSIVELY MANAGE SERVICE BEHAVIORS |  |  |  | S3/A | ML | DIG
Tie Customer ratings to manager/Associate evaluations.
Create, recognize & reward Heroes of Customer Service.
Group rewards for achievement of special service targets/improvements.
CS.7.2 | ORGANIZE & DEPLOY ASSOCIATES TO SERVE CUSTOMERS |  |  |  | S3/B | ML | DIG
Consider following & setting up separate DIGs for each project chosen.
|  | Set up the Adopt-a-Patient Program. |  | A
Set up Customer Satisfaction Teams. Empower Associates with #1 KRA
of Customer Satisfaction. Rotate support staff into direct Customer contact
|  | assignments. Do Customer relations training, if needed. |  | A
Caution: Guest relations behaviors mirror Associate relations. Are
|  | Associate relations good? If not, start with Associate relations training, |  | A
then move to Customer relations training.
CS.7.3 | LINK CUSTOMER SATISFACTION TO ORGANIZATION BONUS |  |  |  | S3/A | ML | DIG
Create bonus program for all Associates based on achievement of org.
BHAG in Customer satisfaction.
INITIATIVE CS.8: LET THE CUSTOMER TEACH YOU THE BUSINESS
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.8.1 | MEASURE: HOW ARE WE DOING? |  |  |  | S4/A | ML | DIG
|  | Install evaluations of departments by in-house customers. |  | A
|  | Implement systematic Customer satisfaction surveys. |  | A
|  | Post visual measures, compliments & complaints to drive change. |  | A
As an organization, monitor service enhancements that are put in place
to assess if the changes are effective and if they should be implemented
on an even wider range of departments.
CS.8.2 | MAXIMIZE CUSTOMER INPUT AND IMPACT |  |  |  | S3/B | ML | DIG
Set up multiple avenues for Customer input. Institute routine focus groups,
|  | feedback, and measures. Incorporate Customer feedback into |  | A
improvement loops. Test: Does the organization provide what the Customer
wants? If not, change it! Let the Customer teach you the business, then
change the business. Involve Customers in the problem-solving.
Provide customer-involved mechanisms for problem-solving process.
CS.8.3 | INITIATE CUSTOMER SATISFACTION SWAT TEAMS |  |  |  | S3/A | ML | DIG
SWAT teams are sets of customer satisfaction experts within your organization
assigned to assist managers who are not able to achieve satisfaction goals.
CS.8.4 | INITIATE HI/LOW CUSTOMER SATISFACTION MEETINGS |  |  |  | S3/A | ML | JDI
|  | Install scheduled meetings with an agenda for review of satisfaction ratings |  |  |  | CEO
by department and at-the-moment action plans for correcting less than
excellent performances
INITIATIVE CS.9: COORDINATE CUSTOMER SERVICE STRATEGY
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS.9.1 | DESIGN A CUSTOMER STRATEGY & PUBLISH A TACTICAL PLAN |  |  |  | S3/A | ML | DIG
|  | Audit the People Strategy. Completion of the People Strategy |  | A
is a precondition for beginning the Customer Satisfaction Strategy.
|  | Module Leader to establish the overall Customer Strategy. Start |  | A
by creating group assignments for each of the headings in this ask. All
TUL participants to be involved in an assignment. Each heading is to
be fully developed. Accountability for a Total Customer Service Strategy
is with the executive group, not the marketing department or any other single
department. Coordination of wide-scale changes to be monitored with
periodic review. Publish a Total Customer Tactical Plan with work assigned
to each quarter, including responsible person and deadline for completion.
CS.9.2 | RESOURCING TO SERVE CUSTOMER, REINFORCE SERVICE BEHAVIORS |  |  |  | S2/A | ML | JDI
|  | Do not allow Customer innovation to be slowed for want of resourcing. |  | A |  | CFO
|  | Are funds available? Has accounting system allowed for innovation tracking? |  | A
|  | Consider profit sharing of new revenue or expenses saved to fund ideas. |  | A
CS.9.3 | WIDER MARKETING CONSIDERATIONS |  |  |  | S4/A | ML | DIG
Conduct the following executive discussion: Does the organization meet what
the Customer wants? Target serviceable Customer groups and feasible
programs. Evaluate departments on Service, Quality and Price.
Discontinue dogging services and outlived services. Do hard pruning.
Identify market niches: Stake out competitively defensible positions.
INITIATIVE CS.10: CONDUCT MID COURSE ASSESSMENT
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
CS10.1 | CONDUCT MID COURSE ASSESSMENT |  |  |  | S3/A | CEO | JDI
|  | Convene Executive Vision Council and Module Leaders. Review |  |  |  | MAC
MidCourse Assessment Agenda provided by MHI plus added client items.
Identify weak implementation points & plan aggressively for adjustments.
Remember, the more implementation points that the client deletes or
weakly implements, the weaker the program results will be. Make
adjustments in leadership & managerial implementation, if needed.
MODULE LC: LOW COST STRATEGY
KRA Focus: ECONOMICS & PORDUCTIVITY
Module Leader:
INITIATIVE LC.1: CHANGES ADDRESSED AT UNCOMMON LEADER SESSION
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LC.1.1 | CONDUCT TUL SESSION: "RISKING FOR GREATNESS" |  |  |  | S4/A | MHI | JDI
Day 1: "Managerial Muscle, Power & Persuasion"
Day 2: "Creativity, Conflict, & the Chaos of Change"
LC.1.2 | CHANGE ELEMENTS INTRODUCED BY PRESENTER AT TUL SESSION |  |  |  | S4/A | MHI | JDI
Introduce "What I like to see in a proposal," conducted by the CEO.
Introduce conflict management protocol.
Assignment to "Bury the Hatchet" & enforcement of conflict mgt. by executives.
Staff swaps required to address any interdepartmental conflict.
LC.1.3 | PROCESS INCOMING MANAGER SUGGESTIONS FROM TUL SESSION |  |  |  | S4/A | MAC | JDI
|  | Capture all ideas/suggestions generated at TUL sessions and move |  |  |  | Chair
into a DIG or JDI form for action.
LC.1.4 | WHAT I WANT TO SEE IN A PROPOSAL, BY THE CEO |  |  |  | S4/A | CEO | JDI
Prepare & deliver a five minute presentation on "What I Want To See In A
Proposal." This format will be used thereafter for all proposal submissions.
Set up standard proposal formats and teach managers how to sell their ideas.
Review MANSYS guide as a starting point, feel free to edit or toss items.
Add new items to MANSYS to customize for your organization. MANSYS
is to become the core of a management orientation program for new managers.
The goal is more proposals accepted & less rework of submitted ideas.
LC.1.5 | DEVELOP LOW COST TACTICAL PLAN |  |  |  | S4/A | ML | JDI
Review all Tasks in Low Cost Strategy, indicate those requiring more work.
Gather add'l low cost ideas from Associates/mgrs. and add to the list.
Format the list into a schedule of work to be done. Include who is res-
ponsible for each Task and when it is to be completed. Work aggressively
on a timetable. Allow a process to add new low cost tactical ideas as they
are generated. This is an eternal process of collecting ideas and then
implementing them. You should have at least 300 new low cost ideas
added to the tactical plan before the conclusion of TUL classroom sessions.
LC.1.6 | CONDUCT PEOPLE CLIMATE AUDIT IN PREP FOR CI PROCESSES |  |  |  | S5/A | MAC | DIG
Numerous previous Tasks must be completed before the org. is ready to go
forward with CI training in an effective manner. Answer the questions on the
Climate Audit and proceed to resolve uncompleted work/problems to prepare
the org. for the CI training.
LC.1.7 | IMPLEMENT STAFF SWAPPING |  |  |  | S4/A | ML | DIG
This Task is involved with making the decisions/guidelines for how and when
staff swapping will occur within each department, as well as the follow up
to assure that the assignment has occurred and will continue to occur
indefinitely for the future, and a tracking of the results of the swapping effort.
INITIATIVE LC.2: LOW COST INITIATIVES FOR PEOPLE PRODUCTIVITY
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
LC.2.1 | DEVELOP PEOPLE PRODUCTIVITY |  |  |  | S5/A | ML | DIG
Identify work groups within a system, or mini systems of people. Empower
groups to make changes in their work to improve quality/productivity.
Set up group responsibilities instead of individual tasks. Get work group
thinking: how to handle work & supervise themselves. Begin discussions
and movement toward semi autonomous work groups. Reward for the
greatest gains in productivity.
LC.2.2 | ADD TOOLS ARE PRIMARY STRATEGY TO MAKE PEOPLE TIME |  |  |  | S5/A | ML | DIG
PRODUCTIVE
Review the current budget for Associate tools and find ways to enlarge it.
Work with dept. managers to identify what tools are needed for each Associate
in order to increase productivity. Look at low cost tools first. Go for quality
tools not cheap price. Develop a process for prioritizing the purchase of tool
requests and coordinate with strategic plan.
LC.2.3 | REVIEW OF DECISION TIMES |  |  |  | S3/A | ML | DIG
Identify where there are unacceptable delays/timeframes for decision-making.
This is within managerial and executive ranks. Reduce decision-making times
by 50%.
[5 empty] | S4/A | ML | DIG
LC.2.4 | POWER-UP DOWN TIMES
Identify periods of time when low productivity levels are consistently found
within each department. Proceed to consolidate the work that is occurring
during light productivity times into a condensed time period thus freeing up
blocks of time when add'l or new work assignments can be given to Associates.
The goal is 100% productivity for all positions at all times.
LC.2.5 | DEVELOP LITE-DUTY RETURN TO WORK PROGRAM |  |  |  | S2/A | ML | DIG
Associates injured on the job or outside of the organization are often
precluded from returning to work at their usual job for long periods of time. In
order for the organization to realize productivity for the lost time money paid to
injured workers, develop a lite-duty work program that assigns Associates
to work chores that they are capable of until such time that they are ready to
return to their usual, full work assignments.
LC.2.6 | OUT-SOURCE SIDELINE OPERATIONS |  |  |  | S2/A | ML | DIG
Identify the work that is being done by Associates on payroll, but is also work
that is not clearly within the mission of the organization, or work that can be
done at a higher quality or a lower cost if out-sourced to an organization that
specializes in that type of work. Implement the out-sourcing recommendations.
LC.2.7 | EDUCATION/CONFERENCE AUDIT |  |  |  | S1/A | ML | DIG
Evaluate planned conference/seminar attendance for the coming 15 months.
Eliminate all development sessions that are non clinical in nature. Give
clinical training seminars a hard look. What alternative ways are there to
achieve the needed training? Think bigger. Turn the education function into
a revenue producing function. Work with HR to identify cross-training
needs for the coming 12 months, create and implement a plan to achieve
the needed t raining and job development with the goal of no layoffs, only
job enrichment and new assignments.
LC.2.8 | EVALUATE INFORMATION SERVICES |  |  |  | S3/A | ML | DIG
Review the current state of information services affairs. Is appropriate info
being provided at the needed times, and linked to eliminate duplicate work?
What new information needs will there be? Create a tactical plan of work to be
done, prioritize the work, and move to put the plan into action.
LC.2.9 | REVIEW THE ON-THE-JOB TRAINING PROCESS |  |  |  | S3/A | ML | DIG
Each dept. already has on-the-job training in place. The question is: is the
training that is in place adequate? Are elements of things "not to do" which
may seem obvious to others, included in the on-the-job training? Coordinate
an organization-wide on-the-job training audit, and plan for improvement. Each
department should be able to add at least five new aspects to their on-the-
job training program in order to enhance it. What are the new pieces that are
being added? Share ideas that may be applicable across multiple department
lines.
LC.2.10 | EVALUATE INFORMATION SERVICES |  |  |  | S3/A | ML | DIG
View the types & timing of patient information services provided to physicians,
nurse managers, and other care givers. Is it real time information; available
immediately to the care giver at the time the results are complete, or is it
delayed by cumbersome processes? How can this information be
more readily accessible to caregivers, and how can redundancies in
information collection be eliminated?
LC.2.10 | REVIEW REASONS FOR ASSOCIATE OVERTIME |  |  |  | S2/A | ML | DIG
Payroll overtime is an unnecessary expense that is typically driven
by other events such as physician tardiness to a case thus requiring
staff to stay overtime to service the physician; delays in getting the
scheduled patients to treatments on time, poor scheduling, etc. Look at the
identified areas in this Task as well as all other areas where any overtime
is clocked. & determine the reasons why the overtime was needed. Within each
reason is a problem to be solved and a cost to be cut. The goal
is -0- overtime expense.
LC.2.11 | EVALUATE PATIENT PREPARATION PROTOCOLS |  |  |  | S4/A | ML | DIG
To achieve maximum productivity, all patients are to arrive in each dept. fully
prepared for the events that are scheduled, i.e. forms completed, prior test
results recorded, etc. All depts. are to review their protocol for preparing
patients. Do not assume that even the simplest knowledge is known by all
Associates. Educate all Associates on the current protocols. Then, add to the
protocols actions that are needed in order to resolve problems that other depts.
are having when they receive patients from your dept. Each dept. is to take
responsibility for full patient preparation.
LC.2.12 | STANDARDIZE COMMON PATIENT CARE ADMINISTRATIVE PROCESSES |  |  |  | S4/A | ML | DIG
Identify clinical support positions which share some level of overlap of skills.
Review common skills, tools, and practices among the staff to determine
which are most efficient & effective. Standardize the tools, location,
practices and skills in order to make the staff more flexible, interchangeable
and efficient in their work.
LC.2.13 | STANDARDIZE COMMON ADMINISTRATIVE CLERICAL PROCESSES |  |  |  | S4/B | ML | DIG
Review common skills, tools, and practices among executive assistants,
administrative assistants, and other groupings of supportive/clerical
skills of various levels. Standardize tools, systems, and processes to
make staff and jobs more flexible and efficient. Leave turf issues off the agenda.
INITIATIVE LC.3: LOW COST INITIATIVES FOR FINANCIAL PROCESSES
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LC.3.1 | INSTALL NEW POLICY: ALL SERVICE CONTRACTS REQUIRE A |  |  |  | S2/A | ML | DIG
FULL RE-BIDDING PROCESS
Often service contracts are renewed without a full rebilling process
being conducted. This blocks out the possibility of competitive pricing,
competitive service, and new service options that may be offered by
competitors. Install a new policy requiring a rebidding process for all
renewals of service contracts, and increase the specifications
to new levels of service, pricing, etc.
LC.3.2 | MANAGING PRIVATE PAY CUSTOMERS |  |  |  | S2/A | ML | DIG
Review the information systems and aggressiveness of A/R processes
for private pay customers. Often, the handling of such accounts is not
as aggressive and appropriate as it should be.
LC.3.3 | MAXIMIZE CASH FLOW MANAGEMENT |  |  |  | S3/A | ML | DIG
Review cash flow from point when customer pays the bill to point when
cash is optimally received. Look for time delays in each step. Make
changes to minimize or eliminate delays of all nature to maximize cash value.
This is an extensive task that involves many aspects of the financial part of
the patient flow process.
LC.3.4 | EVALUATE ACCOUNTS PAYABLE SCHEDULE |  |  |  | S2/A | ML | DIG
Review accounts payable schedule and processes. Are discounts taken
in an aggressive manner? Work the cash flow angle for more time for
your organization and thus better cash flow and investment utilization.
LC.3.5 | MAXIMIZE SPEED OF SERVICE TO BILLING CYCLE |  |  |  | S3/A | ML. | DIG
Detail the process of service to billing to include time frames identifying each step,
and the time from the point of service delivery to the Customer to the point of
time when the billing goes out. Look for ways to reduce the timing by 50%.
Time is money.
LC.3.6 | ELIMINATE LOST CHARGES |  |  |  | S2/A | ML | DIG
Review primary service line accounting processes to determine opportunities
to loose charges. Look for small items of consumption, items of frequent
consumption, or glitches in the system that would cause charges to be
lost or unmanaged. Make modifications to the system and processes to
recapture as many lost charges as is possible, and change the systems
to make them "loss proof."
LC.3.7 | REVIEW THE TIMING OF BUDGET REPORTS |  |  |  | S3/A | ML | DIG
Budget reports that reflect the current financial status of each department's
operations need to be available to department managers immediately
following the close fo business for that month in order to make necessary
adjustments in performances. Reports that are available 3+ weeks
following the close of business are of little or no use in correcting problems
as they occur.
LC.3.8 | EVALUATE FURNITURE/EQUIPMENT IN STORAGE |  |  |  | S4/B | ML | DIG
Often the furniture and equipment from past managers, projects, etc.
are stored in a warehouse facility. Inventory the items and redeploy
those that can be used, sell the balance and move it out of the organization.
It is consuming valuable space. Redeploy the financial resources.
LC.3.9 | EVALUATION OF PAID MEDICAL DIRECTORS |  |  |  | S3/A | ML | DIG
Some organizations have a number of paid medical directors on their
payroll. Generally speaking, this is an unnecessary expense as
there are a great many qualified physicians who are willing to serve in
the role of medical director for their specialty without compensation, or
with a significantly reduced compensatory rate in exchange for the
visibility and business benefits that come with such a position. Think
about this possibility, and if you cannot move dramatically toward it in one
swoop, then move toward it in a series of aggressive moves.
LC.3.10 | REVIEW THE COST MANAGEMENT OF MARKETING NEEDS |  |  |  | S3/A | ML | DIG
Typically there is a great deal of "dumping" of marketing costs onto the
marketing department through which marketing tools are managed.
Consider moving to a marketing line item for every department budget and
charge backs to departments for all marketing services used. Publish
a cost sheet of the charges associated with the most typical types of
marketing requests, i.e. brochures, posters, etc. A charge back process
for marketing materials will dramatically help manage the marketing costs
of the organization. Create a list of questions for department managers
to use to help assess if their request for marketing material is truly
required, or just desired.
LC.3.11 | REVIEW ORGANIZATIONAL MARKETING COSTS |  |  |  | S4/A | ML | DIG
The marketing department typically uses a number of vendors to produce
posters, newsletters, brochures, etc. Relationships between the vendors
and marketing department staff tend to be tight. Often the costs passed
on by the outside marketing vendors are considerably higher than the costs
of doing the work in-house thanks to the birth of desk-top publishing and
the many resources serving that market. Review the costs charged by
outside services to the marketing department compared to the competitive
costs offered by other vendors and suppliers or an internal market.
Frequently there is a major savings in costs.
LC.3.12 | REVIEW BUDGET VARIANCE REPORTING PRACTICES—STANDARDIZE |  |  |  | S3/A | ML | DIG
The budget variance reporting practice should be standardized for all
managers in the organization to use. The timeliness for reporting should
be tight—within 5 business days from the receipt of the financial report.
LC.3.13 | EVALUATE THE POLICY/PRACTICES OF PROVIDING ASSOCIATES WITH |  |  |  | S4/B | ML | DIG
LAB COATS, KLEENEX, COFFEE, & OTHER CREATURE COMFORT
ITEMS
Improving the organizational climate does not mean providing creature
comforts to Associates. Standardize the policy and practices that relate
to providing lab coats, coffee and any other listing of unnecessary
comforts to Associates so all departments are treating all Associates
uniformly. Comforts for Customers are not necessarily comforts for
Associates.
INITIATIVE LC.4: LOW COST INITIATIVES FOR OPERATING PROCESSES
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  | Work To Do |  | Priority | Priority | Leader | Approach
LC.4.1 | IDENTIFY SERVICE LINES |  |  |  | S2/A | ML | DIG
Identify major service lines in the organization. Think through each
major category of Customer, and service lines will emerge. Identify
a project/service line manager for each. Begin thinking in service line
management terms with the service line manager as CEO of each
respective line of service from start to finish with full accountability.
Arrange to provide the necessary information, authority levels, and reporting
relationships for the CEO of the service line, or service line manager, to be
effective.
LC.4.2 | REDESIGN EXECUTIVE STRUCTURE TO REFLECT HORIZONTALLY |  |  |  | S2/A | ML | JDI
FLEXIBLE ORGANIZATION
Evaluate the current executive structure in light of movement to service line mgt.
Caution: No deadlines = no management, loss of control, & renewal stall
Broaden areas of responsibility for each executive and service line manager.
Redeploy executive talents & responsibilities to grow the business.
LC.4.3 | STANDARDIZE SUPPLIES |  |  |  | S2/A | ML | DIG
Identify supplies where various types of the same items are ordered.
Work with consumers to standardize the items, sizes, etc. Standardization
results in cost savings without reduced supplies.
LC.4.4 | REDESIGN ORGANIZATION STRUCTURE TO STREAMLINE COMMUNICATION |  |  |  | S3/A | ML | DIG
Redesign organization structure to follow service line flows. Check
out communication links between workers, services, and system support within
the service line. Look for lost information, waiting time on information,
omitted information problems. Streamline the communication process
to follow the service line flow to assure seamless delivery of service and
accuracy of information.
LC.4.5 | ELIMINATE NO/LOW VALUE-ADDED SERVICES |  |  |  | S3/A | ML | DIG
Audit all value-added services to assess what level of "value" the Customer
sees in it. Eliminate those previous "value-added" services which have
outlived their usefulness and redeploy the assets to new value-added
services which will be more appreciated by Customers.
LC.4.6 | PAPER SYSTEMS CONDENSING |  |  |  | S5/A | ML | DIG
Refine/combine/discard paper systems within your department or service line.
Each department to review all forms & paper elements used in the work systems.
Identify core vs marginal pieces. It may help to flowchart process first.
Start with management & patient care pieces, then expand the net.
Focus on high impact/volume processes. Consolidate multiple forms,
condense by removing useless information. Consider multi-part forms to
meet your needs. Automate forms for just-in-time use. Look in
human resource, finance, and information services departments for a start.
LC.4.7 | REVISIT PAY EVALUATION PRACTICES |  |  |  | S2/B | ML | DIG
Review staff and managerial performance evaluation skills. Are supervisors
skilled enough in conflict management, feedback management? Are
documentation practices in place to make performance coaching easy to do?
Update manager and supervisory skills in what the standards of performance
are, how to stretch them, how to evaluation daily performance against standards,
and to get the best from the people assets.
LC.4.8 | LOCATE AND REDUCE AREAS OF WASTE—COST CONTAINMENT AUDIT |  |  |  | S4/A | ML | DIG
Each manager and supervisor is to work through the Cost Containment Audit
and record the changes to be made. Estimate the value of each change
and submit a summary report to the MAC for ROI reporting. Follow up
on any supervisor/manager with less than 8 - 9 cost containment ideas
to be implemented.
LC.4.9 | NATURAL RESOURCES MANAGEMENT AUDIT |  |  |  | S2/A | ML | DIG
Natural energy resources consume enormous amounts of resources.
Efficient management of such resources is a speciality science where
considerable cost reductions can occur through the employment of
improved systems.
LC.4.10 | PATIENT TRANSPORTATION ANALYSIS |  |  |  | S5/A | ML | DIG
By service line, chart the type of transportation typical patients use, the amount
of transportation used in terms of the amount of time it takes to start & finish
each piece of transportation that a patient needs, & the distance each
patient travels. Determine an average amount of time & distance
traveled for each type of patient served in each service line.
Seek to reduce that amount of time & distance by 50%. Consider
scheduling difficulties, equipment shortages, delays in waiting, and
re-location of services provided.
LC.4.11 | REVIEW TOXIC WASTE MANAGEMENT PROCESS/COSTS |  |  |  | S3/A | ML | DIG
Toxic waste management is often an unnecessarily costly and overly
costly process. Benchmark top performing organizations in toxic waste
management for information and ideas on how to better manage the
costs of toxic waste. Use the additive process theory to design an even
better process for your organization. (The additive process is explained
in TUL Session V, or look it up in continuous improvement books.)
LC.4.12 | REVIEW AND REVISE CATERING REQUESTS AND GUIDELINES |  |  |  | S3/A | ML | DIG
Catering requests are a source of unexpected and unruly expenses.
Establish catering guidelines, include the type of foods that are available
for selection for specific types of events, the advanced time needed to
place the catering order, etc. and manage the use of food, for purposes
other than patient care needs. Consider charging departments directly
for the use of food. Nutrition Services people need to say "no" to
requests outside of the guidelines without being penalized/criticized for it.
LC.4.13 | REVIEW PURCHASING PROCESS |  |  |  | S3/A | ML | DIG
Review the purchasing process to assure that it is a smooth and centrally
managed process that works to the benefit of all. Centralization of
purchasing is objected to only when the process does not serve the
customer well. i.e. when it is too time consuming, deliveries are not
on time, etc. To gain control of the cost and the process, it (the process)
must serve the customer as well as the organization, or decentralization
by default will result.
LC.4.14 | REVIEW THE LIFE SPAN AND REPAIR TENDENCIES OF DURABLE |  |  |  | S4/B | ML | DIG
MEDICAL EQUIPMENT ON HAND IN THE ORGANIZATION
DME that is not durable fuels the organization with additional costs,
frustration, liabilities, lost productivity, etc. Review your repair records
for DME, i.e. wheel chairs, walkers, IV poles, etc. and assure that there
are no breakdown patterns. DME should be durable. Change vendors,
pay for quality products that are dependable and lasting.
LC.4.15 | CONDUCT COST ANALYSIS OF INTERNAL STAFF vs PURCHASED |  |  |  | S3/A | ML | DIG
SERVICES FOR ALL EXTERNAL SERVICES USED.
Frequently the cost of doing facility-based work with temporary or regular
staff is significantly less costly than using an outside vendor. This is the
case generally with landscaping, facility repairs, clerical support and
many other services that organizations routinely contract for with outside
agencies. Take the more aggressive approach and manage the
project internally through regular staff or temporary staff and redeploy
the savings to other revenue generating projects.
LC.4.16 | CONSIDER SUBSTITUTING REUSABLE MATERIALS FOR DISPOSABLES |  |  |  | S4/B | ML | DIG
Velcro striping is reusable. In many situations such as arm bands, etc.
the use of velcro striping rather than taping is cost effective. In patient
care areas, audit the practices where velcro could be substituted for
tape, or where reusable resources can be substituted for one time
use resources such as tape. Every department should be able
to identify at least one or more areas where reusable resources can
replace usable ones with a comparable or improved quality outcome
and a reduced cost.
LC.4.17 | REVIEW THE POLICY/PRACTICE ON FREE MEALS IN THE CAFETERIA |  |  |  | S4/A | ML | DIG
Free meals are a significant cost factor in many organizations. Audit
the number of free meals provided and the type of people they are provided
to. Consider revamping that practice. Ask the question—what KRA
does this type of free meal serve? Is there a real value in it, or is it something
that we have always done and therefore think we must continue doing
it? If there is no real KRA value to it, change the policy/practice.
LC.4.18 | REVIEW THE PROCEDURES & PROTOCOLS FOR RECYCLING EXPENSIVE |  |  |  | S4/A | ML | DIG
MATERIALS AND SUPPLIES
Often an adoption of recyclable supplies/products procedures can result in
a reduction of costs through utilization and/or recycling of parts of the process or
materials. Each dept. is to identify at least one supply where recyclable
or substitute re-usable materials are adopted in place of disposable ones for
a cost savings to the organization.
LC.4.19 | EVALUATE HOSPITAL MAILINGS AND COSTS |  |  |  | S2/A | ML | DIG
Review the number and types of mailings that the organization sends out
to the community, past customers, physicians, Associates, etc. Which of
these communications can be handled with posing internally in
strategic locations VCR. a mailed piece? Which communications can be
combined/consolidated to one publication? How effective are mailings
to patients, i.e. what is the response rate, and is there a better way of
gathering that information?
LC.4.20 | MANAGE THE COSTS OF PRINTING AND DUPLICATION |  |  |  | S2/A | ML. | DIG
Review the printing patterns, quantities, and equipment used for producing
printing requests in your organization. Is the equipment sufficient to do the
job efficiently? Consider the costs of maintenance, supplies, staff time, etc. What
is the cost/benefit factor if different equipment, resources were considered?
What cost savings can be had?
LC.4.21 | PERSONAL USE OF FACILITY SERVICES |  |  |  | S2/A | ML | DIG
Some people do not distinguish the use of facility assets for business
from their personal use. Monitor the use of long distance phone calls
for personal use, the use of mail room service and express mail for
personal use. Identify what is appropriate and what is not, and
and sometimes it becomes a matter of disciplinary need.
LC.4.22 | PROCESS FOR HANDLING LARGE NUMBERS OF REFERRALS AT ONE TIME |  |  |  | S3/A | ML | DIG
Identify and put into place a contingency strategy for how your organization
would handle a large number of incoming referrals at any one point in time.
Think through staffing, operational flow, physician, physical and resource
needs. Identify the point in business levels where this contingency plan
would have to be put into place.
INITIATIVE LC.5: LOW COST INITIATIVES FOR MANAGING INNOVATION
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  |  |  | Priority | Priority | Leader | Approach
LC.5.1 | MANAGE INNOVATION |  |  |  | S5/A | MAC | DIG
Use data from DIG records to identify where operations are improving
significantly and where there is proportionately less improvement occurring.
Assess the information overall for each KRA. Establish priorities for each KRA,
work with RAC to create special incentive programs for innovative ideas.
in KRAs where add'l ideas are needed.
Direct the creative energy that resides in the organization into the prioritized
KRA areas of need for your organization. Track the results of your work.
LC.5.2 | RESOURCE & REWARD INNOVATION |  |  |  | S5/A | ML | DIG
At this point, the DIG process is relatively mature in the organization. It is time
to begin preparation for year II of TUL. Additional emphasis on BHAGs is
needed in year two. While DIGs and JDIs handle the problem-solving, the
bigger goals are the BHAGs. This is your second effort on installing BHAGs.
The reward and recognition for great BHAGs must be significant in order to
light a fire under Associates. Your assignment is to facilitate the development
of BHAGs, and the funding of the reward when the BHAG is achieved.
LC.5.3 | MEASURE & SET GOALS FOR INNOVATION |  |  |  | S5/A | MAC | DIG
The implementation rate for DIGs in Year II must be 90% at a minimum. DIG
work should have become a part of each Associate's job by this point in time.
It is your responsibility to assure that a specific minimal number of DIG
idea creations and implementations has become a part of the job expectation
for every Associate in the organization.
LC.5.4 | INSTALL THE IDEA ENGINE |  |  |  | S5/A | ML | DIG
Process incoming ideas through normal DIG & Just Do It processes.
Publicize results & rewards. This Task is centered around the challenge of
opening up new channels of communications and innovation within and
around the organization. The key to success will be the promotion of the
channels of communication and the process and implementation of the ideas
received. This is an opportunity to involve the community on a grand scale.
LC.5.5 | DEVELOP REWARD & RECOGNITION FOR LOW COST SYSTEM |  |  |  | S5/A | ML | DIG
IMPROVEMENTS
The work of system improvements is more difficult that any other work that has
been done to date. The difficulty arises from the sophistication of the work
systems that will be under review as well as the turf issues that will arise. Thus,
special reward and recognition programs will be needed in order to help
support and encourage the type of work that is needed.
LC.5.6 | STANDARDIZE COMMON PATIENT CARE ADMINISTRATIVE PROCESSES |  |  |  | S4/A | ML | DIG
This task is concerned with standardizing the common administrative processes
used on each patient care unit or in each patient care department.
Standardization of these processes will result in greater flexibility
between units.
INITIATIVE LC.6: BEGIN PHYSICIAN FOCUS OF LOW COST INITIATIVES
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  |  |  | Priority | Priority | Leader | Approach
LC.6.1 | PHYSICIAN UTALIZATION OF CARE MAPS |  |  |  | S5/A | ML | DIG
Most organizations still have a number of physicians who are practicing outside
of the approved care maps or clinical protocols and thus utilizing unnecessary
quantities of resources. Your task is to identify these problematic physicians
and work with the CEO to communicate the needed behavior changes or the
potential consequences. Procrastination on this task is costly to the
organization in real dollars as well as difficulty in having other physicians
comply with your practice needs. Take action now.
LC.6.2 | EVALUATE THE USE OF ECONOMIC CREDENTIALING FOR PHYSICIANS |  |  | S3/A | S3/A | ML | DIG
If you are not already practicing economic credentialing, then look into
adopting it in the most rigorous form acceptable to your organization
at this date. The bond between physician and hospital economics is
growing ever stronger. Unfavorable resource utilization should mean a
change in hospital privileges, processes, or utilization for some
physicians.
LC.6.3 | REVIEW SERVICES PROVIDED TO PHYSICIANS & COST/BENEFIT |  |  |  | S3/A | ML | DIG
Take an inventory of the perks, benefits, and free-bees provided to
physicians in order to attract them to your organization. Translate the perks etc.
into tangible dollars. Consider the benefits you are supposedly deriving from
this arrangement. Is the organization realizing the benefits they thought they
would get from this investment? If yes, then how can the situation be improved
without spending additional dollars? Rethink the cost/benefit analysis, talk
with physicians to see what it is they value, and recreate a new, better fitting
arrangement.
LC.6.4 | EVALUATE THE CONTENTS OF THE NEW HIRE/ASSOCIATE PHYSICAL |  |  |  | S3/A | ML | DIG
| EXAM FOR APPROPRIATENESS AND COST EFFECTIVENESS |  |  |  |  | Dir HR
What aspects of the current new hire physical exam process are truly
necessary and which can be deleted as they have no direct impact on
the person's ability to do the job or as a liability (worker's compensation)
to the organization? Many organizations conduct a full physical
exam including pap tests and EKGs on all new Associates. Some of this
is over kill and not needed. At the same time, what additional testing
should we be doing during the physical exam to assure that the person
is physically capable, without threat of damage to themselves or others,
to do the job?
LC.6.5 | EVALUATE THE IDEA OF STANDING PHYSICIAN ORDERS |  |  |  | S4/A | ML | DIG
Some areas of high traffic patient care operations represent consistent
requests for routine physician orders, yet physicians are not always readily
available to issue the order. The result is that hospital staff end up waiting
which represents unproductive time and longer patient stays. Your task is to
identify where there are consistent requests for the same types of tests,
|  | prescriptions, services, etc. that by law require a physician's order, but in |  | S4/A
reality are administered by hospital staff. Can you establish a standing
physician order that can be accessed under specific controlled situations
in order to eliminate the delay in waiting for an unavailable physician.
SESSION HQ: HIGH QUALITY STRATEGY
INITIATIVE HQ.1: CHANGES ADDRESSED AT UNCOMMON LEADER SESSION
Initiative Leader:
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
|  |  |  | Priority | Priority | Leader | Approach
HQ.1.1 | CONDUCT TUL SESSION: CONTINUOUS IMPROVEMENT TOOLS |  |  |  | S5/A | MHI | JDI
HQ.1.2 | PROVIDE TUL SESSION SUPPORT
|  | Assist seminar presenter in organization of afternoon work groups and |  |  | S5/A | MAC | JDI
other requests. Assure copies of materials that are to be presented by your
hospital presenter, i.e. map, strategic plan document, NAH Change Summary,
etc. arrive at MHI at least 5 business days prior to your scheduled classroom
date.
HQ.1.3 | PROCESS INCOMING MANAGER SUGGESTIONS FROM TUL SESSIONS |  |  |  | S5/A | MAC | JDI
Keep balance between NAH Action Plan Tasks/Initiatives & mgr.
suggestions. Build management machine, not just react to mgr. targets.
Use overhead lists created at TUL session & extend brainstorming. Sort
rapidly & assign to DIGs, Just Do Its (JDIs) JDIs speed time frames.
Balance Module Action Plan items & mgr. suggestions. Build mgt.
machine not just react to mgrs. targets. Use computer to plan, track & retrieve
data. Manage innovation.
HQ.1.4 | CREATE A HOSPITAL MAP |  |  |  | S4/A | ML | JDI
Present a copy of the map at TUL Session V. See the High Quality
Strategy Guide for a model map to use. The map is to be of one section of
the hospital and is not a traditionally formatted map that you might think of.
Bring copies of the map for all participants.
HQ.1.5 | PREPARE STATISTICAL GRAPHS FOR USE DAY 1 OF SESSION IV |  |  |  | S5/A | ML | JDI
Prepare statistical graphs of admissions/day, meals prepared per day,
and FTEs paid per day for each of the past 100 days. Separate
graphs for each kind of statistic. Transfer onto acetates for classroom use.
Call MHI if there are questions.
HQ.1.6 | IDENTIFY WORK GROUPS & TOPICS FOR SESSION IV CLASSROOM |  |  |  | S4/A | MAC | JDI
Identify 10 -12 inter departmental problems, systems, or processes that require
problem-solving. Specific types of problems sought are work system/processes
that require input from more than one department to fix. The identified problems
are to be reviewed with MHI immediately following TUL Session IV. Upon MHI
approval of identified problems, each TUL participant is to be assigned to
the most appropriate problem-solving group at least 3 weeks prior to TUL V.
A Chairperson is to be assigned to each group which we will call a Super DIG.
Super DIGs are to meet at least once prior to TUL Session V to orient
members as to the objective of the Super DIG, organize and plan their work.
Members are to bring needed problem-solving information/data to TUL
Session V as this is where the next piece of work will be done. An action
plan for solving the problem will be created at TUL Session V.
HQ.1.7 | PRESENT SUMMARIZED HOSPITAL STRATEGIC PLAN TO TUL |  |  |  | S4/A | CEO | JDI
| SESSION IV GROUP |  |  |  |  | ML
Using the samples enclosed in the Task, configure your present strategic plan
into this simple format. Make copies for all TUL participants and be prepared
to give a five minute summary presentation on the newly formatted strategic
plan document.
HQ.1.8 | COORDINATE STRATEGIC PLAN PROCESS WITH BUDGET PROCESS |  |  |  | S4/A | CEO | DIG
|  | The strategic planning process must be tightly correlated and sequentially |  |  |  | VP FIN.
|  | scheduled to support the budgeting process. The result is that all items in |  |  |  | ML
the strategic plan are supported financially in the budget in all necessary
departments, and department mgrs. know their role in each strategic initiative
thus improving the integrity of the budgeting process and follow up variance
monitoring.
HQ.1.9 | ESTABLISH KRA/BHAG COUNCILS FOR TUL YEAR TWO |  |  |  | S5/A | MAC | DIG
|  | Move from MAC mgt. to a hybrid of BHAG mgt. & DIG mgt. for future focus. |  |  |  | Ex. Vision
HQ.1.10 | CREATE 12 MONTH QUALITY IMPROVEMENT TACTICAL PLAN |  |  |  | S5/A | ML | DIG
A tactical plan for quality improvement in the coming 12 months should be
complete by TUL Session VI and shared with TUL participants. The plan is to
include components of this checklist and hundreds of quality initiatives as
identified by the Tasks in this guide plus the input from Associates & mgrs.
INITIATIVE HQ.2: QUALITY IMPROVEMENT IN WORK PROCESSES
| Initiative Leader: |  |  |  | Timing/ | Task | Rec
Task # | Idea/Task Title |  |  |  | Priority | Leader | Approach
HQ.2.1 | CREATE DEPARTMENTAL QUALITY CHARTS—EVALUATE QUALITY |  |  |  | S4/A | ML | DIG
| MEASURES |  |  |  |  | Dir. Quality
Current measures of quality within each dept. are up for review. Are
measures representative of core, critical processes within systems as well
as core outcomes? How many quality measures can each dept. reasonably
monitor? Can quality measures that are under control be replaced with
quality measures in need of monitoring without jeopardizing the
integrity of overall quality? Quality measures to be graphed and displayed
in each department for Associates to be aware of.
HQ.2.2 | FLOW CHART EACH SERVICE LINE |  |  |  | S4/A | ML | DIG
For each service line, chart all steps, from the moment the patient registers
at your facility, through to the time of discharge and follow-up.
Include distance traveled, wait time, challenges and problems to be
|  | solved in order to assure a seamless & expeditious experience. Look to reduce |  | Priority
the amount of time consumed for each service line process by 40%.
HQ.2.3 | CONDUCT "BREAKTHROUGH BENCHMARKING" FOR QUALITY PURPOSES— |  |  |  | S4/A | ML | DIG
USE ADDITIVE PROCESS THEORY
Use the criteria: Hi Volume, Hi Cost, Hi Utilization to identify services/processes
where breakthrough benchmark work would pay off by reducing the cost
at the same time increasing the quality of the outcome/experience. Contact
quality department & finance department to identify DRGs & services
where your cost & quality outcomes are not competitive. Go to work using
the additive process theory to change your results.
HQ.2.4 | FLOW CHART MAJOR PROCESSES WITHIN DEPARTMENTS |  |  |  | S4/A | ML | JDI
Task HQ. 2.2 calls for the flowing charting of service lines. This means that
many dept. processes & services will be involved in that flow charting effort, but
not all department processes will be included in that Task. In this Task, each dept.
is to identify the top 3 - 5 processes conducted within the dept. and flow chart
those processes with the objective of reducing dept. time needed to conduct
the process by at least 25 %, and/or improve the seamlessness of the process
as it relates to others who should benefit from your services. Use cycle
time analysis for the timing and distance traveled elements.
HQ.2.5 | EVALUATE ORGANIZATIONAL RESPONSES TO ERRORS IN PATIENT CARE |  |  |  | S4/A | ML | DIG
Errors in patient care come in various sizes & intensities. No error in patient
care is tolerable for any reason. A "no tolerance for patient care error"
attitude must be put in place. Communicate the new attitude and use
any error in patient care as a burning platform for immediate change in the
system, processes, and operations of the departments involved in the error. The
performance standard should be immediate correction and new safe guards to
assure that the same error cannot occur again.
HQ.2.6 | TAKE ACTION ON TRENDS IN ERRORS IN PATIENT CARE |  |  |  | S4/A | ML | DIG/JDI
Create a central monitoring function for errors in patient care. Monitor trends
in errors. Although Task HQ.2.5 calls for immediate corrective action for
errors in patient care, the trends of error activity need to be monitored in order
to adjust organization performance in the area of errors. Monitor trends
monthly and establish a power base for insisting on changes in operations,
training, etc., whatever is needed to destroy the trends that are seen. Do not
take any trend lightly, no matter how small.
HQ.2.7 | IMPROVE PHYSICIAN & CLINICIAN PROTOCOLS IN THE TRANSFER OF |  |  |  | S4/A | ML | DIG
PATIENTS
The point of patient transfer from physician to physician or department to
department, is a key point of error occurrence and a grey area of responsibility
and accountability. Establish a protocol for all types of patient transfers. Include
the roles the transferer and transferee will each assume and how the transfer
will be documented as complete. This is an extensive Task as it should involve
physicians, and all departments and staff who interact with the transfer of a
patient from dept to dept, service to service, physician to physician, or any
combination thereof.
HQ.2.8 | TAKE ACTION ON PATIENT TREATMENT DELAYS, RISKS & LIABILITIES |  |  |  | S4/A | ML | DIG
Patients are routinely experiencing delays of various lengths and for various
reasons in nearly all depts. Your Task is to have mgrs. identify the number, type
and length of delays occurring within their department, and make changes in
staffing, scheduling, or other protocols to eliminate delays in patient services.
This means that patients are served at the time they are scheduled to be
serviced, regardless. Contingency plans for emergencies and staff shortages
should be built into the improved operational plans.
HQ.2.9 | IDENTIFY CRITICAL CLINICAL CONTROL POINTS & INSTALL SYSTEM |  |  |  | S5/A | ML | DIG
ALARMS
Just as there are patient vital signs indicating the level of stability of the
patient, there are also critical control points within each patient care system
or process that indicate the health or illness of the functioning of the system or
process. At this point there are few, if any, standard critical control points within
the patient care system. Within each dept. critical control points need to
be established for the mainline services provided. The critical control
points serve as an early warning signal that this particular patient's service/
care is not as good as it needs to be. Simple examples of critical control points
might be a standardized timeframe for admission, a standardized point
of recovery within a prescribed timeframe for each major diagnosis, a standard
time frame for lab test turnarounds, call button requests, etc. Take each service
line and work with all contributors to the service line to establish critical points
of monitoring for each component of the service provided.
INITIATIVE HQ.3: QUALITY IMPROVEMENT IN PHYSICIAN PRACTICES
Initiative Leader:
Task # | Idea/Task Title
HQ.3.1 | ORGANIZE & MOBILIZE PHYSICIANS TO FOCUS ON COMBINED LOW COST/ |  |  |  | S4/A | ML | DIG
HIGH QUALITY INITIATIVES
Identify key performance areas in service lines or key DRGs where quality
performance or outcomes are inconsistent and/or questionable.
Systematically approach the identity of quality improvement by working
through each service line and key DRGs. Look for reasons why length
of stay is longer than desired in a service line or DRG, or by a particular
physician. Other things to look for include the need to redo work, i.e. lab tests,
food, housekeeping, medical record keeping, etc. Is there an incentive
for physicians to make changes to reduce costs and improve quality? Are
there incentives for others to make these changes?
HQ.3.2 | EVALUATE PHYSICIAN CONTINUING EDUCATION |  |  |  | S4/A | ML | DIG
|  | Are the physicians practicing at your organization using state-of-the-art |  |  |  | Dir. Med.
|  | knowledge? Do they attend and utilize the most current medical information |  |  |  | CEO
opportunities or are they stuck in the old tried and true approaches which are
often no longer applicable? What can the organization do to enhance
physician continuing education? Be creative, not costly.
HQ.3.3 | EXTEND BROAD USE OF CLINICAL PRACTICE GUIDELINES |  |  |  | S5/A | ML | DIG
There are likely to be some clinical paths or practice guidelines in place at your
organization. However, there need to be agreed upon and enforced clinical
practice guidelines for all major service lines, major DRGs, and strategic
DRGs by which all physicians will practice. The clinical practice guidelines
standardize the level of care that patients will receive as well as standardize
the costs and potential outcomes. Of course, appeal processes or exceptions
must be able to be made, but they truly need to be on an exceptional basis.
Move rapidly to create & enforce clinical practice guidelines for all service lines,
key DRGs, and strategic DRGs.
HQ.3.4 | IMPLEMENT COMPUTERIZED DIAGNOSTIC SYSTEMS AS SECOND OPINION |  |  |  | S5+/A | ML | DIG
| OR CHECK POINT FOR PHYSICIANS | [5 empty] | CEO
Physicians have grown cautious in making diagnosis & generally employ the
second opinion of a colleague as a check point. The problem is that the
colleague is often from the same school of thought and/or easily persuaded by
the primary physician, thus the second opinion is not as objective & valuable
as it should be. Computerized diagnostic systems are purely objective in
nature & often provide new ideas/information for the primary physician
to consider. As a quality improvement tool, computerized diagnostic systems
should be a requirement for all physicians to use.
HQ.3.5 | EVALUATE PHYSICIAN PEER REVIEW PROCESS |  |  |  | S5/A | ML | DIG
Is the scope of the physician peer review process as complete as it needs to
be? Complete peer preview would include credentialing, continuing
education, adherence to clinical practice guidelines and utilization review,
economic contribution, quality outcomes, relationship development. Make
enhancements as needed in your approach to peer review.
INITIATIVE HQ.4: NEW THINKING IN QUALITY MANAGEMENT
| Initiative Leader: |  |  |  | Timing/ | Task | Rec
Task # | Idea/Task Title |  |  |  | Priority | Leader | Approach
HQ.4.1 | DEFINE NEW ROLES OF CI SPECIALISTS IN QUALITY INITIATIVES |  |  |  | S5/A | ML | DIG
CI specialists play a leading role in all future quality initiatives. An analysis
of current system/processes is the first step to making changes, followed by
brain-storming, and concluding with an in-depth analysis of the proposed
change made prior to the piloting of the change. Changes in information
|  | systems should always include a CI specialist in the planning phases because |  | Priority
the operating system should drive the information/automation system, not
the reverse. CI specialist is not a full time position.
HQ.4.2 | IDENTIFY CLINICAL OUTCOME MEASURES USED TO DETERMINE 100 BEST |  |  |  | S5/A | ML | DIG
HOSPITALS & MOVE TOWARD THEM—RAPIDLY
The "100 Best Hospitals" list is constructed based on quality & financial stats
on a comparative basis with hospitals within your category. If you are to com-
pete, you must know where your competitors are & what their level of perform-
ance is. Contact Jean Chenoweth at HCIA 1-800-568-3282 for details
on the 100 Best Hospitals information. Compare your quality stats with the
best and create a strategic plan for moving your stats to meet or exceed those
who are currently rated as the best.
HQ.4.3 | BOOST JCAHO STANDARDS OF PERFORMANCE IN YOUR ORGANIZATION |  |  |  | S4/A | ML | DIG
JCAHO, by their own admission, represents what the minimum standards of
performance should be in any healthcare organization. NAH standards need
to be among the best in the industry, thus comparisons with minimal standards
makes no sense. Use JCAHO survey results to identify areas for immediate change
simply to meet minimal standards. Take all JCAHO standards and boost them
by a factor of at least two, meaning that your new organizational standards are
at least twice as stringent as what JCAHO would require.
HQ.4.4 | EVALUATE NCQA OR OTHER ACCREDITING BODY AS SUBSTITUTE FOR |  |  |  | S5/A | CEO | DIG
| JCAHO ACCREDITATION |  |  |  |  | ML
|  | The Value/Cost ratio of JCAHO services and accreditation has come under |  |  |  | Quality Dir.
substantial criticism in 1995 +. Alternative accreditation bodies have been
identified by a number of leading states. This Task has the responsibility of
identifying & evaluating alternative accreditation bodies in lieu of JCAHO.
What other accreditation bodies are there? What states and organizations
have had success transferring from JCAHO to another body? What costs/
benefits would accrue to your organization if you were to take the lead in
making the change? If no change is made, then how can your organization
get greater value out of the JCAHO relationship?
HQ.4.5 | RESTRUCTURE QUALITY, UTILIZATION, ACCREDITATION & RELATED |  |  |  | S4/A | CEO | DIG
SERVICES UNDER ONE DEPARTMENT
Take an inventory of all services that fit under the umbrella of "Quality", i.e.
Utilization Review, Quality Assurance, Safety/Security, Infection Control,
Risk Mgt., Peer Review, etc. Consolidate all such services under the umbrella
of one Director for a more synchronized & effective management.
HQ.4.6 | STUDY NCQA STANDARDS AND HEDIS QUALITY INFORMATION |  |  |  | S4/A | ML | DIG
The National Council for Quality, and the Healthcare Employers Data
Information Set are two sources for comparative statistical data to use in
evaluation of your organization's quality and pertinent performance stats.
Both organizations are influencial in healthcare. HEDIS is growing in power
and soon will command the success or failure of individual hospitals based
on hospital performance stats in the areas of quality, cost, and Customer satisfaction.
Compare your organizational stats with the standards set by HEDIS and NCQA
and set goals to meet or exceed the stats posted in HEDIS for your type of
organization. Create a tactical plan that outlines how this will be accomplished.
INITIATIVE HQ.5: QUALITY DEVELOPMENT OPPORTUNITIES
| Initiative Leader: MAC |  |  |  | Timing/ | Task | Rec
Task # | Idea/Task Title |  |  |  | Priority | Leader | Approach
HQ.5.1 | TEACH CI TOOLS AS STRATEGY TO PROBLEM-SOLVE SYSTEM ISSUES— |  |  |  | S5/A | ML | DIG
| ENCOURAGE QUALITY-PRODUCTIVITY CONNECTION |  |  |  |  | TAC
CI tools are taught in TUL Session V, but need reinforcement for use in the
organization. CI specialists are identified to assist in complex system projects,
and to teach Associates about CItools for improvement in their jobs. As a
part of the training, the message regarding the pragmatic connection between
|  | quality and productivity needs to be made as frequently as possible to increase |  | Priority
Associate understanding which leads to compliance & utilitization.
HQ.5.2 | EVALUATE PC AVAILABILITY & SOFTWARE TRAINING NEEDS FOR QUALITY |  |  |  | S5/A | ML | DIG
CHARTING
"A picture is worth a thousand words." A chart is a picture of quality performance.
An earlier Task requires dept. mgrs. to chart and publish quality performance
within their department. In order to do this, they must have access to software
and PC's upon which they can create the charts. This is your Task. How best
can the organization provide computer & software assistance in the short term
and in the long term?
HQ.5.3 | EVALUATE FREQUENCY OF QUALITY AUDITS IN All SERVICE LINES |  |  |  | S5/A | ML | DIG
Determine who is responsible for auditing/monitoring the quality of
services within the organization, how frequently they would be monitored,
what tolerances are acceptable and not, and who will handle less than
acceptable quality performances. What are the quality goals? Are
they great enough? What are the rewards if achievements are made, &
realities if they are not made?
HQ.5.4 | ABOLISH ISOLATION: ESTABLISH NETWORKS & WEBS OF BEST PRACTICES |  |  |  | S5/A | ML | DIG
STUDY GROUPS FOR SPECIALITIES AMONG ORGANIZATIONS
Establish networks and webs of sources of best practices for all components of
service lines & major DRGs offered at your organization as well as the top
15-20 DRGs for your organization. Search out top performing organizations &
investigate details of their success. Do not limit your web to healthcare.
Spend a considerable amount of time webbing with excellent organizations
outside of healthcare; adapt their approaches to your business. Commit
to improving your top service lines & DRGs by learning through your new
web. Move to the learning/leading edge of quality initiatives.
HQ.5.5 | IDENTIFY DIAGNOSIS WHERE RISK OF COMPLICATIONS HAVE PROVEN |  |  |  | S5/A | ML | DIG
TO BE GREATEST IN YOUR ORGANIZATION & MAKE CHANGES
Work with quality & risk management staff to determine DRGs where percentage
of patients with complications is high, or gross number of patients who
develop complications is large, and move to change the protocols that are
contributing to the development of complications. The goal should be no
complications.
HQ.5.6 | IDENTIFY DIAGNOSIS WHERE RISK OF DEATH IS GREATEST IN YOUR |  |  |  | S5/A | ML | DIG
ORGANIZATION AND MAKE CHANGES
Some diagnosis have greater risks of death associated with them,
yet in the face of mortality, some organizations/professionals have smaller
mortality rates than all others. What is it that they are doing to reduce the
mortality rate? What can your organization do to reduce or eliminate the
mortality rate in the high risk areas?
HQ.5.7 | ESTABLISH QUALITY READING STANDARDS & APPLICABLE DISCUSSIONS |  |  |  | S5/B | ML | DIG
Dept. mgrs. & executives need to be more widely read in the area of
quality initiatives, leadership, change, and people growth. The objective of
this Task is to establish minimal & routine quality reading standards for all dept.
mgr. and applicable discussion groups.
HQ.5.8 | MOBILIZE JOB ENRICHMENT & REDESIGN WITHOUT LAYOFFS |  |  |  | S5/A | ML | DIG
|  | Based on the staffing needs of the next 12 - 36 months, strategically & |  |  |  | Dir. HR
|  | aggressively plan for the combination of more jobs (job enrichment) than have |  |  |  | TAC
recently been combined, and the creation of new types of positions that will
support the new services, technology, and structures that will evolve in the next
12 - 36 months. The objective is to enlarge & enrich current positions by-
combining, crosstraining, and eliminating tasks, while redeploying the balance
of the under utalized staff into training programs as needed to fill the new
positions that are to be created. No layoffs are to be administered.
See the task for further details.
INITIATIVE HQ.6: Quality Improvement In Operations
Initiative Leader: MAC
Task # | Idea/Task Title |  |  |  | Timing/ | Task | Rec
HQ.6.1 | REVIEW DEPARTMENT PHYSICAL LAYOUTS |  |  |  | Priority | Leader | Approach
|  | As a follow up to the assignment for dept. mgrs to flow chart dept. systems |  |  | S5/A | ML | DIG
and processes, this Task identifies physical changes that are required within a
department in order to improve quality and productivity. This means looking
at the most efficient layout for equipment, people and service flows. Major
physical construction is not an option due to cost, however, most changes
should not require major physical plant modifications. Use the objective input
from colleagues, staff, and other departments that work closely with you
to assist in rearranging the department layout.
HQ.6.2 | REVIEW PATIENT ROOM LAYOUT |  |  |  | S5/A | ML | DIG
Review the physical layout of patient rooms looking for ways to
rearrange supplies, equipment, patient location, lighting, etc. in order to more
efficiently deliver patient care within that room. This may also include adding
common pieces of equip. to each room, supply sources and other support needs
to speed and improve the delivery of care. There is a Customer Service
Task assigned to look at ways to improve the friendliness, comfort and
acceptability of patient rooms. This Task is not a duplication of that Task.
HQ.6.3 | REVIEW PATIENT & VISITOR WAITING AREAS |  |  |  | S5/A | ML | DIG
Visitor waiting areas are not always considered in the full realm of the
patient delivery experience, yet they should be. Constant communication
with family members in waiting areas is a simple, yet powerful Task required
of patient care givers. This Task is to review visitor waiting areas looking for
ways to improve the waiting experience while make more efficient use of staff
time. Can waiting areas be reconfigured for greater ease of staff to visitor
communication? What other incidents do you experience with waiting patients
& visitors that consume staff time, or create irritants for visitors, staff or physicians?
These are clues of items to fix. The goal is an improved visitor experience
and improved efficiency for hospital staff.
HQ.6.4 | ASSESS NEED FOR MANAGEMENT ENGINEERING PROFESSIONAL |  |  |  | S5/B | ML | DIG
|  | How extreme are your organizational needs for system redesign? How well |  |  |  | EVC
trained, available, and willing are your staff to make substantial system/process
and job redesigns? Would a trained management engineer on staff at your
organization be an asset that you can use, or do you feel that you can
adequately handle major system changes, etc. with existing staff in the time-
frame needed? Include executives in this evaluation.
HQ.6.5 | DEVELOP VENDOR REALTIONSHIP & INVOLVEMENT IN QUALITY INITIATIVES |  |  |  | S5/A | ML | DIG
Vendors are both contributors to high/low quality as well as problem-solvers.
Dept. mgrs. are to identify their top 5 vendors and enlist active participation from
them in this initiative to improve quality. More details of what and how to do this
in the Task.
HQ.6.6 | DEVELOP & MOBILIZE INTER-INTRA DEPARTMENTAL WORK PROCESS |  |  |  | S5/B | ML | DIG
PROBLEM-SOLVING DECISION MAKING MATRIX
The decision matrix tool was introduced in TUL Session V. Take this tool
and determine the "Required" attributes that must be fulfilled in all decisions.
Standardize the "required" attributes & the use of the tool in your
organization. This will reduce the variance in decision-making within the
organization and assure that all "required" components are included in every
decision.