DIG TRAINING GUIDE

FOR

PROBLEM SOLVERS

Dear ______________

Congratulations and thank-you for making the decision to chair one of our hospital’s Do It Groups (DIGs)!  DIGs are one of the key ingredients in Trinity’s culture and success.  DIGs are formed because of our commitment to “listen and respond”.  Being a DIG chair is an important role.  Not only will you have the opportunity to lead a DIG Team, but, you will have an opportunity to make a difference.  The recommendations that your DIG group will develop can make a visible difference in the services that we provide.  Remember:  Our goal is improvement and not perfection.

Thank you for your commitment to improving Trinity Hospital!

Sincerely,

Tom Mroczkowski

Tom  Mroczkowski, Chief Executive

##### DIG Chair Training Agenda

#### ____________________________________________________

#### Introduction									20 Min.

### DIG Members and Accountabilities					20 Min.

### ____________________________________________________

### Meeting #1 									15 Min.

### Meeting #2									15 Min.

### Meeting #3									15 Min.

### Meeting #4									15 Min.

Reports and Forms						                20 Min.

##### Learning Objectives

Purpose:	To provide newly selected DIG chairperson with the information, tools and techniques to successfully chair a DIG Team to completion within the scope of the Do It Group (DIG) Assignment.  After the session you will be able to:

1.	Summarize how an Idea becomes a ‘Do It Group’ (DIG).

2.	Discuss the relationship of the Do It Groups to the Key Result Areas (KRAs), The New Trinity (TNT) and the Mission Values and Philosophy (MVP).

3.	Define basic concepts and components of a Do It Group.

4.	Successfully conduct Do It Group meetings utilizing the appropriate CQI Tool(s).

5.	Complete all related paperwork.

DIGS and The Victory Scoreboard

The Victory Scoreboard located inside the cafeteria keeps all Associates informed of Trinity’s  DIGs.  There are two categories on the Scoreboard:

- DIGs

DIGS that are still looking for membership are posted by shift here.  If an Associate is interested, they can sign up directly on the form.  Also, if an associate is interested in chairing the  DIG,  they can sign their name directly in the chairperson slot.

- Number of DIGs/JDIs implemented

When the recommendations are fully implemented, then the

indicator is moved.

An updated scoreboard is the focus of information on the New American Hospital change process!

OUR HOSPITAL’S

FOUR KEY RESULT AREAS

In Order of Decision Making Preference

1.  High Customer Satisfaction

2.  High Quality

- Growing the Best People

4.  Low Cost/Good Value

ORIENTATION TO DO IT GROUPS (DIG) AND JUST-DO-ITS (JDI)

What Is A Do It Group?

Do It Groups (DIG) are project teams that meet to solve problems.  They are commissioned to get things done.  DIGs focus on solving a single, specific problem within thirty days.  The goal is improvement, not perfection, with an emphasis on swift improvement.

Membership:	Three to six (including chair) with representatives from all of the departments affected by DIG

Duration:		Approximately 30 days

### Frequency:		Weekly meetings, one hour per meeting

Methods:		A Four Step Problem Solving Method ‘D-O-I-T’

Define the problem

Outline causes and identify solutions

Implementation plan

Test changes/track results

Reporting:	DIG reports are due to the Management Action Council (MAC) within 45 days after the DIG begins.  60-day DIG Follow-up Forms are also required documentation.

Source of DIGS: DIGS/JDIs are Associate ideas to improve customer satisfaction,  improve quality, improve organization climate, grow best people, or reduce costs. The ideas may or may not have tangible return on investment. The need only be a good idea that is able to be implemented, and be based on a low cost/no cost philosophy. Ideas that cost money must be accompanied by a Return on Investment form.

ORIENTATION TO A JUST DO IT ASSIGNMENT (JDI)

A JDI is an Associate idea that can be assigned to just one person to handle. The objective of the idea is for improvement to customer satisfaction, quality, cost management, organization climate, or growing the best people .  A JDI counts toward an individual associate’s goal of innovation and recognition and reward. The JDI can be submitted to your  department manager to the MAC directly.

DIG MEETINGS

DIGs generally meet weekly.  Problem solving works best when groups “stay on task.”  DIG meetings should be limited to one hour.  The first meeting should be announced two weeks in advance with group consensus.  Subsequent meeting dates, times and other ground rules should be determined at the first meeting.  This is the most efficient way to schedule meetings and will assure greater attendance.

Implementation of the plan of action should begin ideally by the fourth week (assuming the project doesn’t require executive review.)  The DIG report and action plan should be completed and ready for presentation to the MAC.  An appointment should be made to present the DIG recommendations to the MAC.

A follow-up meeting should take place one month after the implementation of the action plan to monitor, review results and determine necessary changes.  It is the responsibility of the DIG chair to arrange for the follow-up meeting.

It is strongly recommended that a flipchart be used at each meeting to document the ideas and facts that are generated at the meeting.  The recorder should chart the discussion as it flows.

DIG PROCESS FLOWSHEET

DIG ROLES

The DIG chairperson is not exclusively responsible for the success of the DIG.  Equal participation is expected from all members.  Therefore, many roles exist for the other team members.

###### DIG Chair

Recorder

Co-Chair

Devil’s Advocate

Recorder

### ROLE AND EXPECTATION OF DIG MEMBERS

### Membership

- Hold myself and others responsible for OUR Hospital’s success

- Support NMH  in all that is said and done

- Do not make negative comments about NMH or others

- Treat customers and each other in a respectful and courteous manner

Meetings and Communication

- Notify your manager of meeting dates and times in a timely manner to ensure departmental coverage in your absence.

- Attend all meetings (4 are required for credit)

- Contact DIG Chair to report an absence or tardy prior to the start of the next scheduled meeting

- Report to meetings on time.  Late is defined as arriving five minutes or more after the start of the scheduled meeting time.  Two or more occurrences will cause you to loose credit for the DIG

- Complete assignments, bring notes, agendas, schedules and calendars to the meetings

- Verbally contribute to the DO-IT process

- Be courteous, don’t interrupt others who are speaking

- Respect opinions and ideas of others

- Focus on the DIG, time is limited

- Objectively listen to discussions with the focus on a positive outcome

Reporting

- Provide input for the completion of the DIG and 60-Day Follow-up report

Follow-up

- Participate in the implementation of DIG recommendations

- Participate in tracking and monitoring of recommendations

Note:  If I am unable to fulfill the expectations as a member

- of a DIG, I understand that I may be asked to surrender my membership.  Credit will not be granted for participation in this case.

ROLE OF THE DIG CHAIR

### Membership

- Recruitment

- Mixture: number and type

- Role assignments  (i.e. co-chair, timekeeper, devil’s advocate)

- Determine ad-hoc membership (Add a topic expert)

- Review ground rules and expectations with members

- Review responsibilities of assigned roles with members

- Reassess membership (add/remove members)

- Set ground rules with DIG members

Meetings and Communication

- Determine best meeting time and place with DIG members

- Prepare agendas

- Attend all meetings

- Complete all assignments

- Communicate information, changes in membership etc., to DIG members

- Send out DIG communication letter to associates whose membership cannot be accepted due to mixture, number or fit

- Initiate communication with MAC contact prior to first DIG meeting

- Keep Management Action Council (MAC) contact informed of progress or problems

- Discuss DIG recommendations with MAC contact prior to MAC presentation

- Work with MAC contact to communicate to department leaders, DIG members who are not in attendance or those who have involuntarily resigned

Facilitation of meeting

- Encourage each person to contribute and ensures each person is heard

- Ask open-ended questions; Ones that can’t be answered with  a “yes” or “no” response, but require more thought and comment

- Intervene when discussion is being dominated.  For

example, “I understand your point, now let’s hear from

someone else.”

- Keep group on task

- Encourage idea generation and participation

- Guides group to consensus (an agreement that everyone can live with)

- Introduce CQI tools for decision making

- Delegate tasks as necessary

Reporting

- Responsible for the timely completion, outcome and contents of the DIG

- Ensure that DIG reports are completed. Guide group for input in completing

- Present recommendations to MAC before implementation

- Submit completed DIG Report to MAC

- Present recommendations to Executive Vision Council

(EVC)  if  expenditures exceeds $XXXX

Follow-up

- Participate in tracking and monitoring of recommendations

- Complete 60-Day follow-up report

- Review results with DIG members and determine next course of action, if any

- Recognize the contributions of DIG members

ROLE OF DIG CO-CHAIR

### Membership

- Coach other members to accomplish assignments

- Partner with Chair in decision making or action items

- Assume role of Chair in their absence

- Lead one meeting in preparation to Chair a DIG

Meetings and Communication

- Attend all meetings

- Complete all assignments

- Facilitate the gathering and distribution of information to team members

- Assist  with introduction of CQI tools

Reporting

- To Management Action Council (MAC) (if necessary)

- Completion of the DIG report

Follow-up

- Participate in 60-Day follow-up

- Participate in DIG implementation

- Participate in tracking and monitoring of recommendations

ROLE OF DEVIL’S ADVOCATE

### Membership

- Act as the team’s “opposition”. Objects, questions and encourages team to look at different perspectives. This is done in a non-challenging manner.  The purpose is to assure that the team does not ‘jump to conclusions’  or have ‘group think’ where all members quickly come to the same decision.

Meetings and communication

- Attend all meetings

- Complete all assignments

- Facilitate the gathering and distribution of information to team

Reporting

- Provide input for the completion of the DIG and 60-day Follow-up reports

Follow-up

- Participate in 60-Day follow-up

- Participate in DIG implementation

- Participate in tracking and monitoring of recommendations

ROLE OF RECORDER

### Membership

- Act as the team’s “note-taker” in all cases.  The purpose is to ensure that ideas and facts generated at meetings are documented.  It is strongly recommended that a flipchart be used at each meeting. The recorder should chart the discussion as it flows.  Several marking pens should be on hand, and some masking tape to hang pages on a wall.  This simple technique allows for better control of the discussion, as well as generates a set of notes that can be taken away from the meeting for later use and follow-up.

Meetings and Communication

- Attend all meetings

- Complete all assignments

- Facilitate the gathering and distribution of information to team

Reporting

- Document all discussion and decisions made during meetings

- Keep track of assignments

Follow-up

- Participate in 60-Day follow-up

- Participate in DIG implementation

•  Participate in tracking and monitoring of DIG implementation plan/progress

ROLE OF TIME KEEPER

### Membership

- Act as the team’s “clock-watcher.”  The purpose is to ensure that you keep the teams discussion focused at every meeting.  It is strongly recommended that you verbally make note of the time regularly (i.e. every 15 minutes).  Each meeting should only last one hour.  Therefore, the time available for lengthy discussion and debate is limited.  It is common for teams to quickly get off track with stories or examples of how they may have experienced the particular problem. The time keeper should ensure that meetings start on time, end on time, and stay focused.

Meetings and communication

- Attend all meetings

- Complete all assignments

- Facilitate the gathering and distribution of information to team

- Keep the agenda on track by offering quick summaries.  For example, “Okay, so far we have determined that ....”

- Restate relevant points of the agenda when the discussion veers from objectives

Reporting

- Provide input for the completion of the DIG and 60-Day Follow-up Reports

Follow-up

- Participate in 60-Day follow-up

- Participate in DIG implementation

- Participate in tracking and monitoring of recommendations

Role of Management Action Council Contact

(MAC) Contact

### Membership

- Act as the team’s “coach and resource person”

Meetings and Communication

- Assist with removing barriers that prevent DIG from moving forward

- Provide the DIG chair with a detailed explanation of the purpose and intent of the DIG

- Communicate with DIG chair prior to first DIG meeting

- Provide any additional information/support that is needed to ensure the successful completion of the DIG

- Assist chair with communication to department leaders any DIG members who are not attending or who have voluntarily resigned

Reporting

- Assist DIG chair in completing the DIG Report (if necessary)

- Meet with the DIG chair prior to the MAC presentation

- Review completed DIG report before implementation

- Ask for recommendations for other DIGs

Follow-up

- Encourage completion of the 60-Day Follow-up report

- Encourage DIG implementation

- Follow-up with delinquent DIGs

OVERVIEW OF DIG CHAIR ROLE

I.	Role of DIG chairperson

A.	Membership

The DIG chairperson selects members that are known to have an interest in the DIG topic as well as people who represent appropriate areas affected by the DIG.  You have received the names of those who have already volunteered to work on your DIG.  Generally, five to seven people represent the best working number of people on a DIG.  Groups larger than this are hard to handle, and smaller groups don’t have enough brain power to get the work done.  If you need additional members, you may contact individuals directly.

Contact your DIG members immediately.  Before the first meeting, send an agenda to each DIG member with thought-provoking questions to prepare people for the first meeting.

As the DIG progresses, review your membership to assure that you continue to have appropriate representation (all departments who will be affected by the DIG should have a voice).  Expand membership or replace members as needed.

B.	Meetings and Communications

The DIG chairperson selects a co-chairperson.  The DIG chairperson facilitates the co-chairperson’s growth as a future DIG chairperson.  The chairperson works closely with the co-chairperson in a mentor-like relationship.

Prior to the first meeting, the DIG chairperson communicates the purpose of the DIG and distributes any supporting documents or information related to the DIG’s purpose.  An information packet and agenda should be distributed to all members.  The

chairperson schedules the time, date and place for the first meeting, and requests members to bring their calendars to schedule subsequent meetings.

When conducting DIG meetings, the chairperson should:

- Assign roles to participants.  The following roles are to be assigned:  timekeeper, devil’s advocate and recorder.  Specific responsibilities of these roles are outlined in previous section of this manual

- Clearly define the issue to be resolved

- Encourage participation from all members

- Keep meetings focused

- Start and end the meeting on time

- Assess the effectiveness of each member’s participation and the group interaction

- If you experience roadblocks or problems with meeting goals, call your MAC contact

- Use flipchart to document notes of discussion during the meeting.  A flipchart helps you make discussion points clear and provides easy reference for the discussion

C.  Leadership Cautions

Control should be subtle.  Little things can affect the tone of a meeting and cause it to come apart or lose momentum.  They can also destroy the respect participants have for the leader.  This could occur if:

- The chair resents a comment made by a participant and shows it

- The chair gets into the discussion and monopolizes it

- The chair plays the role of a comic.  A little humor is welcome

- The chair puts the participant down, especially with a personal remark.  There may be periodic problems with a participant.  However, a personal and public put-down is never the right way to handle such a situation

- The chair allows an argument to develop between participants

- D.	Reporting

- The DIG chairperson is responsible to keep the MAC informed of progress, problems, and significant developments.  Use your MAC contact to assist in this process.  Complete the DIG report and submit to the MAC prior to your deadline

- E.	Follow-up

- The DIG chair may be asked to present the DIG recommendations to the MAC or the Executive Vision Council.  It is the chairperson’s responsibility to follow through on recommendations to the successful completion of required actions.  Be proactive; Do not wait indefinitely to hear from the MAC.  Tips on how to effectively handle this assignment are:

- Identify the purpose of the DIG in one or two sentences

- Identify the KRA which will be improved by approval of these recommendations

•  	Present recommendations concisely

- Assure that the DIG has contacted the individuals or departments who are involved or will be affected by the recommendations

- Identify additional funds if necessary.  If additional funds are needed, can they be transferred from another cost center.  If unable to financially implement this year, can the recommendations be deferred to the next budget year?

The DIG chair communicates any decision related to recommendations submitted from the DIG first to the DIG members and then to organization.

Finally, recognize contributions of DIG members.

Celebrate achievements!

DIG FLOW CHARTS

SOURCES OF IDEAS

•  ASSOCIATES

•  PHYSICIANS

•  VISITORS

•  CUSTOMERS

IDEAS ARE ADDRESSED TWO WAYS:

JDI (JUST-DO-IT)

An individual assigned to do a specific task

DO-IT-GROUP (DIG)

A group of stakeholders assigned to solve a   problem

DIG CREATION FORM

_____________________________________________________________

Associate's Name                                                                                        Department                          Phone Extension

We are looking for ways to improve everything we do.  We accomplish that by making suggestions and setting up DIGs to make these ideas work.  A DIG may be initiated by any Associate.  If you have an idea or have identified a problem and would like to have a DIG formed, complete this side of this form.  Forward this form to the chairperson of the Management Action Council (MAC).

1.Is this an Idea for something new or different, or is this a problem that needs to be solved?

•  If this is an idea, state the idea________________________________________		_________________________________________________________________

•  If this is a problem, answer the following questions:

1a	Describe the problem?____________________________________

1b.	Where does the problem occur? _____________________________

1c.	When does it occur? _____________________________________

1d.	Who does it affect? _______________________________________

1e.	What magnitude is the problem?  ____________________________

1f.	What is distinctive about the problem? ________________________

1g.	What are possible causes? _________________________________

2.  Is this problem or idea unique to your department or does it impact more 			     broadly?

_____   Impacts my department only

_____    Impacts multiple departments

_____    Impacts the entire organization

3.  Would you like to serve on the DIG addressing this problem?

YES ___    NO ____ If so, have you had DIG training?   YES ___   NO ___

4.  Would you be willing to serve as chairperson of this DIG?  YES ___   NO ___

5.  Which performance areas do you think this idea or problem impacts most:					___Customer Satisfaction	___Economics

___Quality	___Productivity

___Organization Climate	___Economics

___People Growth	___Innovation

6.  Has this idea/problem been discussed with your manager?  YES __  NO ___

7.  Other comments that will help us better understand your idea or problem to be solved. ___________________________________________________________

_________________________________________________________________

After completing this section of the form, please submit to the MAC

MAC USE ONLY

1._______	Date idea was received by MAC

2._______	Date status of idea was communicated to idea originator

3._______	Date DIG was established  ____Date JDI was established

4._______	Date recommendations reviewed by MAC

5._______	Date recommendations reviewed by executives, if appropriate

6._______	Date DIG Chair advised of results

5. Name of MAC contact person_____________________________________

6. Idea/Problem Scope:

_______	Intra-department (within one department)

_______	Inter-department (between two or more departments)

_______	Organization-wide

7. Department heads who were notified:    _____________________________	_____________________________        _____________________________	_____________________________        _____________________________

8.  DIG  Name: _______________________   DIG/JDI #__________________

JDI Assigned to:  _____________________________________________

9.  DIG Chairperson & Members:  (Associates may be identified by MAC or recruited  and finally selected by the Chairperson).

_____________________________________________________________

Chairperson's Name                                                           	Department                                	Phone _________________________________________________________________

Associate's Name                                                                             	Department                               	Phone  _________________________________________________________________

Associate's Name                                                            	Department                              	Phone _________________________________________________________________

Associate's Name                                                           	 Department                             	Phone _________________________________________________________________

Associate's Name                                                                              Department                             	Phone  _________________________________________________________________

Associate's Name                                                                              Department                   	Phone _________________________________________________________________

Associate's Name                                                                              Department            	Phone                 ________________________________________________________________________

DIG PROCESSING

PHASE I

IDEA FROM ASSOCIATE

ASSOCIATE’S     DEPT MANAGER

DIG COORDINATOR      OR TO  MAC  CHAIR

CHART “A”

DIRECTIVES

CHART “B”  DIRECTIVES

CHART “A” DIRECTIVES

CHART “B”

DIRECTIVES

DIG ACCOUNTABILITY

• Associate responsibility

Each Associate is responsible for submitting at lease ___ DIG/JDIs per year, and participating on at least ___ DIG/JDIs per year.

• The DIG Co-ordinator maintains data base of:

• Each DIG/JDI submitted

• Who submitted it (employee name, department)

• Date submitted

• Dates of communications sent from MAC

• Result: DIG, JDI, Hold, Duplicate

• Return on Investment per DIG/JDI

• Cost to implement

• Participating employees

• Date completed

• Category of idea: Customer, Quality, Cost, People

• Reports by depart, by VP etc.

DIG Meeting #1

Define the Problem

Purpose

At the first meeting, specify the problem or idea.  Who is affected? When is it a problem?  Where does it occur?  What happens around or about the problem or idea?  Don’t fall into the trap of jumping to conclusions and don’t allow people to offer solutions at the first meeting.  Spend this first hour getting to know the problem.

Often groups find that they need to gather information, or talk to others to better understand what’s going on.  Ask yourself, what data do we need in order to understand and analyze the problem?  Who will collect the data?  Where will it be collected?  Better to do that now than to proceed in an uninformed way.  As a general rule, input should be sought from all areas involved.  If the problem is heated or there has been past conflict, each side should be allowed to state the problems without interruption while the other side records the problems.  When both sides have aired their opinions, summarize what the problem seems to be by incorporating common facts from all sides and listing the potential contributing issues or ramifications to be considered in solving the problem.

NOTE:  After defining the problem, review DIG membership to assure that all applicable Associates are involved in solving the problem either as part of the DIG team or as a special resource to the DIG.

Pre-Meeting Checklist

DIG Meeting #1

Define the Problem

Planning Checklist

Meet/talk with your MAC contact to ensure that you are clear about the intention of the DIG

Get appropriate number and representation of members

Send out TNT Communication letters

Send a letter to all of the DIG members thanking them for participating

	Seek best date/time convenient for most of the members

	Schedule meeting room (Call ext. 4100 to schedule meeting rooms)

Send agenda to all members and remind them to bring their schedules and/or calendars

Obtain appropriate equipment (overhead, flip chart easel) from the Library

DIG Meeting #1

Define the Problem

Meeting Agenda

5 min. 		Welcome and Introduction of DIG members

- Thank members for participation

- Have members sign an attendance sheet

10 min.		Review DIG roles/responsibilities

•   Determine roles: Devil’s Advocate, Timekeeper, Recorder, Co-Chair

•   Set ground rules

5 min.		Review the 4 Step D-O-I-T Process

5 min.		Review and discuss the ‘problem or intent’ of the DIG

- Define the problem

10 min.	Write a Problem Statement clearly defining what you intend to accomplish with this DIG

15 min.		Outline the current process

5 min.		Determine if you have enough data to clearly 							define the problem

- What departments are affected?

- When/how often is it a problem?

5 min.	      Make assignments in preparation for meeting  #2

ROSTER

Attendees:			        Dept:

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

DIG Meeting #1

Define the Problem

CQI Tools To Use

- Brainstorming

- Survey

- Customer Feedback

- Sampling

- Benchmarking

- Interviews

- Focus Groups

See CQI Tools section for more information regarding the

use of the tools.

MEETING #1:  IDENTIFY THE PROBLEM		DIG# _________

What Depts are Affected? (Identify Stakeholders)		5 Minutes

Discussion:_____________________________________________________________________________________________________________________________________

Conclusions:_____________________________________________________________ 
______________________________________________________________________

Action Items:_____________________________________________________________

Person Responsible_________________________       Deadline _______________________

When/How Often is it a Problem?			        5 Minutes

Discussion:_____________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________ 
______________________________________________________________________

______________________________________________________________________

Action Items:______________________________________________________________

Person Responsible ________________________       Deadline _______________________

Any Questions?				                        5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:____________________________________________________________________________________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

______________________________________________________________________

Review Meeting/Assignments			               5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions: _____________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

DIG Meeting #2

Outline Causes and Identify Solutions

Purpose

The team must identify the possible causes of the problem and zero in on root causes.  A good technique to follow is to ask the question “Why?” five times for each cause.  Following the identification of root causes, possible solutions can be developed.  Be sure to identify a number of solutions to the problem.  There is never just one answer.  When there are several solutions identified, begin processing or analyzing each solution to choose the best one to solve the problem.  In order to sell your solution to others you need to show them you have completely thought through the problem and considered all alternatives - choosing only the best.

Pre-Meeting Checklist

DIG Meeting #2

Outline Causes and Identify Solutions

Planning Checklist

Set up meeting with co-chair to complete the following items:

   Review minutes from meeting # 1 for deferred agenda

topics

Review CQI tools

Determine which CQI tools to use at meeting

Schedule meeting room

    Prepare agenda for meeting # 2.  Include deferred

agenda topics from meeting # 1

Send meeting # 2 agenda to DIG members

Obtain appropriate equipment (overhead, flipchart easel)  from the Library

Complete homework assignments

DIG Meeting #2

Outline Causes and Identify Solutions

Meeting Agenda

5 min. 		Review notes from last meeting

- Have members sign an attendance sheet

5 min.		Review assignments

- Report on information obtained

10 min.		Brainstorm causes

15 min.		Identify solutions

10 min.	Analyze/choose solution

- Write a statement clearly defining what solutions/improvements

are recommended

5 min.			Review notes and make assignments in preparation

for meeting #3

ROSTER

Attendees:			        Dept:

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

DIG Meeting #2

Outline Causes and Identify Solutions

CQI Tools To Use

- Brainstorming

- Fishbone diagram

- Multivoting

- Cost Benefit Analysis

- Cycle Time Analysis

See CQI Tools section for more information regarding the

use of the tools.

MEETING #2:  IDENTIFY THE PROBLEM		DIG# _________

BRAINSTORM CAUSES?		                               10 Minutes

Discussion:_____________________________________________________________________________________________________________________________________

Conclusions:_____________________________________________________________ 
______________________________________________________________________

Action Items:_____________________________________________________________

Person Responsible_________________________       Deadline _______________________

IDENTIFY SOLUTIONS			        	               15 Minutes

Discussion:_____________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________ 
______________________________________________________________________

______________________________________________________________________

Action Items:______________________________________________________________

Person Responsible ________________________       Deadline _______________________

ANALYZE/CHOOSE SOLUTION				       10 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:____________________________________________________________________________________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

______________________________________________________________________

Review Meeting/Assignments			               5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions: _____________________________________________________________

Pre-Meeting Checklist

DIG Meeting #3

Implementation Plan (Action Plan)

Planning Checklist

Set up meeting with co-chair to complete the following items:

Meet or talk with your MAC contact regarding progress of DIG

    Review minutes from meeting # 2 for deferred agenda topics

Review CQI tools

Determine which CQI tools to use at meeting

Schedule meeting room (Call ext. XXX)

    Prepare agenda for meeting # 3.  Include deferred agenda topics from meeting # 2

Send meeting # 3 agenda to DIG members

Obtain appropriate equipment (overhead, flipchart easel) from the Library

Complete homework assignments

Purpose

Many excellent solutions do mature due to sloppy implementation.  Be organized in developing your implementation plan. This includes obtaining input from all key stakeholders.  (You may elect to invite stakeholders to the meeting).

Devise an action plan and implementation schedule to manage the process. List each step that must be taken, the timeframe within which it is to be done and who is responsible for each step. Each action plan should include a communication and education plan.  The communication and education plan outlines who receives the information or training, what information needs to be communicated and what type of training should be offered. Once completed, the chair will send the recommendations, implementation plan, and Return on Investment (ROI) analysis to the MAC contact for assistance.

DIG Meeting #3

Implementation Plan (Action Plan)

Meeting Agenda

5 min. 		Review notes from last meeting

- Have members sign an attendance sheet

5 min.		Review assignments

- Reports on information obtained

30 min.		Develop implementation Plan

- List steps and timeframes that are involved in implementing solution

5 min.		Determine who will be affected?

- List individuals/departments that will be affected and involved in implementing solution

5 min.	How will we communicate this change?

- List methods to effectively communicate

5 min.		Review meeting notes and make

assignments in preparation for meeting #4

DIG Meeting #3

Implementation Plan (Action Plan)

CQI  Tools

- ROI  (Return on Investment)/Cost Benefit Analysis

- Flowcharting

See CQI Tools section for more information regarding the

use of the tools.

ROSTER

Attendees:			        Dept:

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

MEETING #3:  DEVELOP IMPLEMENTATION PLAN	DIG# _________

IMPLEMENTATION PLAN DISCUSSION	                               30 Minutes

Discussion:_____________________________________________________________________________________________________________________________________

Conclusions:_____________________________________________________________ 
______________________________________________________________________

Action Items:_____________________________________________________________

Person Responsible_________________________       Deadline _______________________

WHO WILL BE AFFECTED?			        	               10 Minutes

Discussion:_____________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________ 
______________________________________________________________________

______________________________________________________________________

Action Items:______________________________________________________________

Person Responsible ________________________       Deadline _______________________

HOW WILL WE COMMUNICATE THIS CHANGE				 5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:____________________________________________________________________________________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

______________________________________________________________________

Review Meeting/Assignments			               5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions: _____________________________________________________________

DIG Meeting #4

Test Changes/Track Results

Purpose

Once the team has agreed upon your action plan and implementation schedule, a monitoring system to follow the results is needed.  The monitoring system will outline the method to track the results of your work and find out how the changes are doing. The monitoring system must help to determine a baseline (current data before changes) in order to effectively measure the impact of the change.  As the plan is being developed, keep the following questions in mind:

1.	Is the customer happy?

2.	What expectations are not yet met?

3.	What does the data show?

4.	What do Associates report?

5.	Who needs a report on progress?

6.	What problems still exist?

7.	Was the solution adequate? If not, what else can be done?

8.	What tangible payoff has been provided?

9.	What intangible payoff has been provided?

10.	Was the result worth the work?

11.	Should the results be communicated? If so, how?

During this meeting, the DIG evaluation forms should be returned to the DIG chair for summarizing.  This will provide the DIG chair with valuable insight regarding facilitation of meetings and outcome of the DIG.

Pre-Meeting Checklist

DIG Meeting # 4

Test Changes/Track Results

### Planning Checklist

Set up meeting with co-chair to complete the following items:

Meet or talk with your MAC contact regarding progress of DIG

   Review minutes from meeting # 3 for deferred agenda topics

Review CQI tools

Determine which CQI tools to use at meeting

Schedule meeting room (Call ext. 4100 to schedule meeting room)

    Prepare agenda for meeting # 4.  Include deferred agenda

topics from meeting # 3

Send meeting # 4 agenda to DIG members prior to next meeting

   Obtain appropriate equipment (overhead, flipchart easel) from the Library

Complete homework assignments

Obtain DIG evaluations for distribution to DIG members

Decide how to celebrate and recognize accomplishments

DIG Meeting #4

Test Changes/Track Results

Meeting Agenda

5 min. 	Review notes from last meeting

- Have members sign an attendance sheet

- 5 min.		Review assignments

- Report on information obtained

- 5 min.		Determine tangible cost

- 5 min.		Determine intangible costs

- 5 min.		Determine tangible benefits

- 5 min.		Determine intangible benefits

- 10 min.	Complete Cost Benefit Analysis

- 5 min.		Complete Return on Investment (ROI) portion of DIG report

- 5 min.      	Determine tracking system

- List how results will be measured and monitored

- List who will be responsible for tracking

- 5 min      	 Review meeting and make assignments in

- preparation for 60-Day Follow-up meeting or

- meeting #5

- DIG Meeting #4

- Test Changes/Track Results

- CQI Tools

- Survey

- Sampling

- Interviews

- Variance Analysis

- See CQI Tools section for more information regarding the use of the tools.

ROSTER

Attendees:			        Dept:

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

_____________________	______________

MEETING #4:  TRACK RESULTS/EST MONITORS    	DIG# _________

REVIEW NOTES FROM LAST MEETING	                               5 Minutes

Discussion:_____________________________________________________________________________________________________________________________________

Conclusions:_____________________________________________________________ 
______________________________________________________________________

Action Items:_____________________________________________________________

Person Responsible_________________________       Deadline _______________________

REVIEW ASSIGNMENTS:			        	                       5 Minutes

Discussion:_____________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________ 
______________________________________________________________________

Action Items:______________________________________________________________

Person Responsible ________________________       Deadline _______________________

DETERMINE TANGIBLE COSTS				 	      5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

Conclusions:____________________________________________________________________________________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

DETERMINE INTANGIBLE COSTS			                     5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

- Conclusions: _____________________________________________________________

DETERMINE TANGIBLE BENEFITS				 	      5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

DETERMINE INTANGIBLE BENFITS			                     5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

______________________________________________________________________

- Conclusions: _____________________________________________________________

COMPLETE RETURN ON INVESTMENT (ROI) FORM		             5 Minutes

Discussion:_______________________________________________________________

______________________________________________________________________

Conclusions:____________________________________________________________________________________________________________________________________

Action Items:______________________________________________________________

Person Responsible________________________      Deadline_________________________

______________________________________________________________________

DETERMINE TRACKING SYSTEM AND WHO IS RESPONSIBLE FOR IT	5 MINUTES

Discussion:_______________________________________________________________

______________________________________________________________________

- Conclusions: _____________________________________________________________

REVIEW MEETING ASSIGNMENTS			                      5 Minutes

Responsible parties:_________________________________________________________

- Date Due: _______________________________________________________________

- Notes: __________________________________________________________________

- MAC PRESENTATION MEETING

- Purpose

- After the DIG has developed an action and monitoring plan, the DIG chair or any member of the DIG should prepare to present their recommendations to the MAC.  Be prepared to hear additional ideas on how the solution may be enhanced even further.  Receive new ideas with enthusiasm and consider the merits if possible.

MAC PRESENTATION MEETING

- PRE - PLANNING CHECKLIST

-     Individuals or departments affected have been contacted and

- signed the DIG report

-     Participating DIG members have signed the DIG report.

-     Discuss recommendations with MAC contact

-     Call MAC recorder at ext. 5155 to get on agenda

- POST - MEETING CHECKLIST

-  Attend MAC meeting and present recommendations to MAC

- Communicate MAC recommendations to DIG members

- Follow through with MAC recommendations

- Prepare for an EVC presentation (if necessary)

- Pre-Meeting Checklist

- DIG Meeting #5

- Follow-up

- Purpose

- The DIG should meet again 60-Days after all changes have been made.  The purpose of this meeting is to evaluate the results-to-date.  Adjustments should be made at this time and sent to the MAC.

- Planning checklist

- Set up meeting with co-chair to complete the following items:

-   	 Review minutes from meeting # 4 for deferred agenda topics

- 	Review CQI tools

- 	Determine which CQI tools to use at meeting

- 	Schedule meeting room

-     	Prepare agenda for meeting # 5.  Include deferred agenda

- topics from meeting # 4

- 	Send meeting # 5 agenda to DIG members

- 	Obtain appropriate equipment (overhead, flipchart, easel)

- from the Library

- 	Complete tracking homework

- DIG Meeting #5

- Follow-up

- Meeting Agenda

- 5 min.    Review notes from last meeting

- Have members sign an attendance sheet

- 10 min.	Review results from implemented change

- Report on information obtained

- 10 min.     Determine any changes that need to be made

- 10 min.     Complete 60-Day follow-up report

- 5 min.     Report on information obtained

- 20 min.    Celebrate your success!!

MEETING #5:  FOLLOW UP    	DIG# _________

REVIEW RESULTS FROM IMPLEMENTED CHANGE	              5 MINUTES

Discussion:_____________________________________________________________________________________________________________________________________

Conclusions:_____________________________________________________________ 
______________________________________________________________________

Action Items:_____________________________________________________________

Person Responsible_________________________       Deadline _______________________

DETERMINE ANY CHANGES THAT NEED TO BE MADE               5 MINUTES

Discussion:_____________________________________________________________

______________________________________________________________________

______________________________________________________________________

Conclusions:______________________________________________________________ 
______________________________________________________________________

Action Items:______________________________________________________________

Person Responsible ________________________       Deadline _______________________

- Congratulations!!

- Celebrate your Success!!

DIG CHAIR EVALUATION FORM

______________________________________________________________________________

Name of DIG

_____________________________________

Name of Chairperson

YES	    NO

1.	Did the Chairperson help the group clarify tasks and operate within

the parameters of the 4 step D.O.I.T. process?				____	   ____

2.	Did the Chairperson conduct a minimum of 1 meeting weekly?		____	   ____

3.	Did the Chairperson bring results in on time?				____       ____

4.	Did the Chairperson delegate minutes preparation?				____       ____

5.	Did the Chairperson keep meetings to 1 hour maximum?			____	   ____

6.	Did the Chairperson delegate appropriately with designated tasks to

be completed before the next meeting?					____	   ____

7.	Did the Chairperson maintain the focus of  meetings?			____	   ____

8.	Did the Chairperson facilitate participation from group members?		____	   ____

Comments: ____________________________________________________________________

______________________________________________________________________________

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Please return this form to the DIG Chairperson.  Thank you in advance for your cooperation.

DIG EVALUATION

Please complete and return this form to the DIG Chairperson at the last meeting.  The chairperson will share results with the MAC contact assigned to this DIG

DIG Title: _____________________________________________________________________

DIG Chairperson: _______________________________________________________________

Name					    Dept.          		Extension

1.	I was:

______ Member of this DIG

______ Chairperson of this DIG

2.	What number of DIG meetings did you attend?  Check one.

______ All     ______ 4     ______ 3     ______ Less than 3

3.	Did the DIG complete its work within 45 days?

______ Yes        ______ No    If no, please explain: _____________________________

_______________________________________________________________________

_______________________________________________________________________

4.	Will the recommendations from your DIG solve the problem(s) identified?

______ Yes        ______ No    If no, please explain: _____________________________

_______________________________________________________________________

For the following questions, please circle the best response:

Highly			  Highly

Disagree    Disagree    Agree      Agree

5.	The goal of the DIG was clearly defined.			    1	      2	      3	     4

6.	The DO-IT process was used.				  	    1	      2	      3	     4

7.	Action occurred in a timely manner.				    1	      2	      3	     4

8.	Group discussion was relevant to the task.			    1	      2	      3	     4

9.	The group members worked well together on this DIG.		    1	      2	      3	     4

10.	All members had an opportunity to provide input.		    1	      2	      3	     4

11.	All members contributed to the work of this DIG.		    1	      2	      3	     4

12.	Recommendation resulted from group consensus.	  	    1	      2	      3	     4

13.	All members attended at least 4 meetings.			    1	      2	      3	     4

14.	Chairperson did a good job of facilitating the group.		    1	      2	      3	     4

DIG EVALUATION - Form D

Page 2

Highly			  Highly

Disagree    Disagree    Agree      Agree

15.	The chairperson helped to focus the work of the group.	    	    1             2	      3	     4

16.	The MAC assisted the DIG upon request.			    1	      2	      3	     4

17.	The goal of the DIG was achieved.				    1	      2	      3	     4

18.	Being on this DIG was a positive experience for me.		    1	      2	      3	     4

19.	Suggestions for the improvement of future DIGs.

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

20.	Please list any feedback/recommendations that you may have for the:

a.  Chairperson _________________________________________________________________

___________________________________________________________________________

b.  Specific Group Member _______________________________________________________

___________________________________________________________________________

21.	Would you be willing to serve on another DIG?   ______ Yes        ______ No

If no, please explain: ____________________________________________________________

_____________________________________________________________________________

_____________________________________________________________________________

Signature ___________________________________________________ Date_______________

- GLOSSARY

- OF

- TOOLS AND TERMS

- THE NEW DO-IT GROUP AND

- JUST DO IT LANGUAGE

| - The New American Hospital Language |  |  |
| --- | --- | --- |
| - BHAG | - Big Hairy Audacious Goals | - A stretch goal-reflects an important standard that everyone in the organization aspires to meet. BHAGs are present targets that fire the imagination, provide challenges. |
| - BHAG - Council | - Big Hairy Audacious Goals Council | - Individual councils comprised of leaders who focus on one BHAG and develop an mechanism to improve the results: QUALITY--BEST PEOPLE--CUSTOMER SATISFACTION—PRODUCTIVITY |
| - CAC | - Communication Action Council | - Responsible for publicizing all programs, changes and events. |
| - CQI | - Continuos Quality Improvement | - Principles and methods for achieving enhanced health care outcomes, delivering caring personal service and providing user-friendly and cost effective systems. |
| - DIG | - Do It Group | - Project teams that look for improvement opportunities (not committees that go on forever and accomplish little or nothing). Teams focus on a single, specific issue within thirty days. The goal is improvement (not perfection) with emphasis on swift results. |
| - EVC | - Executive Vision Council | - Group comprised of executive team and MAC. Addresses issues concerning the change effort. Looks at the overall direction and strategy. |
| - JDI | - Just Do It | - Suggestion that does not require a DIG or is clearly within someone’s responsibility to complete. May be department or individual - process specific that does no effect another area. |
| - KRA | - Key Result Areas | - 7 Major Concentrations: - Customer Service, Quality, People Growth, Innovation, Organization Climate, Productivity, Economics |
| - MAC | - Management Action Council | - Middle-management committee who steer the various project action teams, actively broker the overall change efforts and implements new systems. MAC chair reports directly to the CEO |
| - MLAC | - Medical Leadership Council | - Responsible for development and presentation of TNT material to the medical staff. Council acts as resource for MAC on physician issues and collaborate with MAC for solutions. |
| - MVP - award | - Missions, Values and Philosophy | - Award for associates who successfully integrate Advocate’s value into their daily work life. See associates’ handbook for MVP statements |
| - RSVP | - Recognition - Socialization - Valuing - People | - Responsible for developing and awarding associates for dynamic ideas and achievements and for coordinating social events to celebrate. |
| - SDIG | - Super DIG | - CQI-driven project team that addresses complex clinical and operational issues. Structure is similar to DIG group – larger scale. |
| - TAC | - Training Action Council | - Responsible for development and presentation of TNT material to all the associates and acts as a resource. |

- GLOSSARY OF TOOLS AND TERMS

- Ad-Hoc Membership: A temporary membership to a committee because of the knowledge or experience in a topic.

- Benchmarking: Measuring performance against the best organizations in the world.

- Brainstorming: A free thinking approach to generating as many ideas as possible in a short period of time.

- Conflict Management: Working through differences within a group in order to focus on the task at hand.

- Consensus: Reaching agreement among team members that everyone can live with.

- Cycle time analysis: Documentation of each task, work and wait time involved, the people and process involved to determine what steps can be consolidated or how wait time can be reduced.

- Data Sheets: Data that is gathered by observation in order to detect patterns.

- Facilitation: Process to guide group to discussion and decisions.

- Fishbone Diagram: A tool used to represent the relationship between the same “effect” and all possible causes that influence it. Sometimes referred to as a “cause and effect” diagram.

- Flowchart: Helps to identify the actual and ideal path that a product or service flows in order to identify deviations.

- Ground Rules: Agreement set by a group outlining expectations and operational guidelines. Examples include: how to handle interruptions, beepers, phone calls etc.

- Histogram: A bar graph display of measurement data. e.g. temperature, dimensions. Reveals the amount of variations within a process.

- Multivoting: A decision-making technique designed to reduce a list of more than ten ideas to a manageable number.

- Nominal Group Technique: Allows everyone an equal voice. It is a weighted ranking technique that allows a team to prioritize a number of issues without creating winners and losers.

- Pareto Chart: A special form of a vertical bar graph used to display the relative importance of all candidates or problems. It helps direct our attention and efforts to the most important problems.

- Rank Ordering: A group decision-making technique designed to provide a visual display of the degree of agreement on a list of ten or fewer ideas.

- ROI (Return On Investment): An analysis to determine the financial relationship between cost of implementing a change and the benefits that will result from the change. Both tangible and intangible measures are considered.

- Run Chart: Employed to visually represent data. It is the simplest display of trends within observation points over a specific period of time.

- Scatter Diagram: Used to display what happens to one variable when another variable changes in order to test a theory that the two variables are related.

- Stakeholders: Individuals or departments that will be effected by the recommendations of a DIG. It is necessary to get their approval prior to the implementation of DIG recommendations.

- Structured Discussion: A group decision-making technique designed to lead a group to consensus on a list of five or fewer ideas.

- Variance Analysis: Answering a series of questions helps to clearly understand the problem and prepares group for creating a solution.

- TOOLS SECTION

- Brainstorming:

- Purpose: Generate many & zany ideas

- Avoid small, tunnel, one best answer thinking

- Rules:

- Always visualize on flip charts

- Create options furiously, praise all ideas

- No criticism, no analysis, no discussion

- Do critical thinking last - do ideas fit the facts?

- Techniques:

- Random - most common

- Round Robin - controls contribution

- Paper Slips - least threatening

- Nominal Group Technique - paper slips plus discussion plus group thinking

- When brainstorming, always use a flip chart or large board to record all ideas as they are generated.  A large board is important because all participants should be able to see the list as it is being created.  The four most often used techniques in brainstorming are:

- Random:  People voice their ideas as they are generated.  There is no pattern or priority to the process.  This is the most common style of brainstorming.  Some people feel stifled by this style.

- Round Robin Style:  Go around the room one by one in a sequence, each person being responsible for giving a new idea.  This style is easiest to facilitate, and forces participation.

- Paper Slip Style:  Each person writes down his or her ideas on a slip of paper.  The papers are put into a hat and the facilitator draws ideas from the hat, reading them to the group.  Others in the room add to the idea list as they go.  This style is more comfortable for those who are shy.

- Nominal Group:  Paper slip technique plus discussion plus group thinking.

- Usage:  Creating ideas.

- Multivoting:

- When an adequate number of ideas have been generated, and the group has nothing more to add to the list, it is time to process the ideas.  The objective in processing a list of ideas is to separate those ideas, which the group feels are most important, need rapid attention, or have greatest impact, etc., from the others.  This is best through a voting or ranking of the ideas.

- Surveys:

- Used to collect data from people relative to their “feelings,” “plans,” or “opinions.”  It is an “interview on paper.”

- Usage: effective in gaining input from a large group of people, or gaining input on a variety of topics.

- Source of Surveys/Feedback:

- Customers

- Vendors

- Visitors

- Results of the process

- Personal behaviors

- Competitors

- Physicians

- Types of Surveys:

- Oral

- Written

- One on one

- Customer Feedback:

- The Value of Feedback:  Feedback is information provided to an individual or group about its performance.  It is a score keeping system.  In business, the activity of accounting was developed to “keep score” of performance.  Score keeping and feedback are imperative to successfully completing improvement initiatives.

- Guidelines for Effective Feedback:  Feedback knows no boundaries.  Peers give feedback to one another and supervisors, and supervisors give feedback to associates.  Communication is feedback.  It occurs regularly, in casual settings, and in formal meetings.  Effective feedback must have certain characteristics.

- Effective Feedback is:

- Specific, immediate, and honest

- Defines performance in a measurable way that is meaningful to the team

- Frequently and consistently provided

- Positive, whenever possible

- Sampling:

- The selection of a specific group representative of a larger group.  For example, selecting 25 students out of a class of 100 would be a sampling of the class.  Usage: Effective in getting a rough idea of how the normal portion of a large group would respond to something.

- Interviews:

- Provide qualitative (a persons feelings, thoughts or opinions that are subjective) data collected from people, usually on a one-to-one basis, or sometimes in a group.  It is a forum for exploring answers in detail, and getting a clear understanding of the response.

- Usage:  Effectively used to probe the detailed opinion of one person, or one aspect of the problem.

- Focus Groups:

- Groups of people who share a common part of the process (i.e. input or output), coming together to talk about their feelings and thoughts.

- Usage:  To gain insight to the opinions and actions of others, and to generate ideas for added value.

- Benchmarking:

- Benchmarking is the comparing of an organizations’ practices or products against the world’s best.  It can occur within your own industry or outside your industry.  Are we as good as they are?  If not, what can we learn and adapt from them?

- Usage:  Setting better/greater goals, identifying improved ways of doing work, improving clinical outcomes.

- Fishbone Diagram:

- The Cause & Effect diagram was developed to represent the relationship between some “effect” and all the possible “causes” influencing it.  The effect or problem is stated on the right side of the chart and the major influences or “causes” are listed to the left.

- Cause & Effect diagrams are drawn to clearly illustrate the various causes affecting a process by sorting out and relating the causes.  For every effect there are likely to be several major categories of causes.  The major causes might be summarized under four categories referred to as the 4M’s: Manpower, Machines, Methods, and Materials.  In administrative areas it may be more helpful to use the 4P’s:  Policies, Procedures, People, and Plant.  Remember that these categories are only suggestions.  You may use any major category that emerges or helps people think creatively.

- A well-detailed Cause & Effect diagram will take on the shape of fishbones and hence the alternate name Fishbone Diagram.  From this well-defined list of possible causes, the most likely are identified and selected for further analysis.  When examining each cause look for things that have changed, deviations from the norm or patterns.  Remember, look to cure the cause and not the symptoms of the problem.  Push the causes back as much as is practically possible.

- Steps in Constructing a Cause and Effect Diagram:

- Place the problem statement in the box on the right (under the fish’s eye).

- List all the sources of the problems that you can think of.  Group thinking and brainstorming are good to use here.

- The Intent of the Fishbone Diagram:

- To organize you thoughts around what is causing the problem.  Once organized and visualized, it is easier to zero in on the most likely root causes.

- Usage:  Organizes brainstorming on causes of a problem or ways to effect a solution.

- Cycle Time Analysis

- A cycle time analysis chart is designed to document each task that is done, including the amount of time, distance, and people involved in each step.  Using this information, the cycle of work can be analyzed.  Tasks and/or time frames can be reduced, eliminated, or consolidated.  It is different from a flowchart in that the degree of detail is greater and it focuses on time reduction.

- Usage:  Identifies where and how work steps can be consolidated and wait time reduced.  Effective in studying resource consumption (such as time or materials), or improving clinical outcomes.

Flowcharting

- Flowcharting is a means of documenting a process.  It makes the process visual, spots bottlenecks, assists in the evaluation of alternatives, and is the basis for joint understanding.  When changes are made in a process, documentation of the revised process clearly communicates what actions are being taken, and preserves the intended process.  Flowcharting a process makes it easier to find ways to improve it.  Waiting times can be easily identified as well as steps that could be combined, eliminated, or changed.

- Usage:  Documents current processes, and communicates process flow.  Effective in studying a system for improvement, in consolidating a process, saving time, saving space, or savings steps in a process.

- Flowchart  Symbols

Begin or End

Decision

Process

NO

YES

- Variance Analysis

- It is often not enough to identify the cause of the problem.  We also need to understand the cause of the variance.  If your group is good at problem solving and feels confident that fish-boning has been enough, then you might choose not to use the variance analysis tool.

- These 5 questions provide the information needed to analyze the variance cause and assist in finding a solution.

- 1.  What is the problem?

- 2.  Where is it located?

- 3.  When does it occur?

- 4.  Who does it affect?

- 5.  What size or magnitude is it?

- Usage:  Determining root causes of problems, or analyzing why a system is not working when it used to.

- COST BENEFIT ANALYSIS

- DETERMINING THE

- RETURN ON INVESTMENT (ROI)

- PURPOSE

- A method used to define the relationship between the costs of a change, (financial and non-financial) and the benefits derived from the change.  This process will help you to make a good decision and is the first step in determining the ROI.

- Why?

- To put a dollar value on benefits

- To evaluate an option financially

- To show the cost effectiveness of a decision

- HOW?

- 1.  Decide on the time period that you will analyze.

- 2.  Brainstorm all related COSTS.  Research and determine the

- dollar value of each cost listed, and give a total.

- 3.  Brainstorm all related BENEFITS.  Research and determine

- the dollar value for each, and give a total.

- 4.  Divide the TOTAL BENEFITS by the TOTAL COSTS.

- ROI/Cost Benefit (Cont.)

Costs = Cost Benefit Ratio Benefits

- *  The larger the number, the better the return on investment.

- (benefit dollars returned per dollar spent to change)

- There are two types of Costs and two types of Benefits.

- 1.  Tangible:  those things that you can see, touch and feel - $$

- 2.  Intangible:  those things that you cannot physically see, touch or feel.

- EXAMPLE

- OPTION #1: To Recycle Paper Analysis Period: 1 year

- Tangible Costs/Dollar Value	     Tangible Benefits/Dollar Value

- Labor (internal pick-up)    $5,000	       	  Revenue                                    $25,000

- Cartage    		       2,500              	 Receptacles (provided free)                 0

- Pick-up &  processing        7,500	              City Incentives (tax credit)             5,000

- $15,000                                                                           $30,000

- Intangible Costs               	       Intangible Benefits

- Dedicated space           		                Less natural resources used

- Confidentiality of information			   Less energy expended

- may be compromised            			   Safegaurds environment

- Costs       =   Cost Benefit Ratio  =    15,000      =  0.5

- Benefits                                         30,000

- EXAMPLE

- OPTION #2: Not To Recycle Paper  Analysis Period: 1 year

- Tangible Costs/Dollar Value	     Tangible Benefits/Dollar Value

- City Fines (occurrence)       $5,000		  Savings from Cartage fee         $2,500

- (3) Shredders                     1,500		  Pick-up &  processing                7,500

- Labor (shredding)	       20,500		  Dedicated Internal labor             5,000

- $27,000                                                                     $15,000

- Intangible Costs               	       Intangible Benefits

- Hazardous environment			  Less effort

- Natural resources not protected    		  Space reallocated

  Confidentiality of information protected

Costs       =   Cost Benefit Ratio  =    27,000      =  1.8

Benefits                                         15,000

Which is the best decision?

How does this translate to Return on Investment?

Translating Cost Benefit

Ratio to a ROI

When the cost/benefit ratio is less than one, a positive financial situation exists:

The benefits are greater than the costs.

For example, if a cost benefit ratio is 0.5/1.8, it means that for every $0.50 of cost invested, $1.80 of benefit is received.

APPENDIX

DIG Member Letter

To:   DIG Member

From:

Re:   DIG #

Date:

Thank you for volunteering to participate on DIG # _______.  The following schedule will be the dates of our meetings.  Meetings will last for one (1) hour.  The first meeting will be at:

_______(time) on __________(day/date) in the _____________

department of  ___________(location).

2nd Meeting_______________

3rd Meeting________________

4th Meeting_________________

All meetings will be at (time)  _________in the following location________________.

Your manager is getting a copy of this memo indicating that attendance is required for DIG participation and time needs to be allotted for your attendance.  Additionally, attendance issues will be reviewed with managers to verify cause.  The meetings require strict attendance for effective and timely outcomes.

DIG Communication

Date:

To:

From:    DIG Chairperson

Re:        DIG #

____________________________________________________

Thank you for volunteering for the above DIG.  In order to keep the group effective, it is necessary to ensure “balanced” representation for all affected departments and limit members to seven.  Unfortunately, due to these constraints, it is not feasible to appoint you as a DIG member at this time.  Please do not be disappointed or discouraged.  Your continued input and participation are very important.  You are encouraged to contact any DIG member to voice your opinion for this or any other DIG.

Again, thank you for volunteering and please take advantage of opportunities to sign-up for a future DIG.

DIG REPORT RESPONSE LETTER

DATE:

TO:

FROM:         MANAGEMENT ACTION COUNCIL (MAC)

SUBJECT:	  REVIEW OF YOUR FINAL DIG REPORT

Congratulations on completing your DIG focusing on ________________________________________________________________________________________________________________________________!

We appreciate the time you took to serve as chair of DIG# ______ and are proud of your efforts.  We hope you will continue to participate in future DIGs and JDIs.

After reviewing your final report, the MAC:

1. Has approved all of your DIG’s recommendations.  You

may now move ahead with implementation.  Within 60

days, please submit the attached follow-up form to keep the

MAC posted on your team’s progress and success.

2. Has approved your DIG’s recommendations with the

following suggestions:

___________________________________________________

___________________________________________________

Please integrate these suggestions into your implementation

plan, then	move ahead with implementation.  Within 60 days,

please submit the attached follow-up form to keep the MAC

posted on your team’s progress and success.

3. Would like to ask for some further details before approving

implementation of your recommendations.  Please provide the

following additional details to the MAC:

_____________________________________________________

_____________________________________________________

These details should be submitted to the MAC by:  ______________

After reviewing these details at the next MAC meeting, we will

respond quickly to you.

Thanks again, for the leadership you offered in support of this idea.  Your DIG is accomplishing meaningful results.

DIG REPORT

DIG Chair:

SECTION I:  DIG Chair Basics

Congratulations on being assigned to chair DIG #

DIG Title:

Your DIG Chair Training is scheduled for                                                            in the H.R. conference room.  Call  (     )  e in H.R. (Innovation & Learning) at Ext. (     )  if you are unable to

attend.  Training is scheduled only once a month, so please try to attend on the above date.  Also, see

(insert name) in (insert name) Dept. to pick up your training manual before the class date.

See the attached sign-up sheet for a list of your DIG members.  If there are spaces where a

department was specified but no one signed up, please contact the department leader to ask for a

representative for your DIG.  You may then notify your members of your first meeting date, which

should occur shortly after DIG chair training.

The MAC contact assigned to your DIG is ______________________________________.

Your completed DIG report is due to the MAC on or before  ________________________.

Contact your MAC Liaison if you cannot or have not completed your DIG by the assigned date.

SECTION II:  Recommended Solution

What is the current situation:

What solutions/improvements is recommended (list each separately):

What steps are involved in implementing solution:

Which individuals/departments will be involved in implementing solution:

Target date for implementation of solution:

How will results be measured and monitored:

SECTION III:  Cost/Benefit Analysis

Tangible Costs:	$ Value				Tangible Benefits:	$ Value

Intangible Costs:						Intangible Benefits:

Cost/Benefits Ratio:  Total Benefits= _________

Total Costs

SECTION VI:  Key Stakeholder Sign-off

Prior to submitting completed form to the MAC, have all key stakeholders (those outside the DIG

who will be involved in/affected by solution) sign-off below to indicate they have reviewed

recommendations and agree with implementation plans.

_______________________________________     __________________________________

_______________________________________     __________________________________

SECTION V: Participating SECTION DIG Members

List below those associates who actively participated on this DIG.

______________________________________	_____________________________________

______________________________________	_____________________________________

_____________________________________	_____________________________________

SECTION IV:  Values/KRA Check

How does recommended solution relate to The New American Hospital Values Statement?

How does the recommended solution impact the KRA’s?

SECTION III:  Cost/Savings Analysis

1)  What is the annual cost of implementation? _____________

a) List each item separately and its related cost.

b) What is the one-time cost (if applicable)? ______________

2)  What will be the annual savings? ____________________

3)  How much  annual  revenue will  be generated? ___________________

SECTION VII:  Implementation Implications

Stakeholders:

1.  Does this DIG group recommend an ongoing processes that someone or some department needs to 	be accountable for owning?						YES	or     NO

2.  If yes, what key stakeholder will be accountable for maintaining the process recommended after 	your DIG group completes its work?

Signature Required _______________________________________________

SECTION VIII:  Implementation Implications

Monitors:

1.  What monitor(s) have your DIG Group chosen to measure the success of your recommendations?

2.  Does your group recommend that these monitors be measured beyond the 60 day follow-up

process?									YES    or   NO

3.  If yes, who will be accountable for monitoring?

Signature Required ____________________________________________________________

SECTION IX:  Implementation Implications

Communication Plan:

1.  Who should receive updates regarding the changes recommended by your group?

2.  How will the information be communicated?

3.  Who will be accountable for communicating the information?

Requires Signature _______________________________________________

SECTION X:  Implementation Implications

Education Plan:

1.  Who needs to receive education or training?

2.  How will the training be accomplished?

3.  Who is responsible for ensuring the training takes place?

Requires Signature _______________________________________________

FOR MAC USE ONLY

Date recommendations reviewed by MAC:

MAC suggestions/questions:

Date of EVC review (if required):

Date approved for implementation: